## Slide 1: 6m (and 8m) scale-up Giorgio Ambrosio Fermilab
BNL - FNAL - LBNL - SLAC
Contributions from:
Fred Nobrega, Rodger Bossert, Guram Chlachidize (FNAL)
Jesse Schmalzle , Mike Anerella, Peter Wanderer (BNL)
LARP Collaboration Meeting 14
Fermilab
April 26-28, 2010
Focus of this talk is on equipment and infrastructure, NOT on tooling
Notes: 1

## Slide 2: 6-8 m coils at FNAL
Winding:
  6m: present table with stronger motor (minor upgrade)
  8m: may need the MQXB winding machine
    Significant upgrade: software and control system
Curing:
  6 and 8m LQ coils: OK
  6 and 8m HQ coils: new curing mold
Reaction:
  6m: present oven is OK
  8m: oven upgrade (major up. with long shutdown)
Impregnation:
  Ovens are OK, but angle is smaller and smaller…

## Slide 3: 6-8 m coils at BNL
Winding:
  6m: Minor upgrades: extend winding machine mandrel shuttle; May also need to modify or build additional mandrel rotating supports
  8m: Extend winding machine base and winding supports
Curing:
  6 and 8m: extend curing press
Reaction:
  6 and 8m: extend oven (major up. with long shutdown)
Impregnation:
  6m: present equipment is OK
  8m: build impregnation dewar (horizontal or angled)

## Slide 4: Assembly & Test at FNAL
Assembly:
  6m: present press used for 4m mirror
    Need to complete weld-carriage upgrade
  8m: need to check weld press length…
    Length upgrade is possible
Test:
  6m: should reassembly/refurbish “Jessica” cryostat; test-stand should be restored and upgraded (current, QP, …)
  8m: new cryostat

## Slide 5: Assembly & Test at BNL
Assembly:
  6 and 8m: some ideas to be explored
Test:
  6m: Vertical test facility is OK
    Small upgrade needed for HQ coil test (QP)
  8m: new horizonthal cryostat

## Slide 6: Possible plan
Make 6m HQ coil and assemble it in mirror structure at FNAL, and test it at BNL; while upgrading BNL equipment for 8m coils.
  Get results in the shortest time
  Preserve one active long-coil production line
  Build equipment for 8m coils
    Need to evaluate time, cost and funding for this upgrade

## Slide 7: Timeframe
6m coil |  | timeframe | 
Design & procur. parts and tooling | FNAL | FY11 Q1-Q2 | 
Coil(s) fabrication | FNAL | FY11 Q3-Q4 | After LQ03 coils
Mirror assembly | FNAL | FY12 Q1 | 
Test | BNL | FY12 Q2 | 
8m coil |  | timeframe | 
Design & procur. Parts and tooling | BNL |  | Feedback from 6m coil fabric.
Infrastructure and cryostat | BNL |  | Need to develop plans and coordinate funds among LARP, BNL, APUL(?), …