## Slide 1: Group A Summary
Jim Kerby
28 October

## Slide 2: Agenda
650 MHz Cavity RD&D at RRCAT (A. Puntambaker)
650 MHz Cavity RD&D at VECC (S. Som)
650 MHz Cryomodule Design (P. Khare)
SSR1 Cavity Status …. (P. N. Prakash)
650 MHz Cavity Helium Vessel Design (T. Peterson)
650 MHz Blade Tuner Design (H. Carter)
Development of SRF Infrastructure at RRCAT (S. Joshi)
650 Cavity RD&D (con’t) (A. Puntambaker, C. Ginsburg)
650 Cryomodule Comments (con’t) (T. Peterson)

## Slide 3: Status
Cavity R&D efforts at RRCAT consist of an existing effort at 1300 MHz that is being finished and redirected to 650MHz b = 0.9
  Two single cell 1300Mhz are being prepared for second round of tests at FNAL
  Two new single cells will be fabricated shortly thereafter
  Two 7 cell cavities to follow
  Preliminary (Aluminum) 650 half cells have been formed
  650 single cell prototype fabrication will start at the end of Feb 2011; Nb is required
650MHz b = 0.61 Cavity R&D efforts at VECC are underway with RF simulations and cross checks of models
  High RRR 4mm sheet ordered from ATI Wah Chang; delivery March 2011

## Slide 4: Status
650 MHz Cryomodule Design at RRCAT well developed assuming design is Type IV derivative
  Need to check vs. current understanding of optics, cryogenics
  Many engineering calculations in parametric spreadsheets, can be updated relatively quickly
SSR1 at IUAC in final assembly steps; now expected at FNAL May 2011
  Vendor summer period to be accounted for in future planning
  Better status communication needed
SCRF Infrastructure development at RRCAT is advancing
  The D from June is quite impressive!
FNAL single cell 650 MHz prototypes ordered; 5 cell design drawings being prepared
650 MHz Cryomodule cryogenics under review w/ change to CW and segmentation

## Slide 5: Comments
Good(!) discussions started that will continue the next two days.
  Schedule integration, information transfer
Specifications need to be created.
  Project X is pre CD-0…optics+ are changing and becoming more detailed
  However, many ~stable parameters that can be documented
  Relative importance of remaining “TBDs” will come from more detailed discussions

## Slide 6: Suggestions
Nb purchase and supply needs to be integrated
  Legal issues, US-India and internal to India should be addressed
  May apply to other sensitive/difficult items as well
Continue to improve communication
  Use SPM/POCs, more frequent technical, topic specific webex/phone/mtgs (at mutually uncomfortable times)
  Logs of open items / actions
  Data Transfer
  Timely personal contact at collaboration meetings, conferences, specific visits
Continue to work on VISA issues
Write it down
  As needed use ranges, TBDs, and understand there will be revisions in the future

## Slide 7: Agenda
Oct 29
Cavity Helium Vessel
SCRF Infrastructure
VTS Discussion (incl. RF)
Oct 30
HTS Discussion (incl. RF)
650 Cryomodule Discussion
SCRF Cavity Discussion

## Slide 8: Oct 29-30
Useful and active discussions on design, processes, procedures, standards, engineering notes, infrastructure
  Started w/ prepared list of 50+ questions on HE vessel design
Future group webex times set, proposals for future in person meetings
Ordered lists of where to start on cryomodule design
At least one example where a trade may work….650 tuning machine design / mechanics for controls
P. Kush visit to FNAL in next weeks will further help on infrastructure / RF issues
Tom / Camille to report in more detail next week…