## General Info
Fedv6: Agency Transition Results
DRAFT DATA CALL - AGENCIES REQUESTED TO PROVIDE COMMENTS TO OMB
General: The OMB Memorandum titled "Transition to IPv6" and dated September 28, 2010 stipulates two enterprise network goals: 1) "Update public facing/external servers and services to native IPv6 by end FY 2012". 2) "Upgrade internal client applications that communicate with public Internet servers and supporting enterprise networks to use native IPv6 by end FY 2014" The Federal IPv6 Task Force is charged with facilitating Agencies to realize these goals. The following checklists are for use by Agencies to communicate with the Federal IPv6 Task Force and accomplish these goals. OMB and the Federal IPv6 Task Force will use this information to monitor the penetration of IPv6 over time. A Primary Services checklist is provided to list the services specific to OMB Goal 1. An Internal Client Apps checklist is provided to list the services and detail the interim transition steps specific to OMB Goal 2. A Transition Manager checklist is provided to identify and sequence the processes needed to effect transition across all units in the Agency.
3) This checklist shall be completed by April 2011, showing progressive rollout of IPv6 services between April 2011 and September 2012 (for Goal #1) or September 2014 (for Goal #2).
In support of 1) "Update public facing/external servers and services to native IPv6 by end FY 2012": Every Agency should list on the worksheet titled "Primary Services", the URL, the projected IPv6 live date and the completion checkmark for: - Its primary DNS server at each Agency site, and all other DNS servers. - All web servers with publicly accessible content. - The mail server address at every Agency mail server.
The Agency should create a rollout plan with effective dates of transition for each node, progressively spreading from January 1, 2011 to September 30, 2012.
In support of 2) "Upgrade internal client applications that communicate with public Internet servers and supporting enterprise networks to use native IPv6 by end FY 2014": Every Agency should list on the worksheet titled "Internal Client Apps" the type of service, URL, projected IPv6 live date and completion checkmark, as above. The Service column can be as detailed as necessary.
A companion spreadsheet entitled "Fedv6_Transition_Process" contains detailed interim goals for Agency associated Software Developers, Information Assurance Analysts and Network/Systems Administrators and should be used to structure and implement application by application and node by node IPv6 transition activities.

## Primary Services
Fedv6 Task Force Primary Services Worksheet
Agency:
Transition Manager:
Contact Information: Email, Phone
Service | URL | Planned Live Date | Actual Live Date
e.g. Web | web.omb.gov | 2011-06-01 | 2011-05-01

## Internal Client Apps
Fedv6 Task Force Internal Client Applications Worksheet
Agency:
Transition Manager:
Contact Info: Email, Phone
Service | URL | Test Method | Planned Live Date | Actual Live Date
e.g. database | db.omb.gov |  | 2014-06-01 | 2013-12-12

## Transition Manager
Progress: |  | Program Name | … |  | System/Portfolio Name
Number | Category | Query | Proposed Verification Method | Point of Contact | Planned Completion Date | Actual Completion Date | Fedv6 Notes
1 | Transition Planning | Are you in coordination with your Agency IPv6 Transition Manager on the USG transition mechanisms (strategy, schedules, milestones, compliance with policy)? | Coordination/Liaison |  |  |  | Agency Transition Manager
2 |  | Have you developed and submitted to your IPv6 Transition Manager appropriate documents/inputs they require for IPv6 (e.g., Transition Plans, Implementation Schedules, Status/Update Reports)? | Coordination/Liaison |  |  |  | ditto. Detail these documents.
3 |  | Have you documented the scope of the bubble slice included in the planned implementation of IPv6? Have you developed a transition strategy based on the scope of the bubble slice and planned solutions for implementation of IPv6 ? Have you developed an IPV6 Transition Plan based on your strategy? | Transition Plan |  |  |  | The terms expanding bubble and bubble are used to describe a fully interconnected routing mesh across multiple enclave domains. A bubble may cross organizational boundaries and traditional routing domains but must be fully interconnected. In other words there can be no isolated islands created when a technology is introduced as an expanding bubble. This is a critical concept to the dual capable system-wide transition strategy. The term bubble slice is used to refer to a new set of nodes being added to an existing bubble.
4 |  | Is the scope of the bubble slice included in the planned implementation of IPv6 under the purview of a single Agency site? If not, is there an MOA or other formal agreement in place between the cognizant sites for the planned implementation of IPv6? | Transition Plan
5 |  | Have you incorporated USGv6 compliant products in your transition planning per the FAR? | Transition Plan
6 |  | Have you identified both internal and external dependencies? | Transition Plan |  |  |  | Public facing vs internal?
7 |  | Have you identified any unique IPv6 requirements from your users? | Transition Plan
8 |  | Does the transition plan for the bubble slice have the support of key stakeholders (e.g., Agency CIO, site CIO)? Have the stakeholders reviewed/contributed to the transition plan? | Transition Plan
9 |  | Have you identified funding sources for the IPv6 transition (Tech Refreshment funding; other funding; provided inputs to POM process)? | Transition Plan/Funding documents
10 |  | Is there a plan for dual-stack operation since IPv4 cannot be removed for a significant period of time? | Transition Plan
11 |  | Is there a plan for an IPv4-only ("Legacy") network segments to accommodate things that cannot ¦ will not support IPv6? | Transition Plan
12 |  | Have you developed a plan to remove any IPv4 configurations, support contracts, or services that are not required once the transition to IPv6 is complete? | Transition Plan
13 |  | Have you developed an implementation schedule for transition, broken down by appropriate waypoints? | Implementation Schedule |  |  |  | et waypoints from MO3
14 |  | Does the schedule include start and end dates for IPv6 Compliant? | Implementation Schedule
16 |  | Is the schedule factored into your technology refreshment schedules? | Implementation Schedule
17 |  | Does the schedule address the availability of hardware and software to implement the IPv6 transition, and mitigations for cases where the level of support is insufficient? | Implementation Schedule
18 |  | Does the schedule address resources and personnel to implement the transition? | Implementation Schedule
20 |  | Is the schedule based upon the available funding (e.g., fully funded, partially funded, or is it unfunded)? | Implementation Schedule
21 |  | Do you have a risk management and mitigation process for IPv6 transition at each of the appropriate implementations? | Risk Management Plan |  |  |  | Analyse MO3 for risk mitigations
22 |  | Do you have a Configuration Management process and mechanism to track all the changes made specific to your environment? | CM Plan
23 | Acquisition | Are you in coordination with your Agency IPv6 Transition Manager and compliant with the FAR and Agency acquisition guidelines? | Acquisition Planning
24 |  | Have you incorporated IPv6 requirements in your acquisitions, per the FAR? | Acquisition Planning
25 |  | Have you incorporated the USGv6 profile? | Acquisition Planning
26 |  | Do your acquisitions for networks (IPv6 products) incorporate Agency guidelines and IPv6 policy and Federal Acquisitions Regulations guidelines for the following:
27 |  | - Use USGv6 tested Products | Acquisition Planning
28 |  | - Accommodate IPv6 in network infrastructure, services, and management tools and applications | Acquisition Planning
29 |  | Conform to NIST security guidelines | Acquisition Planning |  |  |  | list them …
30 |  | - Conform with the requirements of the USGv6 profile | Acquisition Planning |  |  |  | USGv6 profile
31 |  | - In the case of no submitted SDOC meeting the requirements, do you possess a migration plan and/or commitment to upgrade from the developer (i.e., letter) as the IPv6 standard evolves | Acquisition Planning |  |  |  | Point to the SDOC and its description
32 |  | - Ensure product developer IPv6 technical support is available | Acquisition Planning
33 |  | Conform to the USGv6 NPD profile and applicable NIST security guidelines | Acquisition Planning
34 |  | Have you developed a cost estimate for your environment to be IPv6 capable (e.g., procurement, integration, testing)? | Acquisition Planning
35 |  | Have you updated your existing Program life cycle cost estimate to include costs related to IPv6 transition (e.g., training, management and maintenance requirements)? | Acquisition Planning
36 | Address Plan | Have you developed a IPv6 address plan specific to your environment (allocation of address space)? | Address Plan
37 |  | Is your IPv6 address plan in compliance with the Agency IPv6 Address Plan? | Address Plan |  |  |  | NEED A PRESENTATION ON ADDRESS PLANNING; Fedv6 transition plan - and is this complete/comprehensive
38 |  | Have you submitted a IPv6 address space request to the Agency <address allocation authority>? | Address Plan |  |  |  | Agency CIO? N.B. How is Address Allocation doen in each Agency?
39 |  | Have you received IPv6 address space from the Agency <address allocation authority? | Address Plan |  |  |  | Agency CIO? N.B. How is Address Allocation doen in each Agency?
40 |  | If you utilize IP Planning and Address Management (IPAM) tools to assist with address planning, are they also used to aid in deployment to DNS & DHCP servers/services, and are they upgraded for IPv6? | Address Plan
41 | Environment Identification | Have you compiled an inventory of components in the bubble slice? Have you identified those components that need to be IPv6 capable? Does this inventory allow for "legacy" enclaves of IPv4 only devices - which should then have a specified "sunset" timeframe or be designated "long term legacy" device? | Design Review
42 |  | Have you compiled an inventory of software in the bubble slice? Have you identified what software needs to be IPv6 capable? Does this inventory include any software on "legacy" enclaves of IPv4 only devices - which will then need a transition path from the "legacy" enclaves when they sunset? | Design Review
43 |  | Have you verified compliance of all software and hardware components that need to be IPv6 ready? Categories include logical/physical architectures; private/service network; geographic - regional/mobile requirements. | Design Review
44 |  | Have you conducted a Functional Decomposition and developed a IPv6 transition mechanism of major sub-systems including the following ?
45 |  | - Decomposition of: Application/Database/E-mail/OS/Collaboration etc | Design Review
46 |  | - Decomposition of Voice/Video requirements | Design Review
47 |  | - Decomposition of IA requirements | Design Review
48 |  | - Decomposition of networks (routers/gateways/addressing/DNS) | Design Review
49 |  | - Decomposition of servers/clients (various configurations) | Design Review
50 |  | - Identified any external network dependencies | Design Review |  |  |  | Your ISP and/or Networx?
51 |  | - Performed gap analysis of components that have IPv6 patches/release/upgrades (libraries, compilers etc) | Design Review
52 | Test & Evaluation | Have you developed a Test Plan for all the components that need to be IPv6 compliant? | Test Plan |  |  |  | 1. This is integration testing not device testing. 2. substitute memoranda?
53 |  | Have you developed a Test Plan schedule for all the components that need to be IPv6 ready? | Test Plan |  |  |  | Integration test plan
54 |  | Are all the system components tested in USGv6 accredited test laboratories? | Test Plan |  |  |  | Specific to new acquisitions, not existing infrastructure
55 |  | Does the SDOC justify non-accredited testing? | Test Plan
56 |  | Have you developed a component and Interoperability testing plan for your IPv6 environment, relevant to each enclave? | Test Plan
58 |  | Have you determined what is necessary to receive an Authority to Operate (ATO)? | Test Plan
59 |  | Have you identified the location of and equipment configuration in your Program IPv6 device test lab? | Test Plan
60 | Training | Have you identified a Transition Team and their responsibilities? | Charter
61 |  | Have you identified all of the staff (personnel) required to support an IPv6 environment? Don't forget computer operations, network operations, maintenance, help desk, web site developers and maintainers, security, purchasing, technical writers, and training personnel. | Training Plan |  |  |  | Need to identify IPv6 unaware users as a control group to help ensure a seamless transition
62 |  | Have you identified all of the IPv6 specific training requirements for your staff? | Training Plan
63 |  | Have you developed an IPv6 specific training schedule for your staff and developed a tracking mechanism? | Training Plan
64 |  | Does the training include hands-on experience with transition mechanisms, tools and processes presented in a fashion that allows "free form" interaction with a knowledgeable instructor? | Training Plan
YES
NO
N/A