## Slide 1: OTE Building PMG Report 11/29/10
Rhonda Merchut

## Slide 2: Overall Project Summary Status:
OTE Building Final Project Plan updated per Director’s Review. Approval 11/16/10.
OTE Final Design & Construction Support (HOK) RFP completed, negotiated, REQ approval compete 11/23/10. PO to be issued o/a 11/29/10.
OTE Design Coordination RFP (RBA) completed, REQ approval awaiting 2nd floor approval
OTE Task Codes established per State reporting requirements

## Slide 3: Table of Recommendations – Corrective Action Plan
#
Recommendations
Assigned to
Status/Corrective Action
Due Date
Closed
2.0
Project Preparedness
2.1
Cost and Scope
1.
The use of the DOE escalation rate for FY12 is not a recognized best practice. Facility and construction escalation costs have historically been significantly higher than DOE rates. It is recommended more appropriate escalation rates be used for the cost estimate.

## Slide 4: Table of Recommendations – Corrective Action Plan
# | Recommendations | Assigned to | Status/Corrective Action | Due Date | Closed
2.0 | Project Preparedness |  |  |  | 
2.1 | Cost and Scope |  |  |  | 
1. | The use of the DOE escalation rate for FY12 is not a recognized best practice. Facility and construction escalation costs have historically been significantly higher than DOE rates. It is recommended more appropriate escalation rates be used for the cost estimate. | Merchut | Comment withdrawn by J. Budd per email 10/14/10. 5.4% Escalation indicated in PP adequate. |  | 10/14/10
2. | Additional scope items need to be identified, estimated, and prioritized so in the event favorable bids are received during the construction RFP a clear plan is in place for allocating the additional funds. | Merchut | Additional Scope items identification & design included as part of HOK scope of work. | Prelim: 2/1/11 Final: 7/14/11 | 

## Slide 5
# | Recommendations | Assigned to | Status/Corrective Action | Due Date | Closed
2.1 | Cost and Scope |  |  |  | 
3. | Project currently plans include continuation of RBA as LEED project manager to insure the project obtains Gold certification. Project should consider assigning responsibility for LEEDs Gold certification as part of the HOK design contract. In the same manner that “design to cost” is a contract requirement, “design to LEEDs Gold” could also be a delivery requirement. | R. Merchut | LEED Manager responsibility to provide final design documents to achieve LEED Gold, with all supporting documentation, tracking, shop drawing verification, & final systems verification included in HOK scope of services. RBA project coordination RFP is to provide review & oversight of HOK LEED work. |  | 11/18/10

## Slide 6
# | Recommendations | Assigned to | Status/Corrective Action | Due Date | Closed
2.0 | Project Preparedness |  |  |  | 
2.2 | Schedule |  |  |  | 
4. | Create an integrated overall IARC schedule which includes accelerator operation decision points, scheduled shutdowns, the utility upgrade project, and the OTE design and construction schedules. | R. Merchut B. Aprile AD CDF | Baseline integrated schedule for utility upgrade progect and OTE created and will be updated and expanded on-going during final design & construction. Accelerator shutdown dates have not been determined - dependent on Tevetron run, funding. | 6/2/11 | 11/10/10

## Slide 7
# | Recommendations | Assigned to | Status/Corrective Action | Due Date | Closed
2.0 | Project Preparedness |  |  |  | 
2.2 | Schedule |  |  |  | 
5. | Review the OTE project schedule to assure that adequate time is included for performing reviews, addressing recommendations and obtaining signoff/approval of final procurement documents. | R. Kephart R. Merchut | The additional Director’s Review at the end of final design is incorporated into the schedule. Add’l time DOE approvals to be determined and added. | 5/6/11 | 11/10/10

## Slide 8
# | Recommendations | Assigned to | Status/Corrective Action | Due Date | Closed
2.0 | Project Preparedness |  |  |  | 
2.2 | Schedule |  |  |  | 
6. | The impact of vibration due to construction on accelerator operations has not been clearly understood. The committee recommends pre-drilling a prototype casing foundation to measure the impact on operations. | R. Merchut CDF AD | Prototype caisson drilling will be performed when foundation design is better understood during final design phase. The timing of the prototype will be coordinated with AD & CDF, to insure drilling occurs during end of beam run. Schedules dependent on tevetron run. | Spring 2011 | 

## Slide 9
# | Recommendations | Assigned to | Status/Corrective Action | Due Date | Closed
2.0 | Project Preparedness |  |  |  | 
2.3 | Management and Oversight |  |  |  | 
7. | There should be CDF and AD people on the IPT. | R. Merchut P. Czarapata | Dervin Allen has been added for CDF. AD representative to be identified. | 12/15/10 | 

## Slide 10
# | Recommendations | Assigned to | Status/Corrective Action | Due Date | Closed
2.0 | Project Preparedness |  |  |  | 
2.3 | Management and Oversight |  |  |  | 
8. | Retain the Project Managers control over change to a reasonable level, and make the PMG function as the change control board for larger changes. This eliminates the separate change control board and removes the need to check with the PMG for changes that require broader consideration. | R. Kephart R. Merchut | The Project Plan has been revised to eliminate the separate Change Control Board. The PMG is now identified as the Change Control Board. |  | 10/29/10

## Slide 11
# | Recommendations | Assigned to | Status/Corrective Action | Due Date | Closed
2.0 | Project Preparedness |  |  |  | 
2.3 | Management and Oversight |  |  |  | 
9. | Project management should convene a working group or mini-review where operations experts can work with the FESS to ensure the proposed building construction steps fit the schedule and minimally impact operations, e.g. CDF, TD, Road D, fire response, etc. | R. Merchut | To be conducted during Concept validation. Additional reviews will take place as the design develops | 12/30/10 7/14/11 | 

## Slide 12
# | Recommendations | Assigned to | Status/Corrective Action | Due Date | Closed
2.0 | Project Preparedness |  |  |  | 
2.3 | Management and Oversight |  |  |  | 
10. | There should be a review prior to submitting an RFP for the construction contract to ensure that the cost, schedule and interface conditions are well understood. | R. Merchut | A Director’s Review at the conclusion of Final Design has been added to the schedule. | 7/21/11 | 

## Slide 13: Fiscal – EDI Professional Services
Chart: 
| OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP
COSTED | 0
Prof Serv Oblig | 941000 | 25000 | 456000
OTE Bldg EDI (601) | 2707150 | 2707150 | 2707150 | 2707150 | 2707150 | 2707150 | 2707150 | 2707150 | 2707150 | 2707150 | 2707150 | 2707150
Prof Serv Projected | 134400 | 134400 | 134400 | 159400 | 134400 | 134400 | 134400 | 22800 | 22800 | 22800
Total | 134400 | 268800 | 403200 | 562600 | 697000 | 831400 | 965800 | 988600 | 1011400 | 1034200

## Slide 14: Schedule Resource loaded schedule in progress
Tracking Milestone | Definition | Target Date | Date Accomplished
OTE Building |  |  | 
CDR Complete | RBA delivers CDR document | 6-Oct-10 | 6-Oct-10
Director’s Review | Review by FNAL mgmt of Proj Plan | 13-Oct-10 | 13-Oct-10
Engineering Start | Proj Plan approved, directorate sign-off | 18-Nov-10 | 16-NOV-10
A/E start | Proposal negotiations complete, PO issued | 18-Nov-10 | 
Concept Validation |  | 30-Dec-10 | 
30% Final Design OTE building |  | 24-Feb-11 | 
Pre-Final Design OTE Building |  | 19-May-11 | 
CC Review Building Final Design |  | 16-June-11 | 
Eng Drawings complete | CCR comments incorporated | 7-Jul-11 | 
Director’s Review | Review by FNAL management for cost, schedule, & interface conditions per 10/13/10 Director's Review | 21-Jul-11 | 

## Slide 15: External Milestones
IASU: Final Design Complete 1/28/11
Accelerator Shutdown(s): TBD

## Slide 16: Risk Management External Risk Status
IASU Final design (BMD) RFP negotiated, PO issued, design underway
IASU Design Coordination RFP (RBA) completed, REQ approval awaiting 2nd floor approval
IASU Wetlands investigation underway. Draft application for JD from COE underway, coordinated with DOE (Rick Hersemann), ES&H (Teri Dykhuis)
IASU concept revisions for new parking lot and horseshoe sidewalk buy-in by TD, ES&H, FD, R&G.
IASU communications ductbank design direction revised to accommodate VOIP
IAU Oversight Task Codes established – Funding status?

## Slide 17: Critical Procurements
HOK Final Design
RBA Design Coordination

## Slide 18: Labor Resources

## Slide 19: Change Request
Conference Area expansion to 175 people?
  Move utilities
  Expand parking

## Slide 20: Issues
PMG meetings - scope
Lengthy approval process for HOK & RBA PO has delay start of final design.
DOE Directive for $2M – impact of full-year continuing resolution?
Conference Room expansion.
Wetlands impact from revised parking layout – 2 phase construction

## Slide 21: Look Ahead
Continue working on Integrated Project Schedule
December 2, 2010: OTE Final Design start. Organize meetings for concept validation. Possible meetings:
  HOK/RBA/IPT/FESS-Eng;
  HOK/FESS-Eng /FESS-Ops;
  HOK/FESS-Eng/FESS-Roads & Grounds
  Coordination IASU design meetings: BMD/IPT (including CDF&AD)/FESS-Eng/RBA (when PO issued)