Booster Daily Shutdown Report

Friday, April 28, 2006

| Tunnel Conditions | Booster is in supervised access. Remember to frisk yourselves on exit. Remember LOTO |
| --- | --- |
| Description of work performed on Thursday, April 27, 2006 | 400MeV/Injection Girder - Pump down continues for injection girder - Completed electrical connections 480 & 110V for ORBMP - Single wire scanner repaired for ORBMP - Testing 400Mev quad supplies MI-8 Line: Dump Relocation - Labeling and connecting up cables Electricians - Worked on 110V for MP03, waiting for approval for 208V panel connection - Completed electrical connections 480 & 110V for ORBMP - Installing new lighting fixtures in the tunnel near MI8 kickers Water Work - Completed sump mitigation from MI8 sumps to Booster SP3 Did not drain Booster pond! Booster RF Work - Maintenance - cavity cooling - Installed current transformer in West APS - Assembling current transformer for East APS MI8 Excavation - Back filled road just outside of the Booster ring road |
| This week's plan Friday, April 28, 2006 | Injection Girder/ORBMP - Continue 400 MeV injection girder pump down - Connecting up the remaining corrector package - Testing 400Mev quad power supplies - Final 400 MeV line alignment (Tuesday) MI8 Line - Install kicker magnets - Add trim magnet to dump line Electricians - More cable pulls Water work - Finished Booster RF - BRF maintenance MI8 Excavation - Finish running new conduit lines to chipmunks - Top soil and seed |
| ES&H Items Inspected or Reported | Item Acceptable Unacceptable Housekeeping √ PPE √ Ventilation √ Rigging √ Ladder/Fall Protection √ Lighting √ Communications √ Moving Equipment √ Electrical Safety √ Noise (Ear protection) √ Radiation Safety √ |
| ES&H Items |  |
| Additional items | Saturday, April 29th 0600-0800 Booster power outage entire Booster ring losses power 0815-1130 Booster East Gallery, Tunnel and Towers 1300-1600 Booster West Gallery, Tunnel and Towers FESS will backfeed tunnel sumps and lights. Site-wide power outage, estimate Monday??? TDB Friday 1400 |