## Slide 1: MicroBooNE Regina Rameika Fermilab Institutional Review June 6-9, 2011

## Slide 2: Outline
Introduction
  Mission Need
  Project Scope
  Key Performance Parameters
The Project Plan
Project Organization
Progress on the Plan
  Infrastructure
  Detector Systems
Cost & Schedule Summary
  Resources
Conclusion

## Slide 3: Introduction
The MicroBooNE detector will be a liquid argon time projection chamber (LAr TPC) containing 170 tons of liquid argon, and located on the Booster Neutrino Beamline.
The experiment’s goal is to begin operation in 2013; availability of funding may constrain the schedule
This device represents a major advance in neutrino detector technology.

## Slide 4: Evolution of Neutrino Detectors
Bubble Chambers
Cherenkov
Emulsion
Tracking
Calorimeters
Liquid Argon

## Slide 5: T-600 at Gran Sasso : 1st generation of large LAr
Evacuated cryostats; 1.5 m drift; warm (exterior) electronics

## Slide 6: From NuSAG 2006 report : develop a plan to go to the 10’s of kTon scale

## Slide 7
LAr1:
Engineering
prototype

## Slide 8: MicroBooNE will :
Fully test the LAr TPC technology at a scope and scale that will help inform the design and operation of very large LAr TPC detectors for next-generation neutrino oscillation experiments.
  Purity without evacuation; cold electronics; 2.5 m drift
Investigate the source of the excess of low energy electron-type neutrinos observed by the MiniBooNE experiment using the unique electron-photon discrimination power offered by a LAr TPC.
Produce the first high-statistics measurements of neutrino interactions in argon. Currently, such measurements do not exist; they will provide the first constraints for future LAr-based neutrino oscillation experiments.
Physics

## Slide 9: Mission Need for a Large Liquid Argon Detector for Neutrino Physics – September 2009

## Slide 10: Project Plan
CD-0 Mission Need : September 2009
CD-1 Alternative Selection and Cost Range : June 2010
CD-2/3a : Performance Baseline
  Director’s review – End of June
  DOE Review – End of July
CD-3 Begin Construction : before end of CY2011
CD-4 Begin Operations :
  Working date – mid-2013 (~2 years from now)
  DOE milestone – mid 2014

## Slide 11: Project Scope – DOE + NSF funding
Cryostat to contain 170 tons of LAr
Cryogenic system for purging, filling and purification
Time Projection Chamber and PMTs
  $900K + $180K
Front end electronics and digitization
Readout ($700K)
DAQ, monitoring and slow control
Building and Infrastructure
Project Management
DOE Project funding ~$20M

## Slide 12: Key Performance Parameter (KPP) and CD-4 Definition
The Key Performance Parameter for the project is : Liquid Argon Time Projection Chamber Detector positioned in the Booster Neutrino Beam with a total capacity for at least 100 tons of liquid argon after filling
The KPP is achieved by demonstrating the following items that enable readiness for initial filling with liquid argon :
  Experiment infrastructure complete and operational
  Safety systems operational
  Detector installation complete
  Detector subsystem checkouts complete
  Cryo-plant tests complete
  Operational readiness clearance granted by the Laboratory

## Slide 13: Project Scale
Cryostat
TPC

## Slide 14: Work Breakdown Structure and Organization

## Slide 15: Progress on the Plan
Detector Systems
  Cryostat design
  TPC design
  Electronics and readout prototypes
  PMTs
  Integration
Infrastructure
  Cryo system design
  Building design
  Assembly and Installation planning

## Slide 16: Cryostat design
Removable end
Market Survey – Feb 2011
Design nearly complete

## Slide 17: TPC Components and assembly sequence Technical Design Review – June 14
2.5 m drift
3 mm wire pitch
8,256 wires (150 micron)
U,V,Y

## Slide 18: Front end electronics (cold + warm)

## Slide 19: PMT System

## Slide 20: Integration of components

## Slide 22: Cryogenic System Process Flow

## Slide 23: Cryogenic equipment and piping
Filters
Pumps

## Slide 24: Cooldown system
Heat exchanger
Molecular Sieve filter
compressor

## Slide 25: An actual setup – LAPD* at PC4
*Liquid Argon Purity Demonstration
30 ton tank

## Slide 26: Building just upstream of MiniBooNE on BNB
Delivery area
Controls
room
Locations for detectors in
a future SBL neutrino program
Could hold a larger membrane
cryostat design in future

## Slide 27: Construction similar to MiniBooNE
54 week construction time

## Slide 28
MicroBooNE detector
will be located on
BNB centerline

## Slide 29: Electronics and readout racks

## Slide 30: Rack locations in detector hall

## Slide 31: Schedule Overview

## Slide 32: Detector Assembly Plan
Use D0 Assembly Area
Vessel will be delivered there and placed on temporary support structure
Detector components fabricated at Yale, BNL, MIT, FNAL
Detector components will be delivered to DAB
Clean assembly area will be constructed
TPC will be assembled in clean “tents”
TPC, FEE and PMTs will be inserted into cryostat
Cryostat will be sealed (flange or/and weld)
Electronics racks will be pre-assembled at D0
DAQ systems will be tested prior to installation

## Slide 33: D0 Assembly Hall to be cleaned out
Racks for MicroBooNE

## Slide 34: Project Cost Estimate being developed for CD-2 baseline
Base Cost
  $19M
Includes costs since CD-0
  $2M
Contingency
  30% on remaining work = $5M
TPC ~ $24M
Before Contingency ~$15M
Including PM ~$19M

## Slide 35: Fermilab Manpower Resources
On-project
  FY11 : 7-8 FTE
  FY12 : 11-12 FTE
  FY13 : 12 FTE
Scientific Staff in addition to PM (Rameika, James)
  Baller, Jostlein, Kirby, Pordes, Raaf, Rebel, Zeller

## Slide 36: MicroBooNE Collaboration
13 institutions
~60 collaborators

## Slide 37: Off-project activities
Argon procurement
Filling and purification
Booster Neutrino Beam preparation
Off-line software

## Slide 38: Summary and Conclusions
Project design is nearing completion
Project team is in the process of optimizing the schedule to determine the earliest technically driven completion date ; aiming for completion in 2013
CD-2 review is planned for end of July
Procurement of key elements (building, cryostat and cryogenic equipment) could begin in October if funding is available