## AR - CERN Schedule
| 2020 | [7 empty] | 2021 | [11 empty] | 2022
| May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
ProtoDUNE 2 Trial Assembly Phase 1
Build first HV FC prototypes-Test Latches
Order materials/fabricate Module 0 components
Module 0 ProtoDUNE 2 FC delivered
Module 0 ProtoDUNE 2 CPA,EW delivered
Full scale ProtoDUNE 2 installation tests
Remove then re-install ProtoDUNE steel Structure
ProtoDUNE II Trial Assembly Phase 2-Upside Down APA
Trial Assembly Phase 2 | bar: 2020 May to 2021 Jul
Design DSS Steel Support/Platform System-Barr | bar: 2020 May
Review design, bid documents, procure | bar: 2020 May
Fabricate/Install DSS steel support structure | bar: 2020 Jun to 2020 Aug
Initial Test DSS | bar: 2020 Sep
APA Shipping Frame Tests: 4-6 weeks | bar: 2020 Sep to 2020 Oct
Ship APA Box Plus APAs to SURF- 3-4 Weeks | bar: 2020 Oct to 2020 Nov
Module 0 HV TPC components fabricated/delivered | bar: 2020 Aug to 2020 Sep
First Row installation/deployment tests | bar: 2020 Oct to 2020 Dec
25th Row Installation tests | bar: 2021 Jan to 2021 Mar
Revised installation tooling and TPC | bar: 2021 Feb to 2021 Mar
First Row installation/deployment tests | bar: 2021 Apr to 2021 May
25th Row Installation/Deployment tests | bar: 2021 May to 2021 Jul
Trial Assembly Phase 3 | bar: 2021 Jul to 2022 Feb
Planning, designing, review & procure | bar: 2021 Jul to 2021 Aug
Installation of mechanical DSS feed thru | bar: 2021 Aug
Installation of mechanical Cable feed thru | bar: 2021 Sep
First Row installation/deployment tests | bar: 2021 Oct to 2021 Nov
25th Row Installation/Deployment tests | bar: 2021 Nov to 2022 Feb
ProtoDUNE-II CERN | 2021 Jan: Ash R-2 FTE; 2021 Jun: Ash R-2 FTE
Disassembly TCO drift volume | bar: 2021 Jan to 2021 Mar
Open TCO | bar: 2021 Apr to 2021 May
Remove ProtoDUNE-SP TPC | bar: 2021 Jun to 2021 Aug
Cryostat Mods, clean roon | bar: 2021 Sep to 2021 Oct
Install ProtoDUNE-II-SP Detector | bar: 2021 Oct to 2022 Feb
Close TCO | bar: 2022 Feb to 2022 Mar
Deploy Beam Left Drift | bar: 2022 Mar
Fill Detector | bar: 2022 Apr
Commission -First quaility assessment of data | bar: 2022 Apr to 2022 May

## Deliverables-ProtoDUNE II-DUNE
Summary of Deliverables for ProtoDUNE and Dune Trial Assembly work at Ash River
DUNE Phase 2 Trial Assembly- DSS Support Struture-Cryostat
2020-05-04 | Bid documents out | UMN | DONE
2020-05-18 | Contractor site visit | UMN | Scheduled
2020-06-01 | Bid's Due | UMN
2020-06-05 | Notice to Proceed | UMN
2020-07-17 | ProtoDUNE II removed, NOvA "Towers", etc. | UMN
2020-07-20 | Fabricated steel arrives | UMN
end of August | Structure is compeleted | UMN
ProtoDUNE II-Phase 1 Beam left Top APA
End Wall Tests
Complete By | Item | Responsibility | Status | Comments
2020-03-13 | Parts breakdown structure for items shipped | LSU | DONE
2020-03-13 | Shipping and tracking information | LSU | DONE
2020-03-20 | Ship End Wall Components (Some extrusions at AR) | LSU, UMN | DONE
2020-03-20 | End Wall Assembly Tooling | LSU | DONE
2020-03-20 | Build End Wall transport equipment | UMN | DONE
2020-04-17 | Order End Wall Al I-beam | ANL, UMN | DONE
2020-05-15 | 5-End Wall Hanger Blocks and blocks | ANL, UMN | In progress | 3-ANL 2-UMN May 15
2020-04-17 | EW Cable and Cable attachment-UMN to order, ANL specs | ANL, UMN | DONE
2020-04-17 | Assembly 6 EW panels carts | UMN | DONE
2020-04-30 | Assembly 6 EW panels for 2 drifts | UMN | DONE
2020-05-05 | Summary of Documents on EDMS | UMN, ANL,FNAL | DONE
2020-05-11 | Load test on EW Lifting beam | UMN | DONE
2020-05-11 | Build first End End Wall | UMN
2020-05-21 | Hang End Wall on hangers | UMN
?? | APA to Endwall connection | ANL
HV SP Field Cages
Complete By | Item | Responsibility | Status
2020-04-10 | Parts breakdown structure for items shipped | UTA, SBU, ANL | DONE
2020-04-10 | Shipping and tracking information | UTA, SBU | DONE
2020-04-10 | Deliver FC Assembly fixture | UTA, SBU | DONE
2020-04-10 | Deliver FC components | UTA, SBU, ANL | DONE
2020-05-15 | 2- sets of latches for second drift volume | ANL | In progress
2020-04-17 | Move left I-Beam to proper drift pitch | UMN | DONE
2020-04-17 | Second block and winch for lower field cage deployment | ANL, UMN | DONE
2020-04-17 | Design/Build new lifting device Bottom FC | ANL | DONE
2020-04-17 | Build improved lower FC latch pivot frame old/new APA | UMN
?? | Designed Lower FC latch pivot frame | PSL
2020-05-18 | New Al CPA hinges- 2 top and 2 bottoms | ANL | Ordered
2020-05-18 | Updated pin design between CPA panels | ANL
2020-05-18 | Connection between APA and End wall | HV, ANL | Conceptual
2020-05-18 | Connection between CPA and End Wall | ANL | Ordered
2020-05-05 | FC storage cart-Design done, fabrication by UMN | BNL,UMN | DONE | need to machine additional plates
2020-05-05 | Complete two top and two bottom Field Cages | UMN | DONE
2020-05-15 | Summary of Documents on EDMS |  | In progress
2020-05-18 | Load test FC deployment winches | UMN
2020-05-21 | Complete Top APA Drift volume | UMN
2020-07-17 | Remove ProtoDUNE Support Structure | UMN
ProtoDUNE II-Phase 2 Beam right Bottom APA
Complete By | Item | Responsibility | Status
2020-05-15 | Updated ProtoDUNE II TPC 3-D model | PSL, HV | In progress
2020-09-04 | Install ProtoDUNE Support Structure | UMN
2020-08-31 | Yoke including raising/lowering device | PSL
2020-08-31 | FC Latch pivots and frame for cable trays for Bottome APA | PSL, BNL, UMN
2020-08-31 | Bottom FC latch frame and pivots for Top APA | PSL
2020-08-31 | Lifting fixture for Top and Bottom APA out of APA shipping frame-sized with ProtoDUNE SS I-beams | PSL, UMN
2020-08-31 | Modifications to any FC lifting fixtures after Phase 1 | ANL, UMN
2020-08-31 | Connection between APA and End wall-Phase 2 | HV, ANL
2020-08-31 | Connection between CPA and End Wall-Phase 2 | ANL | Ordered
2020-09-25 | Begin Phase 2 mechanical tests | HV, UMN
~Sept 2020 | Begin installation tests using APA shipping frame | HV, UMN
Late Sept | Beam Plug support tests | HV, UMN
Mid-Oct | Complete ProtoDUNE II tests | UMN
Late-Oct | Remove ProtoDUNE II support structure | UMN
Any Required Decommissioning tests
2020-07-17 | Complete any Decommissioning tests | UMN
DUNE Trial Assembly Deliverables
August | Double APA lifting fixture engineering note | PSL
August | Lifting fixture for Bottom APA | PSL
August | 6 middle End Wall sections | HV, UMN
August | New CPA panels for DUNE | HV,ANL
September | APA Shipping Frame | APA,W&M

## Weekly Schedule
2020
| April |  |  |  | May | June | July | August | September | October | November | December
ProtoDUNE 2 Trial Assembly-Phase 1
Built 6 End Wall | X |  |  |  | X
Build 4 FC and Cart |  | X | X |  | X
Complete Documentation-EW and FC |  |  |  | X | X
EW Installation
First ProtoDUNE 2 installation tests
Remove ProtoDUNE Support structure
Reinstall ProtoDUNE Support structure
ProtoDUNE 2 TAssembly-Phase 2- Upside down APA
Remove ProtoDUNE Support structure
Design DSS Steel Support/Platform System-Barr | X | X
Review design, bid documents, procure
Fabricate DSS steel support structure
Install DSS steel support structure
Initial Test DSS
APA Shipping Frame Tests: 4 weeks
Ship APA Box Plus APAs to SURF- 3-4 Weeks ??
Complete Review Documentation Process
Module 0 HV TPC components fabricated/delivered
First Row installation/deployment tests
Trial Assembly Phase 3
Planning, designing, review & procure
Installation of mechanical DSS feed thru
Installation of mechanical Cable feed thru
First Row installation/deployment tests
25th Row Installation/Deployment tests
2021
| January |  |  |  | February | March | April | May | June | July | August | September | October | November | December
25th Row Installation tests
Revised installation tooling and TPC
First Row installation/deployment tests
25th Row Installation/Deployment tests
Trial Assembly Phase 3
Planning, designing, review & procure
Installation of mechanical DSS feed thru
Installation of mechanical Cable feed thru
First Row installation/deployment tests
25th Row Installation/Deployment tests
ProtoDUNE-II CERN |  | Ash River Average 2 FTE | [6 empty] | Ash River Average 2 FTE
Prep tools, documentation, training
Disassembly TCO drift volume
Open TCO
Remove ProtoDUNE-SP TPC
Prep Cleanroom
Clean Cryostat/Cleanroom
Modifiy and install CPAs | [11 empty] | Modify CPAs
Integrate, test & install APA 1-2
Integrate, test & install APA 3-4
Install EW
Close TCO-2022
Deploy Beam Left Drift Volume
Fill Detector | [14 empty] | Start-Apr 22

## Optimistic Schedule
2020
| April |  |  |  | May | June | July | August | September | October | November | December
ProtoDUNE 2 Trial Assembly-Phase 1
Built 6 End Wall | X
Build 4 FC and cart |  | X | X
Complete Documentation-EW and FC |  |  |  | X | X
EW Installation
Phase 1 ProtoDUNE 2 installation tests
ProtoDUNE 2 TAssembly-Phase 2- Upside down APA
Remove ProtoDUNE Support structure
Design DSS Steel Support/Platform System-Barr
Review design, bid documents, procure
Fabricate DSS steel support structure
Install DSS steel support structure
Initial Test DSS
APA Shipping Frame Tests: 4 weeks
Ship APA Box Plus APAs to SURF- 3-4 Weeks ??
Complete Review Documentation Process
Module 0 HV TPC components fabricated/delivered
First Row installation/deployment tests
25th Row Installation tests
Trial Assembly Phase 3
Planning, designing, review & procure
Installation of mechanical DSS feed thru
Installation of mechanical Cable feed thru
First Row installation/deployment tests
25th Row Installation/Deployment tests
2021
| January |  |  |  | February | March | April | May | June | July | August | September | October | November | December
25th Row Installation tests
Revised installation tooling and TPC
First Row installation/deployment tests
25th Row Installation/Deployment tests
Trial Assembly Phase 3
Planning, designing, review & procure
Installation of mechanical DSS feed thru
Installation of mechanical Cable feed thru
First Row installation/deployment tests
25th Row Installation/Deployment tests
ProtoDUNE-II CERN |  | Ash River Average 2 FTE | [6 empty] | Ash River Average 2 FTE
Prep tools, documentation, training
Disassembly TCO drift volume
Open TCO
Remove ProtoDUNE-SP TPC
Prep Cleanroom
Clean Cryostat/Cleanroom
Modifiy and install CPAs | [11 empty] | Modify CPAs
Integrate, test & install APA 1-2
Integrate, test & install APA 3-4
Install EW
Close TCO-2022
Deploy Beam Left Drift Volume
Fill Detector | [14 empty] | Start-Apr 22