## Slide 1
Krista Majewski
01 June 2020
HEPCloud Facility Board meeting
Project Update

## Slide 2: General information
Project focus so far has been on framework development
Initial set up of development environment and testing has been a huge undertaking
  Continuous improvement for testing is ongoing. Goal is at least 90% of testing coverage. We started with <30%.
  Important for building experience to accomplish later tasks
Documentation was also missing
  Continuous improvement for documentation ongoing as well
Requirements discussion have been the focus for the past few weeks
  Developers have been working on production backlog. This experience will be very beneficial to project development
Channel planning has been initiated

## Slide 3: Status and effort updates
All estimates are done based on people committing 25% of their time
  Estimates assume effort levels to continue
Work has been broken down into tasks. Related tasks were then clustered into groups called milestones.
  Will review current milestones on the following slides
  Each milestone generally takes ~2 months with design work, 5 weeks if not. Some, like the new configuration system, have a large amount of design and implementation effort.
  Testing takes ~2 weeks of effort for each

## Slide 4: Preliminary Work milestone
Preliminary Work milestone is 100% complete when python3 testing is done
  Python2 version testing was completed right after the last stakeholder meeting (I misunderstood this difference)
  Dependency on python3 versions of glideinWMS
    This does not exist yet but should be released soon (couple of weeks?)
  Will be a few weeks until in production
  No additional effort is needed from the project to complete

## Slide 5: Configuration System milestone
Understanding of existing system - 100% complete
Requirements for configuration system - 100% complete
New configuration system design – 10% complete
  Design progress will be enough to use the new language starting June 15
  Kyle K responsible for design efforts, working with Marc P
Retrofitting code is expected to completed by July 21
  Kyle K, Vito D
Will need extensive testing
  Steve T (and CSI), to be completed by Aug 11

## Slide 6: Requirements milestone
Decision Engine Framework requirements – 100% complete
Decision Engine Modules requirements - 5% complete
  Marco M sent surveys to experiments
Provisioning requirements - 0% complete
  Will describe workflows and getting them to the sites
Edge Services requirements - 0% complete
  Not enough defined on the LCF side to make progress. CMS is doing some preliminary work that may inform the project.
Functional requirements – 100% complete
Monitoring Requirements
  Start a separate monitoring project within the HEPCloud umbrella? Or have a separate monitoring project that HEPCloud can provide requirements to?

## Slide 7: Error Handling/Logging milestone
Error handling
  Design effort for error handling requires a series of meetings with project leads. Approx ~1 week of effort and will be completed by June 19
  Retrofit of code base will be completed July 17
    Pat R, Shreyas B, Hyunwoo K
Logging
  No design effort needed, work is understood
  Lisa G, to be completed Aug 7
Testing
  Steve T (and CSI), to be completed Aug 21

## Slide 8: Produces/Consumes and Source Proxy milestone
Produces/Consumes redesign
  Design effort for error handling requires a series of meetings with project leads. Approx ~1 week of effort and will be completed by July 17
  Prototype completed by July 31
Source Proxy redesign
  Minimal design effort, to be completed by July 17
Unsure of exact development effort yet
  Lisa G
Testing
  Steve T (and CSI)

## Slide 9: Logic Engine Milestone
Decision has been made to re-implement the Logic Engine in python
Requires change request to project since not in scope
Design – 20% complete
  Narrowed down to two possibilities
  Requires a series of meetings with project leads and ~1 week of effort, to be completed by August 14
Implementation
  The two possibilities have very different effort estimates. Effort estimates and timelines will be completed when decision is made
Testing
  Steve T (and CSI)

## Slide 10: Additional framework milestones
Remaining milestones:
  Module Versioning, Channel Replay, and High Availability
    Only remaining design effort
    Estimated design to be completed end of Sept
  Framework Query Tools, Datablock Introspection Tools
  Database Performance Monitoring, Database Storage Review
  Validation Testing (only 1 month)
At this time, our estimate is to complete the framework development ~end of year
  This may change due to scope changes (add logic engine, move monitoring to outside project), effort availability (vacations), etc.

## Slide 11: Effort Summary - Framework
Kyle K: continuous through the end of Sept
  Maybe more depending on logic engine
Dmitry L: continuous
  splitting his 25% with operations may delay project goals
Steve T: focused effort the last few weeks of the milestones. But also meetings, planning, requirements, etc
Developers:
  Lisa G: now -> beginning of Aug+
    Slated for redesign of source proxy and produce/consume work
  Vito D: mid June -> mid July
  Pat R: now -> mid July
  Shreyas B: mid June -> mid July
  Hyunwoo K: mid June -> mid July

## Slide 12: Project Status – Channel planning
Marco M is leading this effort
Very initial planning stages
He sent a survey for the experiments to start work on requirements
  Will be asking for more input at the stakeholders meeting
Requirements and use case definitions to be completed by the end of June
At this point we do not need additional effort for requirements and design work
Expect to do milestones in parallel
  Will stagger design and development effort to best utilize resources

## Slide 13: Effort Summary - Channels
Marco M: continuous
Dmitry L: continuous
  Minimal for now, not sure how much will be needed yet
Steve T: focused effort the last few weeks of the milestones
  Expect continuous and larger amount of effort needed than in framework development, not sure yet
Developers:
  TBD

## Slide 14: Additional notes
Plan to continue to do milestones in parallel
  Team has determined no framework milestone interdependencies or framework-channel dependencies
  Looking at additional milestones like Framework Query Tools, Datablock Introspection Tools to do in parallel
Will stagger milestone (or sub-milestone) effort
  While one (sub) milestone is in the design phase, development will take place for another to be efficient with resources and complete as quickly as possible
Because production support is ongoing, releases and testing may be combined and can cause delays to the project timeline

## Slide 15: Additional notes
Any questions?