## Slide 1
Krista Majewski
06 July 2020
HEPCloud Facility Board meeting
Project Update

## Slide 2: Framework status
Project focus continues to be on framework development
First milestone/release still not fully tested
  Waiting on the python3 glideinWMS release
Next release to come next week
  Requires python3 glidenWMS release
  Contains the new configuration system language
  There will be a few weeks of work to migrate and test the current production configurations
Work continues on logging
  Some changes have already been included in releases
Design work has started on error handling
Design work has started on produces/consumes

## Slide 3: Monitoring
Kevin R met with experiments, HEP Cloud facility people, etc
He is finishing the monitoring requirements
  One more meeting needed
  Cleaning up the document
  ~95% complete
Planning of work is next
  Determining how much effort is needed for the project dashboard
  Including monitoring data requirements in channel planning
Document will be on sharepoint and available to the monitoring project when it is completed

## Slide 4: Channel planning
Marco M sent out a survey and hosted discussions on requirements
  These discussions have been summarized and put on sharepoint as HEPCloud expected use and Channel discussions
Requirements are being written
  Project team will review and prioritize what needs to be addressed first
  May require review and further discussions with experiments for specific details
Next step will be to create a plan
  Determine design, work breakdown, effort needed

## Slide 5: Additional notes
We will be getting an update from Marco on the python3 glideinWMS release today
  Marco may need more effort to complete
  This is a high priority so may divert project effort
Any questions?