## Slide 1
Krista Majewski
08 Sept 2020
HEPCloud Facility Board meeting
Phase 4 and Theta Projects Status Updates, Phase 4 Effort Estimates

## Slide 2: Phase 4 Framework Status
Project focus continues to be on framework development
Next quarterly release is on track for end of Sept
  Error handling updates
  Logging updates
Previous releases still not fully tested
  Waiting on python3 glideinWMS. Previous estimate was end of Aug, they have made some significant progress so we hope to get it soon.
  Then need to test
Work continues on logging, error handling redesign and produces/consumes redesign

## Slide 3: Phase 4 Channel Design and Planning Status
Marco has not had time for channel design
  Focus has been on python3 glideinWMS release and the retirement of the glideinWMS frontend
  Without knowing the scope of work with an overall design, we have been unable to create a plan
    How much is refactoring/reuse of existing code
    What algorithms are needed

## Slide 4: Theta Status
Maria has accomplished a lot, we are currently ~6 weeks ahead of schedule
  Transfer work from CMS Global Pool to HEPCloud: 100%
  Transfer and execute work on Wilson Cluster for “proof of concept”: 100%
  Replicate Wilson Cluster work on Theta: 100%
  Perform end-to-end test on Theta: 25%
  Execute production CMS workflow at Theta: 0%
  Post mortem work: 0%
    Notes are being taken as we go so while not formally documented, work has been done here

## Slide 5: Framework effort estimates:
Remaining work:
  Redesign of Produce/Consume
  Redesign of Source Proxy
  Module Versioning
  Channel Replay
  High Availability
  Query Tools, Datablock Introspection tools
  Database Performance Monitoring, Database Storage Review
Effort needed:
  2 designers at 25% through Sept of next year (Kyle K, Dmitry L)
  4 developers at 25% through Sept of next year
  Expect to have input from Marc P and Tony T on designs

## Slide 6: Channel effort estimates: Design
Overall design
  Effort conflicts have meant we have made no progress
  Effort needed: 40hrs * 2 people (new people to the project will need additional ramp up time)
Channel designs
  Effort needed: ~40 hrs * number of channels, assuming 1 person per channel in the overall design

## Slide 7: Channel effort estimate: Module Implementation
Workflows that need to be addressed:
    HTC on local resources (gpgrid)
    HTC on IC
    HTC on grid
    HTC on cloud
    HTC on HPC
    HPC on cloud
    HPC on MPI
    HPC on pipeline
    Unhandled jobs
    Cloud and HPC calculations
    Monitoring channels – not sure if this applies?
Work will ultimately depend on the design but estimate ~4 people + team lead at 25% each through June of next year

## Slide 8: Edge Services Effort Estimate:
This is applicable to Theta
Dirk is negotiating a special node from Theta for us to set up HTCondor infrastructure
.1 FTE of Maria's time over FY21

## Slide 9: Other Project Tasks Effort Estimates:
Testing:
  We need .25 FTE over FY21. This includes
    Release validation testing
    End to end testing
Documentation:
  Code will be documented as part of the development process
  Documentation of module interfaces: .1 FTE over FY21
Monitoring:
  Data will be provided as part of the channel design/development process per the requirements
  Create the public/DOE dashboard: 40hrs * 1 person

## Slide 10: Additional items:
These items are not currently in scope but will need to be addressed:
  Logic Engine redevelopment
  Pilot infrastructure