## Title Page
PIP-II 121.04 Linac Installation and Commissioning System Design Plan
Document Number: TC ED0010553
Document Approval
|  | Signatures Required | Date Approved
|  | Approver: Jerry Leibfritz, Linac Installation and Commissioning L2 Manager (Acting) | Approved in TC
|  | Approver: Arkadiy Klebaner, Technical Director | Approved in TC
| Revision Number | Revision Notes
| - | Initial Release
| A | Updated Release - 2020-04-11
WBS | WBS Activity | Review Title/Deliverable | Justifying Document | Status | Document Location
All Reviews Must Include:
Up-to-date Prevention through Design Assessment Table
Up-to-date Risk Register
Up-to-date Basis of Estimates (BoEs)
Up-to-date Resource Loaded Schedule (RLS) including Partner Schedule where relevant
Up-to-date Baseline Change Requests (BCR)
Resolution of all previous relevant review recommendations (system/sub-systems)

## 121.04.02 WFE
WBS | WBS Activity | Review Title/Deliverable | Justifying Document | Status | Document Location
121.04.02 | Warm Front End
2021-10-27 | WFE11890 | FDR - Ion Source Power cabinets and Ion Source Overall Layout
Requirements
|  | Ion Source FRS(/TRS) |  | Released | ED0001288
Interfaces
Ion Source Power Cabinets Interface Documents
Risk & Safety
|  | Updated Risk Assessment Document |  | No released version | ED0006531
Updated Prevention through Design Table
Updated Hazard Analysis
Cabinets access LOTO procedure
Ion Source access LOTO procedure
Project Documents
|  | Updated RLS (Schedule) |  | Revision controlled | P6/PIP-II-doc-4095
Design
Ion Source, cabinet, and interconnection overall Layout including cages and stay-clear boundaries
Cabinets and interconnect electrical schematics (detailed)
Cabinets and supporting infrastructure 3D models/90% complete mechanical drawings
Cabinets Interlock documentation
Procurement/Production/Installation
Procurement Plan/Parts List
Ion Source Procurement QC Plan
Ion Sources' Power Cabinets Assembly QC Plan
Ion Sources' Modulators Fabrication QC Plan
Cabinets Verification Test Plan
Preliminary Installation Plan
Electrical Code Compliance Roadmap
2022-06-01 | WFE12800 | FDR - MEBT Beamline
Requirements
|  | WFE FRS |  | Released | ED0008004
|  | PIP-II MEBT FRS |  | Released | ED0001303
Interfaces
MEBT ICD/ISD
Risk & Safety
Updated Risk Assessment Document
Updated Prevention through Design Table
Updated Failure Mode and Effect Analysis
Project Documents
|  | Updated RLS (Schedule) |  | Revision controlled | P6/PIP-II-doc-4095
Design
|  | Updated 3D model/90% complete drawings of all components |  |  | F10001763 & sub-components for PIP2IT
|  | Updated lattice file (beam optics) |  |  | PIP-II-doc-119
Technical reports on vacuum quality and performance downstream of DPI region at PIP2IT (with and without beam)
Procurement/Production/Installation
Draft installation plan
Bunching Cavities Fabrication QC Plan
MEBT Quadrupoles Procurement QC Plan
Procurement Plan/Parts List for all new components
2022-11-30 | WFE14080 | FDR - MEBT Kicker Driver
Requirements
|  | PIP-II MEBT FRS |  | Released | ED0001303
|  | Kicker System FRS |  | Released | ED0001305
|  | Kicker Assembly TRS |  | Released | ED0008094
|  | Kicker Mechanical System Technical Requirements Specification |  | Released | ED0002305
Kicker Driver Technical Requirements Specification
Interfaces
MEBT ICD/ISD
Risk & Safety
|  | Updated Risk Assessment Document |  | Released | ED0006652
Updated Safety by Design Assessment Table
LOTO procedure for maintenance/repairs of the kicker
Failure Mode and Effect Analysis
|  | Updated Hazard Analysis |  | No released version | ED0006653
Project Documents
|  | Updated Resource Loaded Schedule |  | Revision controlled | P6/PIP-II-doc-4095
Design
Resolution of all previous relevant review recommendations
Photonics chassis layout - Wiring Diagram
Photonic Transmitter PCB drawing
Photonics chassis mechanical assembly drawing
Photonics chassis enclosure drawing
Kicker system layout - Wiring Diagram
Driver Assembly layout - Wiring Diagram
GaN FET PCB drawing
Photonic and GaN FET driver PCB drawing
AC power delivery PCB
|  | Driver Assembly mechanical assembly drawing |  |  | F10045400 & sub-components
Driver Assembly enclosure drawing
Load Assembly layout - Wiring diagram
Tests Reports (without beam) - Technical Meeting Presentation(s)
Tests Reports (with beam) - Technical Meeting Presentation(s)
Procurement/Production/Installation
GaN FET Driver PCB Low Level Preliminary Test Procedure
GaN FET Driver PCB Timing Calibration Procedure
Hi-Side Switch Full Power Test Procedure
Low-Side Switch Full Power Test Procedure
Propagation Delay Measurent Procedure
Impedance Measurement Procedure
Dispersion Correction Procedure
|  | MEBT Kicker Driver Fabrication QC Plan |  | Not started | ED0010482
Procurement Plan/Parts List
Fabrication Plan/Procedure
Draft Installation Plan
Electrical Code Compliance Roadmap

## 121.04.03 TestInfra
WBS | WBS Activity | Review Title/Deliverable | Justifying Document | Status | Document Location
121.04.03 | Test Infrastructure
2020-02-17 | TI-733920 | PDR - PIP2IT modifications for 650 MHz test stand and associated cryo transferline modifications
Requirements
2020-04-15 |  | L3 Functional Requirements Specification for PIP2IT Test Infrastructure
Interfaces
Master Interface Control Document (PIP2IT Test Infrastructure Items)
Interface Specification Document from HB650 CM
Risk & Safety
Failure Mode Effect Analysis (FMEA) of CTL
Prevention through Design Table for CTL
Preliminary ODH Calculations
Project Documents
Updated Schedule for 650 MHz CM Test Stand
Design
Preliminary transfer line layouts and routing including U-Tubes and CM including supports
Preliminary 3D Models of all CTL Components
Preliminary P&ID
Preliminary Relief Calculations
Preliminary Flexibility Analysis (thermal contraction)
Procurement/Production/Installation
Preliminary QA/QC Plan for CTL
2020-08-14 | TI-733950 | FDR- PIP2IT modifications for 650 MHz test stand and associated cryo transferline modifications
2020-09-24 |  | Requirements
L3 Functional Requirements Specification for PIP2IT Test Infrastructure
"
Interfaces
Master Interface Control Document (PIP2IT Test Infrastructure Items)
Interface Specification Document from 650 MHz HPRF
Interface Specification Document from HB650 CM
Risk & Safety
Failure Mode Effect Analysis (FMEA) of CTL
Prevention through Design Table for CTL
Final ODH Calculations
Project Documents
Updated Schedule for 650 MHz CM Test Stand
Resolution of all PDR review recommendations
Design
Final 3D Models of all CTL Components; 100% released drawings complete of all CTL systems
Final P&ID
Final Relief Calculations
Approved System/Sub-System Engineering Calculations and Engineering Notes for CTL
Procurement/Production/Installation
Final QA/QC Plan for CTL
Procurement Discussion with the Buyer
CTL Installation and Validation Plan

## 121.04.05 Linac Installation
WBS | WBS Activity | Review Title/Deliverable | Justifying Document | Status | Document Location
121.04.05 | Linac Installation
2022-01-10 | LI13580 | Cryomodule Stands FDR
Requirements
|  | L3 Functional Requirements Specification |  | Released | ED0007996
|  | TRS for Cryomodule Stands |  | Released | ED0007997
Interfaces
|  | ISD - drawing for cryomodule interfaces |  |  | F100..
Risk & Safety
|  | Updated Risk Assessment Document |  |  | ED0008514
|  | Updated Prevention through Design Table |  |  | ED0008514
|  | Failure Mode Effect Analysis (FMEA) |  |  | ED0008514
Project Documents
|  | Updated RLS |  |  | P6/DocDB
Design
|  | Updated EPDM |  |  | ED0008305
|  | Final 3D Models/Drawings of all Major Components; 90% complete of sub-components |  |  | F100..
|  | Draft FESHM 5031 note, including structural and modal analysis |  |  | EN03448
|  | Resolution of all previous relevant review recommendations |  |  | FDR package
|  | Lessons learned list from PIP2IT Stands |  |  | TBD
Procurement/Production/Installation
|  | Final QA/QC Plan - specific to cryomodule stand. Includes acceptance criteria |  |  | ED0008417
|  | Updated requirement Verification matrix (complimentary to QA/QC plan) |  |  | ED0008417
|  | Cryomodule Stand Procurement Plan |  |  | RAPTR
|  | Draft Installation Plan |  |  | FDR package
2022-04-04 | LI13720 | Cryomodule Transportation System PDR
Requirements
|  | L3 Functional Requirements Specification |  | Released | ED0007996
|  | TRS for Cryomodule Transport System |  |  | ED…
Interfaces
|  | ISD - drawing for cryomodule interfaces |  |  | F100..
Risk & Safety
|  | Updated Risk Assessment Document |  |  | ED…
|  | Updated Prevention through Design Table |  |  | ED…
|  | Failure Mode Effect Analysis (FMEA) |  |  | ED…
Project Documents
|  | Updated RLS |  |  | P6
Design
|  | Updated EPDM |  |  | ED…
|  | Preliminary 3D Models/Drawings of all Major Components |  |  | F100..
|  | Preliminary Structural analysis |  |  | PDR package
|  | Preliminary Cryomodule Moving Scheme |  |  | PDR package
Procurement/Production/Installation
|  | Preliminary QA/QC Plan |  |  | ED…
|  | Draft requirement Verification matrix (complimentary to QA/QC plan) |  |  | ED…
|  | Draft procurement plan |  |  | RAPTR
2022-11-17 | LI13680 | Cryomodule Transportation System FDR
Requirements
|  | L3 Functional Requirements Specification |  | Released | ED0007996
|  | TRS for Cryomodule Transport System |  |  | ED…
Interfaces
|  | ISD - drawing for cryomodule interfaces |  |  | F100..
Risk & Safety
|  | Updated Risk Assessment Document |  |  | ED…
|  | Updated Prevention through Design Table |  |  | ED…
|  | Failure Mode Effect Analysis (FMEA) |  |  | ED…
Project Documents
|  | Updated RLS |  |  | P6
Design
|  | Updated EPDM |  |  | ED…
|  | Final 3D Models/Drawings of all Major Components; 90% complete of sub-components |  |  | F100..
|  | Draft FESHM 5031 note, including structural and modal analysis |  |  | FDR package
|  | Updated Cryomodule Moving Scheme |  |  | FDR package
Procurement/Production/Installation
|  | Updated QA/QC Plan |  |  | ED…
|  | Updated requirement Verification matrix (complimentary to QA/QC plan) |  |  | ED…
|  | Updated procurement plan |  |  | RAPTR
|  | Draft operations procedure |  |  | ED…
2021-06-22 | LI13820 | Linac Warm Section Structures PDR
Requirements
|  | L3 Functional Requirements Specification |  | Released | ED0007996
|  | TRS Warm Unit Structures |  | In Workflow | ED0008578
Interfaces
|  | ISD - drawings for matnet, instrumentation interfaces |  |  | F100..
Risk & Safety
|  | Updated Risk Assessment Document |  |  | ED…
|  | Updated Prevention through Design Table |  |  | ED…
|  | Failure Mode Effect Analysis (FMEA) |  |  | ED…
Project Documents
|  | Updated RLS |  |  | P6
Design
|  | Updated EPDM |  |  | ED…
|  | Preliminary 3D Models/Drawings of all Major Components |  |  | F100..
|  | Preliminary Structural analysis |  |  | PDR package
|  | Preliminary Cryomodule Moving Scheme |  |  | PDR package
Procurement/Production/Installation
|  | Preliminary QA/QC Plan |  |  | ED…
|  | Draft requirement Verification matrix (complimentary to QA/QC plan) |  |  | ED…
|  | Draft procurement plan |  |  | RAPTR
2022-01-31 | LI13780 | Linac Warm Section Structures FDR
Requirements
|  | L3 Functional Requirements Specification |  | Released | ED0007996
|  | TRS Warm Unit Structures |  | In Workflow | ED0008578
Interfaces
|  | ISD - drawings for matnet, instrumentation interfaces |  |  | F100..
Risk & Safety
|  | Updated Risk Assessment Document |  |  | ED…
|  | Updated Prevention through Design Table |  |  | ED…
|  | Failure Mode Effect Analysis (FMEA) |  |  | ED…
Project Documents
|  | Updated RLS |  |  | P6
Design
|  | Updated EPDM |  |  | ED…
|  | Final 3D Models/Drawings of all Major Components; 90% complete of sub-components |  |  | F100..
|  | Draft FESHM 5031 note, including structural and modal analysis |  |  | FDR package
Procurement/Production/Installation
|  | Updated QA/QC Plan |  |  | ED…
|  | Updated requirement Verification matrix (complimentary to QA/QC plan) |  |  | ED…
|  | Updated procurement plan |  |  | RAPTR
|  | Draft Installation Plan |  |  | ED…
2021-01-04 | LI15200 | Linac Installation Plan - PDR
Requirements
|  | L3 Functional Requirements Specification |  | Released | ED0007996
List of policies/procedures/requirements governing work (e.g. ED0011409)
Interfaces
|  | CAD model tunnel and gallery elevation envlopes |  |  | F100..
|  | Installation Deliverable Lists |  |  | ED..
Risk & Safety
|  | Draft risk assessment collection framwork |  |  | PDR package
|  | Draft Safety by design collection framework |  |  | PDR package
|  | Draft Hazard Analysis Framework |  |  | PDR package
Project Documents
|  | Updated RLS |  |  | P6
Design
|  | Updated EPDM |  |  | ED0010199
|  | Preliminary 3D Models for the accelerator footprint |  |  | F100..
|  | Preliminary Installation Plan Document |  |  | ED0007915
|  | Preliminary Installation Storyboard |  |  | ED0008045
Procurement/Production/Installation
|  | Preliminary QA/QC Plan framework |  |  | ED…
|  | Preliminary Cryomodule Installation Traveler |  |  | Vector
|  | Davis Bacon Determination Request |  |  | TBD
|  | Preliminary subcontract list and procurement plan |  |  | RAPTR
2022-07-07 | LI15780 | Linac Installation Plan - FDR
Requirements
|  | L3 Functional Requirements Specification |  | Released | ED0007996
List of policies/procedures/requirements governing work (e.g. ED0011409)
Interfaces
|  | CAD model tunnel and gallery elevation envlopes |  |  | F100..
|  | Installation Deliverable Lists |  |  | ED..
Risk & Safety
|  | Updated risk assessment collection framwork |  |  | FDR package
|  | Updated Safety by design collection framework |  |  | FDR package
|  | Updated Hazard Analysis Framework |  |  | FDR package
Project Documents
|  | Updated RLS |  |  | P6
Design
|  | Updated EPDM |  |  | ED0010199
|  | Updated 3D Models for the accelerator footprint |  |  | F100..
|  | Updated Installation Plan Document |  |  | ED0007915
|  | Updated Installation Storyboard |  |  | ED0008045
Procurement/Production/Installation
|  | Updated QA/QC Plan framework |  |  | ED…
|  | Updated Cryomodule Installation Traveler |  |  | Vector
|  | Installation Traveler Index |  |  | TBD
|  | Final Davis Bacon Determination |  |  | TBD
|  | Updated subcontract list and procurement plan |  |  | RAPTR

## 121.04.04 Building Infra
WBS | WBS Activity | Review Title/Deliverable | Justifying Document | Status | Document Location
121.04.04 | Building Infrastructure
2021-01-11 | BLDGI20060 | PDR for Utility Plant LCW System
Requirements
FRS - Building Infrastructure
TRS - Utility Plant LCW System
Utility Plant Room Data Sheet
Interfaces
Master ICD
Interface Specification Document
Risk & Safety
Risk Assessment Document for Mechanical System
Updated Prevention though Design Tables
Failure Mode and Effect Analysis
Project Documents
Updated Resource Loaded Schedule
Design
Preliminary Layout 3D model with envelopes and routing
Tanks, headers, pumps, valves
Preliminary P&ID and associated component list for LCW System
Preliminary analysis of design loads, pressures, flows, and temperatures
Procurement/Production/Installation
Preliminary QA/QC Plan
Preliminary Installation Plan
Procurement Plan
2021-04-06 | BLDGI20110 | FDR for Utility Plant LCW System
Requirements
FRS - Building Infrastructure
TRS - Utility Plant LCW System
Utility Plant Room Data Sheet
Interfaces
Master ICD
Risk & Safety
Risk Assessment Document for Mechanical System
Updated Prevention through Design Table
Project Documents
Updated Resource Loaded Schedule
Design
Final Layout 3D model with envelopes and routing
Tanks, headers, pumps, valves
Final P&ID and associated component list for LCW System
Final analysis of design loads, pressures, flows, and temperatures
Final structural support analysis
Resolution of all previous relevant review recommendations
Final Mechanical Drawings
Procurement/Production/Installation
Final QA/QC Plan for Building Infrastructure
System Procurement/Oversight Plan
2020-07-31 | BLDGI28132 | PDR for Linac Complex LCW System Design
Requirements
FRS - Building Infrastructure
TRS - Linac Complex LCW System Distribution
Linac Complex Room Data Sheet
Interfaces
Master ICD
Risk & Safety
Risk Assessment Document for Mechanical System
Updated Prevention though Design Tables
Project Documents
Updated Resource Loaded Schedule
Design
Preliminary Layout 3D model with envelopes and routing
Subheaders, valves, skid locations, hard piping
Preliminary P&ID and associated component list for LCW System
Preliminary analysis of design loads, pressures, flows, and temperatures
Procurement/Production/Installation
Preliminary QA/QC Plan
2021-01-08 | BLDGI28162 | FDR for Linac Complex LCW System Design
Requirements
FRS - Building Infrastructure
TRS - Linac Complex LCW System Distribution
Linac Complex Room Data Sheet
Interfaces
Master ICD
Risk & Safety
Risk Assessment Document for Mechanical System
Updated Prevention through Design Table
Project Documents
Updated Resource Loaded Schedule
Design
Final Layout 3D model with envelopes and routing
Subheaders, valves, skid locations, hard piping
Final P&ID and associated component list for LCW System
Final analysis of design loads, pressures, flows, and temperatures
Final structural support analysis
Resolution of all previous relevant review recommendations
Final Mechanical Drawings
Procurement/Production/Installation
Final QA/QC Plan for Building Infrastructure
System Procurement/Oversight Plan
TBD | TBD | PDR for Nitrogen System Design
Requirements
FRS - Building Infrastructure
TRS - Nitrogen System Distribution
Linac Complex Room Data Sheet
Interfaces
Master ICD
Risk & Safety
Risk Assessment Document for Mechanical System
Updated Prevention though Design Tables
Project Documents
Updated Resource Loaded Schedule
Design
Preliminary Layout 3D model with envelopes and routing
Headers, valves, hard piping
Preliminary P&ID and associated component list for Nitrogen System
Preliminary analysis of design loads and pressures
Procurement/Production/Installation
Preliminary QA/QC Plan
TBD | TBD | FDR for Nitrogen System Design
Requirements
FRS - Building Infrastructure
TRS - Nitrogen System Distribution
Linac Complex Room Data Sheet
Interfaces
Master ICD
Risk & Safety
Risk Assessment Document for Mechanical System
Updated Prevention through Design Table
Project Documents
Updated Resource Loaded Schedule
Design
Final Layout 3D model with envelopes and routing
Headers, valves, hard piping
Final P&ID and associated component list for Nitrogen System
Final analysis of design loads and pressures
Resolution of all previous relevant review recommendations
Final Mechanical Drawings
Procurement/Production/Installation
Final QA/QC Plan for Building Infrastructure
System Procurement/Oversight Plan
2020-08-28 | BLDGI20592 | PDR for Linac Complex Electrical System Design (cables layouts)
Requirements
FRS - Building Infrastructure
TRS - Electrical Cable and Racks System
Interfaces
Master ICD
Risk & Safety
Updated Prevention though Design Tables
Risk Assessment Document for Electrical System
Project Documents
Updated Resource Loaded Schedule
Design
Preliminary Cable List/Database
Preliminary Cable Routing Drawings
Preliminary Rack Location Drawings
Procurement/Production/Installation
Preliminary QA/QC Plan
Preliminary Design Verification Methodology
Preliminary Installation Schedule for Electrical Cables & Racks System
| BLDGI20642 | FDR for Linac Complex Electrical System Design (cables and layouts)
Requirements
FRS - Building Infrastructure
L4 FRS - Electrical Cable and Racks System
Interfaces
Master ICD
Risk & Safety
Updated Prevention through Design Table
Risk Assessment Document for Electrical System
Project Documents
Updated Resource Loaded Schedule
Design
Cable Tray and Penetration Layout Plans
Final Equipment Grounding Scheme
Final Cable List/Database
Final Rack List
Resolution of all previous relevant review recommendations
Procurement/Production/Installation
Final QA/QC Plan for Building Infrastructure
System Procurement/Oversight Plan

## 121.04.06 Linac Beam Comm
WBS | WBS Activity | Review Title/Deliverable | Justifying Document | Status | Document Location
121.04.06 | Linac Beam Commissioning

## ChangeLog (hidden)
CHANGE LOG
Revision No. | Description of Change | P6 ID Number | Submitted by: | Reviewed By: | Date:
WBS 121.04.02 - Warm Front End
1 | Re-aling with P6 | N/A | F.G. Garcia | L. Prost | 2019-12-12
2
3
WBS 121.04.03 - Test Infrastructure
1 | Removed PDR,FDR-PRR for PIP2IT modifications for SSR1-2 test stand and associated cryo transferline modifications from P6. | TI-734280, 734290, 734300, 734310, 734320, 734360 | F.G. Garcia | J. Leibfritz | 2018-12-20
2 | Removed PDR,FDR,ORR for HTS-2 facility , cryo and RF (HTS-2 de-scope - FY20 budget alignment) | TI--740470, TI--740500, TI--51750, TI--735730 | F.G. Garcia | J. Leibfritz | 2019-01-08
3 | Updated deliverables list for each type f review with input from Cryogenic Group (B. Hansen) | N/A | J. Leibfritz | J. Leibfritz | 2019-07-03
4 | Combined FDR/PRR for 650 MHz Test Stand | TI-733970 | F.G. Garcia | J. Leibfritz | 2019-12-12
5
WBS 121.04.04 - Building Infrastructure
1 | Initial Release | n/a | J. Hunt | F.G. Garcia | 2018-11-30
2 | Major re-desing of the plan after scope split effort (BCR0009) | n/a | F.G. Garcia/ D. Still | J. Hunt | 2019-07-01
3 | RE-aling with P6 | n/a | F.G. Garcia | J. Hunt | 2019-12-12
WBS 121.04.05 - Linac Installation
1 | Initial Release | n/a | C. Baffees | F.G. Garcia | 2018-11-30
2 | Check before DR CD2/3a Review | n/a | C. Baffes | F.G. Garcia | 2019-07-01
3 | RE-aling with P6 | n/a | C. Baffes |  | 2019-12-12
WBS 121.04.06 - Beam Commissioning
1 | Initial Release | n/a | F.G. Garcia | F.G. Garcia | 2018-11-30
2 | Check before DR CD2/3a | n/a | F.G. Garcia | F.G. Garcia | 2019-07-01
3 | RE-aling with P6 | n/a | F.G. Garcia | F.G. Garcia | 2019-12-12
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Related tabs hidden
Note on D14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Related tabs hidden