## Assessment
Prevention through Design (PtD) Hazard Risk Assessment
| Date: |  |  | Project: |  |  |  | Review Phase
| Author: |  |  | Sub-project: |  |  |  | Doc # and Rev #
| Potential Hazard, Threat, or Unwanted Consequence | [5 empty] | Inherent Risk |  |  | Mitigation | Residual Risk |  |  | Risk Mitigation Status & Details
# | Description | Owner(s) | Subsys | Life Cycle | Risk to who? | Risk to what? | Severity | Prob. | Impact | General Description | Severity2 | Prob.2 | Impact2 | Action | Effectiv | Status | Comments
1 | Tight working conditions during installation if scheulde runs behind 650MHz CM installation | Lead Engineer |  | Installation | Technicans | Body | Medium | Likely | Serious | Set up comunication to the overall project to hold CM installation and alignment until tranferline is installed. | Minimal | Unlikely | Negligible | Int. into Design | Admin. Controls | Implemented
2 | Tight working conditions during U-tube stinging and un-stinging which could lead to cryogenic burns and ODH scenatios | Lead Engineer |  | Design, Operations | Technicans | Body | High | Likely | Critical | Proper LOTO procedures to be develped, training to be impletmented, and Has written | Low | Possible | Moderate | Int. into Admin Proc. and PPE | PPE | Implemented
3 | Long lead items on delivery | Lead Engineer |  | Procurement | Project | schedule | Low | Unlikely | Minor | Ensure long lead items are identified and ordered | Minimal | Possible | Minor | Int. into Design | Admin. Controls | No Action Required
4 | Unqualified welders & unqualified weld procedures used on piping for cryogenic service | Lead Engineer |  | Testing, Commissioning, Operations | Catastrophic failure of joint could lead to ODH event as cryogens discharged through vacuum vessel relief valve | Leak spoils insulating vacuum. Accelerator operations halted. System warmed up & disassembled to fix. | High | Likely | Critical | Use ASME BPVC IX qualified welders and weld procedures when welding cryogenic piping. Code qualified welders and weld procedures lead to highly reliabile welds, but non-code qualified welds and weld procedures lead to welds of unknown and generally lower level of quality. | High | Rare | Minor | Int. into QA Plan | Admin. Controls | Implemented
5 | Tight working contditions when maintaining the insulationg vacuum | Lead Engineer |  | Maintenance | Technicans | Body | Low | Possible | Moderate | Ensure in design and installation enough room exists to access insulationg pumpdown port or install provisions to allow easy attachment of vacuum pump | Minimal | Rare | Negligible | Int. into Design | Eliminate | In Process
6 | Cryogens present inside cave | Lead Engineer |  | Operations | Technicans and other personnel inside cave | Body | High | Possible | Serious | Ensure proper LOTO procedures are written and ODH calculation verify precautions needed while inside cave | Low | Unlikely | Minor | Int. into Design | Engr. Controls | Implemented
7 | High pressure Warm helium able connected to cryogenic system | Lead Engineer |  | Shipping, Operations | equipment and personnel | Operations | Medium | Unlikely | Moderate | Safety relief valves and controls to be implimented based on operational needs | Low | Unlikely | Minor | Int. into Design | Engr. Controls | In Process
8 |  |  |  | Installation
9 |  |  |  | Commissioning
10 |  |  |  | Operations
11 |  |  |  | Equipment Shutdown
12 |  |  |  | Maintenance
13 |  |  |  | Troubleshooting
14 |  |  |  | Repairs/Replacement
15 |  |  |  | Decommissioning
16 |  |  |  | Disposal or Recycling

## Examples
Prevention through Design (PtD) Hazard Risk Assessment
| Date: | Nov. 18, 2019 |  | Project: | New Accelerator |  |  | Review Phase |  | Requirements & Specifications
| Author: | Lea D. Engineer |  | Sub-project: | New Accelerator Sub-project |  |  | Doc # and Rev # |  | ED000000 Rev -
| Potential Hazard, Threat, or Unwanted Consequence | [5 empty] | Inherent Risk |  |  | Mitigation | Residual Risk |  |  | Risk Mitigation Status & Details
# | Description | Owner(s) | Subsys | Life Cycle | Risk to who? | Risk to what? | Severity | Prob. | Impact | General Description | Severity2 | Prob.2 | Impact2 | Action | Effectiv | Status | Comments
1 | Overexposure to radiation from machine operations | Connie Controls |  | Operations | Personnel on access in beamline enclosure | - | Critical | Almost Certain | Critical | Global requirement to supply a radiation safety interlock system. Technical specification for system to be compliant with FRCM Chapter 10. | Critical | Rare | Moderate | Integrate into Design | Engr. Controls | In Process | Generic Example
2 | Injury or fatality due to catastrophic failure of a cryomodule | Mikayla Mechanical |  | Operations | Personnel on access in beamline enclosure | - | Critical | Possible | Critical | General Functional Requirement to abide by all FESHM and FRCM requirements. Specific pressure and cryogenic safety chapters from the FESHM are referenced in the functional requirements specification | Critical | Rare | Moderate | Integrate into QA Plan | Admin. Controls | Implemented | Generic Example
3 | Insufficient space for radiological frisking equipment limits emergency egress path | Cybil Civil |  | Operations | Personnel on access in beamline enclosure | - | High | Possible | Serious | Conventional Facilities Technical Specification updated to define necessary space for enclosure frisking equipment | High | Rare | Minor | Int. into Specs and Interfaces | Eliminate | In Process | Generic Example
4 | Strain injury during LCW pump installation / replacement | Stella Structural |  | Installation, Maintenance, Repairs/Replacement, Decommissioning | Contractors and Maintenance personnel | - | High | Likely | Critical | Conventional Facilities to design in an A-Frame lifting fixture rated for 1 ton to facilitate pump installation / removal | Low | Unlikely | Minor | Integrate into Design | Substitute | Implemented | Generic Example
5 | Environmental impact from antifreeze in cooling water system | Cybil Civil |  | Disposal or Recycling | - | Cooling ponds and waters of the state | Low | Possible | Moderate | Original version of technical specification called for use of propylene glycol as an antifreeze in cooling water system. Determined antifreeze in cooling water is unnecessary | Minimal | Unlikely | Negligible | No Action Required | Substitute | No Action Required | Generic Example
6 | People writing or reviewing the specifications may not have sufficient depth/breadth of subject matter expertise | Lea D. Engineer |  | Specification | Anybody near the equipment being designed | The equipment being designed | High | Likely | Critical | Assign qualified subject matter expert(s) at the very beginning of the engineering process | High | Unlikely | Moderate | Int. into Specs and Interfaces | Admin. Controls | Not Yet Implemented | Generic Example
7 | Vendor(s) may not be sufficiently capable of delivering a device per FNAL technical specifications | Lea D. Engineer |  | Procurement |  | Device performance, schedule & cost | High | Likely | Critical | Supply technical questionairre as part of request for vendor bids. Apply detailed technical evaluation to score each vendor on their technical capabilities. Collect lessons learned on past procurements with similar projects. Use technical evaluation to select vendor that provides highest value to Fermilab. | Low | Unlikely | Minor | Int. into Specs and Interfaces | Admin. Controls | Implemented | Generic Example
8 | People performing or reviewing the design may not have sufficient time/resources allocated | Lea D. Engineer |  | Design | Anybody near the equipment being designed | The equipment being designed | High | Likely | Critical | Ensure that people performing the design and review work have sufficient time allocated by line management to perform work. Project schedule shows engineer submitting documents for review with sufficient time before ORC so that reviewer not under time pressure | High | Unlikely | Moderate | Int. into Specs and Interfaces | Admin. Controls | In Process | Generic Example
9 | Cryogens present in cryomodule test facility | Mikayla Mechanical |  | Operations, Commissioning | People in Enclosure | - | High | Possible | Serious | Perform ODH analysis on enclosure. Apply sufficient engineering controls so that area can be classified as Engineered ODH0. Engineering note reviewed by cryogenic safety panel. | Low | Unlikely | Minor | Int. into Design | Engr. Controls | Implemented | Generic Example
10 | Windows operating system patching resulted in lost communication with controls system. Can’t control the cryogenic system, so potential for loss of helium and unplanned ODH event | Connie Controls |  | Operations | People near relief devices | Halted operations and associated effort required to recover system. Cost of helium. | High | Likely | Critical | Better procedure for communication about Windows operating system patching allows controls engineer to prepare for loss of communication with cryogenic control system and quickly restore communication | High | Unlikely | Moderate | Int. into Admin Proc. and PPE | Admin. Controls | Not Yet Implemented | Example provided by APS-TD/Cryogenics based on lesson learned
11 | Re-using old outdoor gas storage tanks with minimal documentation available. Level of fabrication quality unknown and corrosion may have weakened vessels over time. May have higher failure probability than new pressure vessel with code stamp and supporting engineering documentation. | Mikayla Mechanical |  | Testing, Commissioning, Operations | People near gas storage pressure vessel | Experiment can’t run without gas storage | High | Likely | Critical | Hire API 510 inspector to perform detailed inspection and determine appropriate pressure rating based on condition of the vessel | High | Unlikely | Moderate | Int. into QA Plan | Admin. Controls | Implemented | Example provided by APS-TD/Cryogenics based on lesson learned
12 | Right-angle miter joints on a cryogenic piping system. Right-angle miter joints have significantly lower pressure rating and poor flexibility characteristics relative to a standard pipe elbow. In addition, this joint type is not allowed on cryogenic piping per the Code (ASME B31.3 Normal Fluid Service) | Mikayla Mechanical |  | Testing, Commissioning, Operations | Catastrophic failure of joint could lead to ODH event as cryogens discharged through vacuum vessel relief valve | Leak spoils insulating vacuum. Accelerator operations halted. System warmed up and disassembled to replace right-angle miter joint | High | Likely | Critical | Switch to butt-welded short radius elbows. Using butt-welded short radius elbow greatly increases welded joint reliability. | High | Rare | Minor | Int. into Design | Substitute | Implemented | Example provided by APS-TD/Cryogenics based on lesson learned
13 | Unqualified welders & unqualified weld procedures used on piping for cryogenic service | Mikayla Mechanical |  | Testing, Commissioning, Operations | Catastrophic failure of joint could lead to ODH event as cryogens discharged through vacuum vessel relief valve | Leak spoils insulating vacuum. Accelerator operations halted. System warmed up & disassembled to replace right-angle miter joint | High | Likely | Critical | Use ASME BPVC IX qualified welders and weld procedures when welding cryogenic piping. Code qualified welders and weld procedures lead to highly reliabile welds, but non-code qualified welds and weld procedures lead to welds of unknown and generally lower level of quality. | High | Rare | Minor | Int. into QA Plan | Admin. Controls | Implemented | Example provided by APS-TD/Cryogenics based on lesson learned
14 | Helium vacuum pump at risk of overheating | Connie Controls, Mikayla Mechanical |  | Testing, Commissioning, Operations | - | Helium Vacuum Pump | High | Possible | Serious | Use PLC to switch to shut off pump prior to overheating based on temperature sensor input. Switch functionality verified through testing prior to commissioning the vacuum pump. | High | Unlikely | Moderate | Int. into Design | Engr. Controls | In Process | Example provided by APS-TD/Cryogenics
15 | Helium vacuum pump at risk of overheating | Connie Controls, Mikayla Mechanical |  | Testing, Commissioning, Operations | - | Helium Vacuum Pump | High | Unlikely | Moderate | Use hard wire temperature switch to shut off pump prior to overheating as an additional layer of protection. Temperature switch functionality verified through testing prior to commissioning the vacuum pump. | High | Rare | Minor | Int. into Design | Engr. Controls | In Process | Example provided by APS-TD/Cryogenics
16 | Helium vacuum pump at risk of overheating | Connie Controls |  | Testing, Commissioning, Operations | - | Helium Vacuum Pump | High | Possible | Serious | Calibrate temperature switch and sensor on regular schedule as recommended by manufacturer | High | Rare | Minor | Int. into Admin Proc. and PPE | Admin. Controls | In Process | Example provided by APS-TD/Cryogenics

## Probability
Fermilab QAM 12030TA Table 2
MISHAP PROBABILITY TABLE
PROBABILITY | DESCRIPTION
Almost Certain | Could occur annually
Likely | Could occur once in two years
Possible | Occurring not more than once in ten years
Unlikely | Occurring not more than once in thirty years
Rare | Occurring not more than once in one hundred years.

## Hazard Severity Matrix
Fermilab QAM 12030TA Table 1
HAZARD SEVERITY
SEVERITY | PEOPLE | ENVIRONMENT | COMPLIANCE | PROPERTY | PROCESS/PROJECT
CRITICAL | Multiple deaths from injury or illness; multiple cases of injuries involving permanent disability; or chronic irreversible illnesses. | Permanent loss of a public resource (e.g. drinking water, air, stream, or river). | Willful disregard for the rules and regulations. | Loss of multiple facilities or program components; (>$5,000,000 total cost*) | Total breakdown identified resulting in loss/shut down of a process or project.
HIGH | One death from injury or illness; one case of injury involving permanent disability; or chronic irreversible illnesses. | Long-term loss of a public resource (e.g., drinking water, air, stream, or river). | Major noncompliance that exposes the Lab to significant potential fines and penalties. | Loss of a facility or critical program component; (>$5,000,000 total cost*) | Major breakdown identified resulting in the failure to attain the budget, schedule, key performance indicators or customer expectations.
MEDIUM | Injuries or temporary, reversible illnesses resulting in hospitalization of a variable but limited period of disability. | Seriously impair the functioning of a public resource. | Significant noncompliance that requires reporting to DOE or other authorities. | Major property damage or critical program component; ($1,000,000 - $5,000,000 total cost*) | Significant compromise to the attainment of the budget, schedule, key performance indicators or customer expectations which exposes process/project to potential failure if gap cannot be immediately resolved.
LOW | Injuries or temporary, reversible illnesses not resulting in hospitalization with lost time. | Isolated and minor, but measurable, impact(s) on some component(s) of a public resource. | Programmatic noncompliance with the Lab's Work Smart set. | Minor property damage or critical program component; ($50,000 - $1,000,000 total cost*) | Minor breakdown or gap identified which does not result in significant compromise to the attainment of the budget, schedule, key performance indicators or customer expectations; gaps can be resolved.
MINIMAL | Injuries or temporary illnesses requiring only minor supportive treatment and no lost time. | No measurable impact on component(s) of a public resource | Specific instance of a noncompliance with the Lab's Work Smart set. | Standard property damage or critical program component; (<$50,000 total cost*) | Minor gaps identified which do not compromise the attainment of the budget, schedule, key performance indicators or customer expectations; gaps can easily be resolved.
* total cost = total dollar value including parts, labor, contingency plans, etc. that is necessary to repair/replace property or program component.

## Risk Assessment Actions
Risk Assessment Codes and Actions
Very High | Unacceptable. Operation not permissible. Immediate action necessary.
High | Mitagation action(s) to be given a high priority.
Moderate | Mitagation action(s) to be taken at an appropriate time. Can be considered an acceptable risk.
Low | Mitagation action(s) discretionary.
Negligible | No action necessary.
;

## Look-up Tables
Life Cycle Stage | Risk Owner(s) | Subsystem | Severity | Probability |  |  | Risk Matrix |  |  |  | Mitigation Action | Implementation Effectiveness | Status of Implementation | Review Phase
[6 empty] | Almost Certain | Likely | Possible | Unlikely | Rare
Specification | Lead Engineer | Subsystem 1 | Critical | Almost Certain | Critical | Critical | Critical | Critical | Serious | Moderate | Int. into Design | Eliminate | Implemented | Requirements & Specifications
Design | Controls | Subsystem 2 | High | Likely | High | Critical | Critical | Serious | Moderate | Minor | Int. into QA Plan | Substitute | In Process | Conceptual Design
Procurement | Technicans | Subsystem 3 | Medium | Possible | Medium | Critical | Serious | Moderate | Moderate | Minor | Int. into Specs and Interfaces | Engr. Controls | Not Yet Implemented | Preliminary Design
Fabrication | FESS | Subsystem 4 | Low | Unlikely | Low | Serious | Moderate | Moderate | Minor | Negligible | Int. into Admin Proc. and PPE | Admin. Controls | No Action Required | Final Design
Inspection | Mechanical | Subsystem 5 | Minimal | Rare | Minimal | Moderate | Minor | Minor | Negligible | Negligible | No Action Required | PPE | Canceled | Manufacturing Readiness
Testing | Structure | [12 empty] | Procurement Readiness
Shipping | [13 empty] | System Acceptance
Installation | [13 empty] | Transportation Readiness
Commissioning | [13 empty] | Installation Readiness
Operations | [13 empty] | Operational Readiness
Equipment Shutdown
Maintenance
Troubleshooting
Repairs/Replacement
Decommissioning
Disposal or Recycling
Multiple