## Sheet1
PIP-II Review Response
| Review Title: | 650 CTL PDR
| Review Date: | 2020-04-22
| Teamcenter ED#: | ED0011903
| System Manager (or Designee): | Jerry Leibfritz
| Recommendation | Response | Action Item | Schedule to Complete Action | Responsible Party | Status | Completion Date | Evidence of Completion
1 | Add vacuum parallel plate by the FDR. Make sure location good for u-tube pulls. Make sure stands and platform do not interfere. | Will be done in Final Design phase | Add parallel plate relief and verify it is in a safe location | Prior to FDR | J. Hurd | Completed | 2020-08-07 | 3D model and drawings presented at FDR (F10126703)
2 | Finish preliminary helium relief requirements by the FDR. Apply this to size the relieve valves. | Will be done in Final Design phase | Complete relief calculations and size reliefs appropriately | Prior to FDR | J. Hurd | Completed | 2020-08-12 | Relief calculations presented at FDR. Will be part of Engineering Note EN04344
3 | Develop preliminary design for CTL supports and platforms necessary for U-tube installation/ removal by the FDR. | Will be done in Final Design phase | Design CTL support and access platform as required | Prior to FDR | J. Hurd | Completed | 2020-09-01 | 3D models of preliminary designs of CTL supports and work platform presented at FDR
4 | Develop preliminary procedure for isolation, depressurization, and U-tube installation/removal by the FDR. Verify that technicians have sufficient access to perform all steps in the procedure. | Will be done in Final Design phase | Develop u-tube installation/removal procedure | Prior to FDR | J. Hurd | Completed | 2020-08-30 | Presented at FDR (ED0012574)
5 | Check tolerance specifications and investigate U-tube design to ensure that a common U-tube set can be used for all cryomodules by the FDR. | Will be done in Final Design phase | Verify CM tolerances and design u-tube interface accordingly | Prior to FDR | J. Hurd/J. Leibfritz | In-Process |  | Tolerance specification for 650 cryomodule bayonets is still in process. This effort is being led by A. Dalesandro of the PIP-II Technical Integration group
6 | Consider a means to ensure that a flex hose is not overstressed should a spider hang up by the FDR. | Will be done in Final Design phase | Finalize design of flex hoses and look at failure scenerios | Prior to FDR | J. Hurd | Completed | 2020-08-17 | CTL Flexibility analysis presented at FDR. Will be part of Engineering Note EN04344. Line length of the flex hoses can take the entire length of pipe contraction
7 | Consider lowering the elevation of the horizontal section of the CTL toward the floor to help simplify the CTL stand and to allow a platform over it to make U-tube access easier by the FDR. | Will be done in Final Design phase | Optimize location of CTL in cave (vertically and laterally) for access and functionality | Prior to FDR | J. Hurd/J. Leibfritz | Completed | 2020-09-01 | 3D models of CTL location (vertically and laterally) and preliminary design of CTL work platform presented at FDR
8
9
10
11
12
13

## Sheet2
Completed
Not Started
In-Process