## Slide 1: LBNF Hadron Absorber Plan for Final Design, Procurement, and Assembly
Hadron Absorber Preliminary design review
Vladimir Sidorov and Abhishek Deshpande
26 June 2020

## Slide 2
Absorber final design planning .
All Absorber components models and drawings are located in the Team center.
Before the absorber final design beginning the energy deposition in the Absorber Complex MARS calculations, the core blocks and steel shielding thermo and stress analyses, the absorber-decay pipe, the absorber-water cooling system, the absorber- air cooling system, the absorber –Hadron monitor interface have to be completed.
Absorber core
blocks and
shielding assembly

## Slide 3
Highlighted assembly drawing F10108550

## Slide 4
Module – Core block assembly drawing

## Slide 5
Core block weldment drawing

## Slide 6
Core block drawing

## Slide 7
Core block drawing

## Slide 8
Shielding plate drawing

## Slide 9
Procurement Planning
The procurement is planned to start in January 2025.
The procurement plan and specification will be developed.
The Fermilab and Vendors responsibilities will be signed.

## Slide 11
Hadron Absorber assembly scheme
Service building
crane
Absorber Hall
crane
Penetration
The absorber components will be installed by two 30 ton the service building and the absorber hall crane. Components are delivered to the absorber hall by service building crane through the penetration.

## Slide 12
Absorber Complex Cross-section

## Slide 13
Loading
zone
Absorber lower level plan view

## Slide 14
693.33
367.48”
662.75
367”
288”
18”
18.23”
36”
Absorber concrete bunker
90”
96”
4x4 angle
41.25

## Slide 15
Bottom Steel shielding Layers 1 and 2 installation
The absorber steel shielding is welded from 9.11” steel plates, 48.75” width.
The structure inside the yellow dashed square is the Decay Pipe downstream nitrogen turnaround and window. This will be installed before the absorber installation begins.
Steel plates
B1
74,350lb
B2
74,350lb

## Slide 16
Steel shielding Layers 3 and 4, weight 235,670lb each
162.25
195
48.75
B3
235,670lb
B4
235,670lb

## Slide 17
Layers 3 and 4 are installed

## Slide 18
Radioactive water collecting pan
The pan is welded from the 48”x120”x ¼” stainless steel base plates and side plates 24 “ height and 1/8” thickness. The final weld of the pan is made in the absorber hall.

## Slide 19
Side plates are welded to the penetrated into the concrete stainless steel strip.
Weld
Stainless Steel
strip

## Slide 20
Vertical Right-1 and Left-1 Layers installation
Layers are welded from 9.11” steel plates 48.75” wide. The Right layer isn’t covered by crane.
L-1
36,680lb
R-1
65,860lb

## Slide 21
Two front layers installation
Front layers are welded from 9.11” steel. Only top plates are 12” and 6” thick.
9.11” steel
12” steel
6” steel
Two layers weight -224,123lb

## Slide 22
Right vertical layers-2 and -3 installation
7” plate
2.5” plate
The Layer-2 is has 7” and 2.5” thickness and can be combined from different thickness plates.
R2
66,573lb
R3
151,811lb
9.11” steel

## Slide 23
Vertical Right layer-4 installation
195”
R4
187,090lb
9.11” steel
123”

## Slide 24
2.5” steel
Left vertical layers-2 and -3 installation
7” steel
L2
58,524lb
9.11” steel
L3
170,048lb

## Slide 25
Left vertical layer-4 installation
L4
212,060lb
9.11” steel

## Slide 26
Support blocks installation
Support blocks
Air channels
Air channels
Rods
Steel 12”x12” blocks 10-113.5” long are installed on the stainless steel pan and joined together with steel rods. Blocks are not welded to the pan. The distance between block is eight inches.

## Slide 27
Mask support structure and steel shielding are welded together layer by layer.
The bottom block is installed, aligned and welded to support bottom blocks first, then U-shape module support structure with aluminum inserts.
Bottom block
U-shape welded blocks
Masks support weldment
552,500lb

## Slide 28
Aluminum core blocks support structure and shielding installation
Aluminum core blocks support blocks and surrounded shielding are installed layer by layer.
Bottom block
U-shape
weldment
Vertical
plates
Spacer
1,668640lb

## Slide 29
Steel core blocks support structure and surrounded shielding installation
Steel core blocks support structure is located under the service building hatch
and can be installed by service building crane.
Hatch projection-before
Hatch projection-after
Steel core blocks support structure

## Slide 30
162.25”
51”
L1-4
130,528lb
L5-6
154710lb
162.25”
69.75”
Downstream end steel shielding installation
237.5”
258.75”
Four layers 213.25”x237.5” x 9.11” and two layers 232”x258.75” x 9.11”steel are installed
in the downstream end of the absorber. Layers are welded from plates 48.75” width.

## Slide 31
Downstream steel shielding installation
Downstream shielding
831532lb
The temporary platform is installed before downstream shielding installation.
Temporary platform

## Slide 32
Concrete T-blocks installation
Concrete T-blocks
Fourteen concrete T- blocks are installed in the downstream end of the absorber.
144”

## Slide 33
Absorber mask-module installation
Module
Mask
Disk
77-79”
77”
164max
83.5”
Removable
block
Mask-module
86”
For the mask-module delivery to the absorber one steel core block support structure cell
has to be made wider.

## Slide 34
Absorber Al core block –module installation
Module
Core Block
67-69”
67”
Tubes
shielding
176” max
Water line
AL core block-
module

## Slide 35
Steel core block-module installation
All steel core block-module can be installed by service building crane.
Module
177.75”
67-69”
67”
Service
building
hatch

## Slide 36
Water lines connection
After masks and core blocks modules installation core blocks and masks tubes are
connected to the manifolds.
Water tubes
connection
Manifold

## Slide 37
Top concrete blocks installation

## Slide 38
Conclusions
1. The final design of the absorber is planned to be started when the Absorber Complex MARS
calculations, the core blocks and steel shielding thermo and stress analyses,
the absorber-decay pipe, the absorber-water cooling system , the absorber- air cooling
system, the absorber –Hadron monitor interface will be completed.
2. The procurement plan and procurement specification is planned to be developed after the final
design of the absorber completion.
3. The absorber installation procedure based on the final design and assembly scheme is planned to
be developed with the Fermilab quality standards.

## Slide 39
Back up slides

## Slide 40
Water cooling manifolds installation
The water cooling supply and return manifolds are delivered to the absorber in several pieces and final weld can be done in the place.
RAW room door
Return
manifold
Supply
manifold
Temporary
hand rails