## Slide 1
QC, Risk, and Safety Overview
Maurice Ball/Jerzy (Yurick) Czajkowski
PIP-II LINAC Complex Mechanical Fluid Systems PDR
April 21, 2021

## Slide 2: Table of Contents
Quality Control
Installation Plan
Risk
Safety

## Slide 3: Quality Control (QC) Plan
  PIP-II Linac Installation Commissioning QA Plan (Document number: pip2-docdb-2611)
  PIP-II Building Infrastructure Materials Quality Control Plan (Document number: PIP-II-Doc-ED0013639)
  QA/QC by project phase:
    Before Installation
      Plans and Specifications, Sequence of Operations, Commissioning Procedures
      Preliminary and Final Design Reviews to verify system designs
      Coordination and sign offs from other L3s for rack locations
    During Installation
      Vendor visits
      Receiving Inspections
      Construction oversight and change order processes
    After Installation
      Acceptance Inspections/Testing
      Commissioning
      Training
        Procurement Quality / Supplier Quality
        Issues Management (Corrective Action/Preventive Actions)
    Lessons Learned (in process)

## Slide 4: Quality Control (QC) Plan (Continued)
Installation Plan – In Stages
  LCW
    F37 Service Building Pump Room
    BTL Enclosure, Absorber, High Bay Building Warm Front End
    Connection to accelerator components – coordinated with Accelerator Complex Upgrades/BTL Installation group under a separate scope
  PCW
    Utility Plant Pump Room, Utility Bridge
    LINAC Gallery
    High Bay Building/Warm Front End
    Connection to LINAC Gallery components – coordinated with LINAC Installation group under a separate scope

## Slide 5: Quality Control (QC) Plan (Continued)
Sequence of Installation
  Equipment mounted; pipe supports installed; piping connected
  Acceptance of physical installation
  Pneumatic (snoop) pressure test
  Hydrostatic pressure test (test and final acceptance may be delayed).
  Coordination with Fermilab designated personnel (i.e. Task Manager)

## Slide 6: Risk Assessment Summary for Mechanical Fluid Systems
Notes: (Standard engineering requirement of the Fermilab Engineering Manual

## Slide 7: Risk – Technical and Safety
We have a process for assessing technical and safety risk.
We have started drafting these and will complete them in the near future (i.e. within the next few weeks)
Safety Risk
  Prevention through Design Table == Personnel Risk/Safety
Technical Risk
  FMEA == Failure Mode and Effect Analysis

## Slide 8: FMEA - Personnel Risk/Safety - Prevention through Design Table

## Slide 9: FMEA - Technical Risk

## Slide 10: ES&H
Construction of Building Infrastructure will be in full compliance with the PIP-II Integrated Safety Management Plan (docdb #141) developed by the Project ES&H Coordinator
Work with ES&H Coordinator to define mitigations for the following hazards:
  Electrical
  Welding/cutting/brazing
  Pressurized systems
  Cooling water
  Material handling and rigging