## Slide 1
Alexander “Sasha” Shemyakin
PIP2IT Operational Readiness ORC
August 25, 2020
Beam commissioning plan

## Slide 2: Outline
Goals
Preparations for the full beamline run
  Commissioning of the “MEBT” configuration
Commissioning stages and additional measurements
Summary

## Slide 3: PIP2IT beam commissioning goals
From “Plan for Phase 2 of PIP2IT Beam Commissioning and Post-Commissioning Beam Tests”
    PIP-II DocDB# 4429
  Primary beam commissioning goals:
    Accelerate beam to 22 MeV and verify its energy in HEBT
  If time permits, complete additional beam commissioning goals:
    Evaluate beam properties in HEBT
RFQ
LEBT
HWR
MEBT
pSSR1
HEBT
dump
Parameter | Maximum value | Unit
Energy | 25 | MeV
Pulse length | 550 | s
Beam intensity per any given hour | 4.95E17 | H- per hour
Current averaged over 1 µs | 2 | mA
Parameter | Maximum value | Unit
Energy | 25 | MeV
Pulse length | 550 | 
Beam intensity per any given hour | 4.95E17 | H- per hour
Current averaged over 1 µs | 2 | mA

## Slide 4: Preparations for the beam run in the full line
Commissioning plan has been developed
Hardware installation, systems commissioning, documents
  Presented in other reports today
Preparation of optics files and tuning procedures
Re-commissioning of the Warm Front End (WFE)
  Was operational in 2018 with beam power up to 5 kW
  Changes
    New MEBT absorber; low-particulate treatment of section near HWR, re-arrangement of diagnostics; “production” kickers (coming in Nov ’20) – see C. Baffes talk
    MPS upgrade – see A. Warner’s talk
  Important for testing programs and verifying the optics
    Next slides

## Slide 5: Re-commissioning of the Warm Front End
Re-commissioning was made in the “MEBT” configuration
  M61 scrapers are fully inserted to prevent further beam propagation; MEBT valve is closed
  Beam can be delivered to the MEBT absorber or M61 scraper
LEBT, RFQ, and most of MEBT are re-commissioned
    Details on the next slides
  No chopping in the MEBT (not ready yet)
RFQ
LEBT
MEBT absorber
RFQ valve
M61 scrapers
MEBT valve
RPU #2
RPU #1
M11 scrapers
M0 scrapers
Kickers with protection electrodes

## Slide 6: 10 µs beam commissioning
Started by verifying performance of all systems at the safe short pulse length, 10 µs
  MPS, RF, LLRF, instrumentation, optics, collimation, programs
For MPS commissioning, used extra measures to prevent running with long pulses
  Fixed ~ 30 µs overlap between modulator and RFQ pulses
  Administrative control of the LEBT chopper pulse length
All available MPS channels were tested with the beam
  Comparison of beam current readings; losses to M61S scraper and kicker protection electrodes; RF trips; etc.
No beam in MEBT if timing of the LEBT chopper pulse is outside of the overlap between RFQ and IS modulator pulses.

## Slide 7: 10 µs measurements: buncher cavity phasing
Procedure: make all tuning at 10 µs
  Increase the pulse length at otherwise fixed settings
Example: Cavity phasing is performed at 10 µs
  The same program will be used for phasing of SRF cavities
Example of cavity phasing measurement: BPM phases as function of the buncher phase. Also fitting curves are shown.

## Slide 8: 10 µs measurements: Beam optics
Beam optics has been verified with differential trajectories and beam size measurements
Example of differential trajectory measurement: response of the trajectory to change in M00CXI corrector by 0.4 A (points). Solid line – OptiM model.
A. Saini
23 July 2020
18 January 2018
Example of quadrupole scan measurement: horizontal beam size as a function of the current in the upstream quadrupole.
J.-P. Carneiro

## Slide 9: Preparation for the full beamline run
For magnet settings expected for the full-line run, determined positions of 8 scrapers at the beginning of the MEBT
  All scrapers are moved to the same offset in number of the corresponding beam rms width, N∙σ
  “5 mA” settings: N=3 (to use when kickers will be available)
  “2 mA” settings: N= 1.3
    Expected to be the main mode for full line commissioning
  “0.2 mA” settings: N= 0.6
    For the first passing of the beam through the full line
      Average beam power at 10 µs x20 Hz x2.1 MeV < 0.1 W
    BPMs still should provide reasonable transverse positions
Differential trajectory measurement at 0.2 mA. Solid line – OptiM model. A. Saini

## Slide 10: Longer pulse operation
With the entire beam placed to the MEBT absorber, the pulse length was gradually increased to 0.1 ms (20 W beam power)
  With all MPS channels are activated
  Work in progress to increase the pulse length to 0.55 ms
Pulse length increase from 10 to 100 µs
Temperature rise at the absorber center ~0.4C
Pressure increase in the absorber box ~6 nTorr
Response of vacuum and temperature to the increase of the pulse length from 10 to 100 µs. 20 Hz, 5 mA.

## Slide 11: Beam commissioning plan
3 stages plus additional measurements
  Pass the beam through the cryomodules without acceleration
  Accelerate the beam to 22 MeV with minimum duty factor
  Measure the main beam characteristics
Additional measurements
  Gradually increase the beam power to PIP-II beam parameters
    Similar to how it has been done in the “MEBT” configuration
  More detailed beam characterization
Tuning and most of measurements are performed in Diagnostic Mode (as it is being done now)
  Beam pulse duration is limited to 10 µs
  Insertion devices are allowed

## Slide 12: 1. Beam through cryomodules without acceleration
Goal: test all systems while minimizing the risks
  Inject a pencil beam prepared with scraping in MEBT
    2.1 MeV x (≤ 2 mA) x (≤ 10 µs) x (≤ 20 Hz) => 0.01 - 1 W
    Set solenoids for low-energy transport
  Observe the beam in BPMs; pass to the dump
  Check polarities of magnets, BPMs; ACCTs etc.
  Measure optics with differential trajectories
Beam trajectory through the MEBT and cryomodules at 2.1 MeV, 2 mA. Ram Prakash.

## Slide 13: 2. Accelerate the beam to 22 MeV
Set solenoids and cavities to nominal values for acceleration
  2 or 3 first HWR cavities are not operational with beam
    Might be still able to get to full energy by sacrificing the emittance
Phase cavities, accelerate the beam (5 - 10 µs pulses)
Measure the beam energy in HEBT with a movable pickup
Beam envelopes for acceleration to 22 MeV without first two HWR cavities.
J.-P. Carneiro
Movable pickup

## Slide 14: 3. Measurements of the main beam characteristics
In Diagnostic mode, measure
  differential trajectory response to correctors; tune optics model
  beam size with Wire scanners in HEBT
  2D phase portraits with the slits in HEBT; calculate emittances
  2D spacial intensity distribution with the slits
  bunch length with Fast Faraday Cup as a function of the last SSR1 cavity’s phase and amplitude; calculate the longitudinal emittance.
HEBT with the beam dump.

## Slide 15: Additional measurements – “PIP-II parameters”
Accelerate 2 mA x 0.55 ms x 20 Hz to full energy
  First, with heavy scraping in MEBT
  Compensate beam loading at 0.55 ms
Commission the MEBT chopping system
  When “production” kickers are installed (~ Nov 2020)
  Demonstrate the “Booster injection” bunch pattern
Accelerate 2 mA x 0.55 ms x 20 Hz to full energy
  With removal of 60% of bunches by the MEBT chopper
Reliability run at “PIP-II” parameters (24 hrs)

## Slide 16: Additional measurements (2)
High power test of the MEBT absorber (in MEBT at 2.1 MeV)*
Residual population of the cleaned buckets
  In HEBT, with Resistive Wall Current Monitor
Correlations between transverse-longitudinal planes in HEBT
4D distribution in HEBT
Emittance dilution due to chopping (measured in HEBT)
Beam orbit transverse jitter*
Laser wire*
Acceleration of bunches with intensity twice larger than nominal
*May be done without injecting the beam to cryomodules

## Slide 17: Summary
The beam was re-commissioned in the “MEBT” configuration
  All subsystems are operational
  MPS was tested with all available channels
    Confident that a beam pulse limit is enforced
Settings for the beam transport in the full line are prepared
  Tested within the “MEBT” configuration
Commissioning plan is developed
  Staged approach
  Follows the same logic of gradual increase of the beam power as was implemented in the “MEBT” configuration
  Commissioning will use the same procedures and programs