## Slide 1: Cryo Assembly, Cold Mass
A. Vouris
Cryo Assy Meeting
June 29, 2020

## Slide 2: Cold Mass Tooling & Design Status
Work Station Equipment
  Order status
    Clock position clamps – Req#306584 PO #666757 (2/25/2020) received and in QC
    Press test fixtures - PRN #242664 extruded shapes rec’d in IB2
    LBNL Survey Ball – Waiting for detail fab drawings from LBNL to make second set
    Weld Station - Fume extraction Hood forming PO 667499 due May 8th. Formed hood and acrylic sight panels mounted to fume duct is complete. Preliminary testing complete and successful.
  Indexing Clamp – inspection programming complete – Brackets QC inspection complete – received inspection reports this past week. Starting review.
Cold Mass Design
    Cold Mass Model – drawings (instrumentation/align, pre-weld / post weld) –
      Cold Mass Assembly drawings – Drawing Tree up to date
      Cold Mass drawing and model work- CM Alignment (Model: 100%, Dwgs:100%), CM shell fit up (Model: 100%, Dwgs: 100%), CM End Cover fit up (Model: 100%, Dwgs: 100%) and Final assembly/Interface: (Model: 99% drawings 98% ) welding and end cover
      Tack Block Test Fixture – validation testing complete. Removed used tack blocks from fixture and starting to inspect.
      ORC walk through set for Tuesday, 6/30

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Cold Mass Practice parts
    Lower plates (saddle supports) – Reviewing inspection reports
    Shell – strain gauge arrangement revision and prepping for installation
    Fasteners received PO# 667202 – replacement of Set screw for alignment tooling in process
    All Cold Mass Practice Unit parts received – Waiting on CERN components delivery
    Tack Blocks – Fit up to magnet complete
    HA’s – Pressure Washing, Alignment Station, Welding Station completed. Tack Block testing HA and Inspection station HA draft complete
    Practice Unit Procedure – 1st draft complete
    Repair traveler
  Engr Analysis & Note:
    Pressure Vessel Note – latest rev. uploaded to docdb and submitted to reviewer (24-April)- no further comments until CERN/welding test results are received for adding into Note
    Tack Block testing – report completion in process.