## Action Item Update
Action item |  | Response | Resposible | Remaining Question | Status
1 | Water pressure: Inlet/Outlet? | Pressure differential of 100 psi (6.9 bar), maximum available pressure 150 psi (10.34 bar). Inlet/Outlet: 150/50 | David Hixson |  | Closed
2 | Cancel the solenoid component for inter-coil connections in quadrupole? | not required | David Harding |  | Closed
3 | Dipole end pack specification | coil end is no more than 5 inches long beyond the core. Drawing package was provided by Kelvin. | Kevin Duel |  | Closed
4 | Does BARC need to install flow control valves (or just valves) on the magnet LCW manifolds. | No, FNAL will do the installation | David Hixson |  | Closed
5 | Tolerances in the integral field strength | 4-unit sigma | George Velev |  | Closed
6 | Specification on effective magetic length | L6eff/L4eff=1.5 |  | tolerance +/-0.02% or 0.1%?
7 | Thermal Switches | Sensata 4344 series, epoxy glued to the surface of the coil | Chris Jensen | Installed at FNAL or BARC?
8 | Electrical steel laminiation B-H curve non-homogenous | Require measurement, 4 pcs of 30 mm W x 305 mm L x 2.5 mm Th | Miao Yu | When will the 4 pcs of sample steel be available?
9 | Further design study to compensate the saggita (7mm for 4-m dipole and 16mm for 6-m dipole) |  | BARC
10 | Laser cut or stamping on laminations? |  | BARC
11 | Copper bus brazing spec. |  | David Harding
12 | Electric inspection spec. (Hipot and impluse test) |  | FNAL