## Slide 1
PIP-II Team
Project Management Group
15-July-2020
PIP-II Report

## Slide 2: WBS 121.01 Project Management
Early Conventional Facilities (ECF) subproject ESAAB scheduled 16-Jul-2020.
  Procurement package on track for end of July award.
“What if” Scenario planning:
  Scenarios for reduced FY21/22/23 funding levels
    Jan.2020 IPR scenario - $120M/$120M/$120M
    $60/$90M/$120M - $51M increase, 12 month delay
    $80M/$100M/$120M - $26M increase, 6 month delay
  COVID impacts. Results presented at 6/4, 6/25 IPTs. Next major iteration to include partner inputs.
Procurement activities and challenges:
  Staffing challenges
  Critical SRF procurements
Internal Audit ongoing
  Inquiries on OHEP monthly reports, procurements, in-kind contributions, cyber security, lessons learned

## Slide 3: EVMS, RLS
EVMS
  Small decrease in SPI 0.905->0.901, CPI unchanged.
  Current period variances in HB650, Linac Complex Design, LLRF
  Transitioning from bundled BCRs to individual
RLS Development
  Updated WBS for ECF
  Updated COVID analysis coding
  Collecting partner input on milestones

## Slide 4: ESH
Several false ODH Monitor Alarms occurred last week
  Traced to RF leakage from the HWR input couplers
  Engineers investigating source of the leakage
COVID-19
  PIP-II COVID-19 Recovery Plan continued throughout June
    To date, completed 5 rounds of returning employees to work
    Overall activities continue to go well
PIP2IT Accelerator Readiness Review
  Scheduled for August 5-6
  Working on support documents and presentations
  Developing COVID-19 protocols for the review
    Plan to have the reviewers in a conference room together (Sky Box capacity 10)
    Presenters and observers connect remotely
Developed a model to apportion Program Support Indirect costs to PIP-II
  Model being reviewed by CFO for CAS compliance
Supporting procurement and design reviews
Reviews of D/S/P Min-Safe plans continued
Started developing the ES&H section of the draft FDR

## Slide 5: Quality Assurance
Advanced Partners Quality Plans have been submitted by STFC and CEA Partners. Great work has been done so far!
All other Partners are working on developing their Preliminary Quality Plans.
All Partners are engaged in quality-related discussions necessary for the development of supporting processes, such as Nonconformance Management and the use of in-process travelers.
The PIP-II Nonconformance Handling Procedure is currently begin updated to clarify expectations. All Partners will align with defined severity levels to ensure consistency and effective communication.

## Slide 6: International General
French Ambassador
visited PIP2IT Friday,
July 10
Post-COVID T6 MS/input to IKC Partners schedule:
  sent to EU Partners,
  working in-progress for DAE (R&D and Construction). Plan is to send them by next week.
  Received back INFN and WUST schedule.
i-CRADA drafted for LLRF partnership with WUT (Warsaw University of Technology) and LUT (Lublin University of Technology) in Poland.

## Slide 7: International Documents Update
Meeting with DOE-GC on PPD Part 1 and status of PPDs.
  DOE-GC reviewing UK and DAE PPD Part 1
  Meeting with STFC this week on PPD Part 1
    Goal: Apply UK PPD Part 1 language to other PPD Part 1
PPD Part 2 including post-COVID dates in progress:
  UKRI, INFN, WUST – Phase 1
    Goal: Sign UK PPDs in ~1.5 month [early September]
  CEA/IN2P3 – Phase 2
  DAE – Phase 3
Acceptance Plans:
  UKRI and CEA in the finalization stage
  For the other EU PIP-II Partners work in progress

## Slide 8: Procurements
*Top 5 = High Lab Visibility; Critical Path Procurements; Critical Procurement Issues
Item |  | Req # | Est SubK Value | Status | Expected Award Date
650 MHz Cavity, B=0.92 |  | 302069 | $455K | Bids closed 1/29/2020. 3 proposals rcvd. 6 week delay waiting for tech evals. Rec’d tech eval 3/10/20. Procurement eval completed on 3/16. BAA determination received from OGC on 7/7. Proceeding with negotiations with RI. Quote validity period extension requested from RI on 7/8. OGC provided comments to RI's exceptions to Ts and Cs on 7/14. Meeting being scheduled with Project, OGC, and Procurement to discuss. RI extended proposal validity 120 days from 7/13. | 8/10/20
PIP-II Construction of Cryo Plant |  | 305761 | $16.5M | Submitted award package for expedited review and internal approvals on 6/22/20. Issued award package to FSO for review/approval on 6/23/20. Received 26 FSO comments on 7/7/20. Addressed comments and resubmitted to FSO on 7/10/20. | 7/31/2020
IDIQ Controls Eng for Dev and Implementation, Training, & Consulting |  | 31729 (Paper Req) | (Est $1.2M) | FPRs received 4/21. Finalizing best value determination for award. Preparing two IDIQ subcontract awards. OCI reviews for both suppliers completed by OCG 6/1. Routed two IDIQ subcontract awards for internal approval 6/11. Internal approvals completed on 7/10. Award of both IDIQ subcontracts expected 7/14. | 7/14/2020
Construction phase support services for PIP-II Cryogenics Building |  | 307598 | $800K | Requested updated quote from Gensler for task order on IDIQ Subcontract No. 651024. | 7/31/2020
A/E services for 100% design of the PIP-II Linac Complex (Est. $1.7M) |  | 308956 | $1.7M | Assigned 6/23. Working on mod to add requirements under Task Order 665242. | Aug 2020

## Slide 9: Procurements
*Top 5 = High Lab Visibility; Critical Path Procurements; Critical Procurement Issues
Item |  | Req # | Est SubK Value | Status | Expected Award Date
RRR300 Niobium Sheet Nb |  | 305748 | $392K | 4/24 Requestor final decision to split requirements. Both RFPs to be issued 4/29. Solicitations Closed 5/19. Technical Evaluations started 5/22. Technical consensus report submitted 6/1. Negotiations underway. Req returned on 7/7 for additional funds. Awaiting re-approval. | Aug 2020
RRR300 Niobium Sheet NbTi |  | 305748 | $40K | 4/24 Requestor final decision to split requirements. Both RFPs to be issued 4/29. Solicitations Closed 5/19. Technical Evaluations started 5/22. Technical consensus report submitted 6/1. Negotiations underway. Req returned on 7/7 for additional funds. Awaiting re-approval. | Aug 2020
SSR2 Resonator Cavities |  | 305165 | $960K | Pre-Solicitation Issued 2/19. RFP issued 4/13. Solicitation Close 5/1 Technical Evaluations Consensus Report submitted to Procurement on 5/22. Negotiations/Award phase started 5/26. Negotiation points rcvd from Donato. Preparing for negotiations for possible awards to two suppliers (both foreign). Working with OGC on RI's exceptions to FRA Ts and Cs. OGC provided comments to RI's exceptions to Ts and Cs on 7/14. Meeting being scheduled with Project, OGC, and Procurement to discuss. | Aug 2020
SSR2 Coupler Assembly and Ceramic Window / Antenna Assembly |  | 308167 | $190K | Presolicitation Notice posted in Beta.Sam on 3/31 prior to receiving approved req. Formal solicitation targeted for week of 7/27 | Sep 2020

## Slide 10: WBS 121.2 SRF Updates – HWR Status
Cryomodule test is in progress
  CAV4 achieved > 10 MV/m
  CAV3 partially tested (~6.5 MV/m), due to RFPI issue (now resolved)
Issues
  RF leakage from coupler DC block trips ODH alarm
    Solution was found. Work in progress
  LLRF phase lock issue
    Investigation is in progress
Cryoplant trip
  HWR on standby
  Investigation in progress
Cavity Position | Cavity Serial # | Nominal gradient required (MV/m) | Maxium gradient (MV/m) | Cavity Q0 | Note
CAV1 | #2 | 1.6 |  | #2 | 
CAV2 | #0 | 2.5 |  | #0 | 
CAV3 | #1 | 3.5 |  | #1 | 
CAV4 | #3 | 4.8 | > 10 | #3 | No FE, no MP
CAV5 | #8 | 6.5 |  | #8 | 
CAV6 | #4 | 8.7 |  | #4 | 
CAV7 | #5 | 9.4 |  | #5 | 
CAV8 | #7 | 9.7 |  | #7 | 

## Slide 11: WBS 121.2 SSR Cryomodules
SSR1: installation is mostly completed at PIP2IT test cave
  ORC is pending.
  Cooldown is pending cryoplant trip investigation.
SSR2: Niobium sheets production at vendor
  All 40 pcs Nb sheets completed.
  QC hold point: Samples were cut and sent to Fermilab for sample test before shipping.
  Tube samples were tested. Evaluation is in progress at vendor site
  Composition met spec.
  RRR: met spec (362 – 480)
SSR2: Cavity procurement is in progress
  Bids evaluation completed, pending procurement action (See previous procurement slide)
SSR2: Conduction cooled solenoid FDR scheduled around 8/3/20
SSR2: Power coupler procurement is in progress, pending procurement action (See previous procurement slide)
SSR2: cryomodule design in progress.
SSR2 Nb: All sheets completed
SSR2 Nb: Nb tubes
finished the machining process

## Slide 12: WBS 121.2 SRF Updates – 650 Cryomodules
Status and plans of four HB650 5-cell cavities
B9A-AES-007; Cavity jacketing pending hardware from AES-008
B9A-AES-008; The second phase of jacketing is in progress.
B9A-AES-009: Met vertical testing acceptance. Pending cavity jacketing.
B9A-AES-010: Transportation to RRCAT is paused, pending RRCAT request.
B92A-RRCAT-502: First set of cage received. Cleaning and fit test are in progress. HPR is expected this week.
LB650 Cavities:
INFN ESS MB704 received. Processing on hold.
MSU cavity S65-01: Vertical re-test completed. 24 MV/m. (1.6e10)
  Previous test at MSU achieved 21 MV/m (2.1e10 @ 16 MV/m).
MSU cavity S65-02 re-processing completed. Vertical test is not schedule yet.
INFN prototype 5-cell: Half of EP (60 um) completed. EP uniformity was much better than expected.
INFN 1-cell LB650: Niobium material characterization. Processing is pending ANL EP tooling and BCR.

## Slide 13: WBS 121.2 SRF Updates – 650 Cryomodules
B9A-AES-009 met specification with good gradient margin
- G. Eremeev
B9A-AES-008 Final weld showed good frequency spectrum response
- C. Grimm
B61-EZ-001 on ANL EP stand for first 60 um step
- G. Eremeev
EP showed acceptable material removal uniformity

## Slide 14: WBS 121.2 SRF Updates – 650 Cryomodules
- G. Eremeev
Preliminary

## Slide 15: WBS 121.2 SRF Updates – 650 Cryomodules
Cryomodule Design:
HB650 FDR dry run was completed 7/6-8
  Attended by all 650 MHz partner labs
  Many issues resolved
FDR was scheduled 7/29-31
  Reviewing presentation
  Post presentations next week (7/20)
Niobium specification:
Received NX niobium samples from INFN
  Conducting sample studies as soon as allowed
  Focusing on cavity processing and testing (LB650 5-cell and 1-cell)
Improve design for transportation
Procurements (previously reported):
B92 cavity procurement is in progress. Buy American Act review took longer time than expected and quote was extended
650 MHz coupler procurement is pending procurement action.
LB650 MHz niobium procurement is pending procurement action
PIP-II LB650 and HB650 Cryomodule Requirements Workshop is scheduled 7/21-22

## Slide 16: WBS 121.2 SRF Updates – Cryogenics
Cryoplant award is in progress.
  DAE approved requisition.
Cryoplant integration preliminary design is in progress
CDS final design is in progress. FDR is scheduled on 8/12/2020.

## Slide 17: Accelerator Systems
Acc Sys overall
  PIP2IT on-site activity – virtually all L3 subsystems
    HWR RF leakage affecting several subsystems
    Active investigation on all fronts esp. HPRF, LLRF/RFPI, Interlocks
  Electronics procurements – how to streamline process
MPS
  Upgrades and expansion continue
    Hardware beam switch
    Increased # of inputs
    Firmware updates
  Differential beam current measurements (via Ring pick-ups) demonstrated

## Slide 18: Accelerator Systems
HPRF/RF distribution
  New Deputy L3 manager in place (Victor Grzelak)
  PIP2IT
    Complete SSR1 distribution installation
  40 kW 650 MHz SSA path forward
LLRF
  PIP2IT on-site work
  RFPI Technical Requirements with IIFC partners
  Updated SOW with LBNL
  Polish collaboration: I-CRADA being drafted for LLRF partnership with WUT and LUT
    IPT briefing on Thursday

## Slide 19: Accelerator Systems
Magnets/Power supplies
  PIP2IT on-site work
      Focus on SSR1 completion
  BTL magnet acquisition plan completion expected in August
Vacuum
  PIP2IT on-site work
  Completed Analysis of cryomodule gas loads
  Dialogue with SRF/Cryo: beamline vacuum burst disks, gate valves, coupler vacuum instrumentation

## Slide 20: Accelerator Systems
Controls
  PIP2IT
  Controls IDIQ awards to go out today
  Self-paced EPICS training development
Safety Systems
  FESHM draft chapter on Non-ionizing radiation hazards
Beam Instrumentation
  PIP2IT on-site support
    BPM system functioning
  Laser-based profile monitor development

## Slide 21: Installation and Commissioning
PIP2IT
  COVID Recovery
    Essentially all critical personnel are back on site for PIP2IT
    Detailed work planning, social distancing, and PPE usage continues
    Employees are adapting well, no major issues
    Tracking weekly progress to try to quantify efficiency during COVID recovery phase
      June – actual progress matched very well with our assumption (50% efficiency - primarily due to phased return to work and initial preparation of facility)
      July – tracking at ~ 75-80% efficiency (assumption is 100%)
        It is too early to tell if it is COVID related, or just operational start-up issues (see next slide)

## Slide 22: Installation and Commissioning
  PIP2IT Progress
    HWR cold RF testing of individual cavities began
    MEBT beam commissioning
      Re-established beam through LEBT, RFQ and into MEBT
      Operation/commissioning of BPM’s, MPS and instrumentation
    SSR1 cooldown
      Final preparation for cooldown
        ORC walkthrough, tuner checks, interlock testing
        Cooldown planned to begin this week
  PIP2IT Delays/Issues
    RF leakage tripping ODH system – under investigation/mitigation (operations/technical delay)
    Facility chiller problems - (COVID-delay due to lack of maintenance and inability of contractors to access site)
    VIP tours – (management delay)

## Slide 23: Installation and Commissioning
Activities that continue to be worked on remotely
  Management of detailed PIP2IT COVID19 Recovery Plan & schedule
  650 Test Stand Cryo Transfer Line (CTL) Final Design phase
  Support of CF design work
    Updating electrical/mechanical requirements, specifications and 3D CAD drawings in support of CF 60% design review
  PIP-II CAD model
    CAD Model updates (LCW piping, electrical layout, 60% CF model import for A&E firm)

## Slide 24: Accelerator Complex Upgrades
BTLBA (Beam Transfer Line Beam Absorber)
  Finalizing the design of Beam Absorbers (Permanent, Movable)
  Engineering help from AD/TSD
Booster
  Finalizing the Design of the Injection Beam Absorber
  Addressing recommendations from the Booster Collimators PDR Review.
  Started work on Booster Longitudinal Dampers PDR
MI/RR/Booster RF
  Finalizing the MI RF Upgrade Design
    AD/RF department personnel working on Modulator Upgrade
  Resumed High Power Testing of the new Booster RF station

## Slide 25: Conventional Facilities
Early Conventional Facilities (ECF) Subproject
  BCR in progress
WBS 121.06.03 - Cryogenics Plant Building
  Responding to comments from Procurement documents
    Required update to Project Manual (1,584 pages in 182 documents)
  A/E Support (construction administration and construction coordination) proposals received
    Construction Coordinator purchase order issued
    Construction Administration requisition in Procurement
WBS 121.06.05 - Linac Complex
  Detailed design continues
  60% design review scheduled for August 2020
  Final Design Proposal
    Within the budget estimate
    Accelerates the completion date to December 2020
    Requisition in Procurement

## Slide 26: Conventional Facilities
View Looking South in High Bay
View Looking Downstream in Tunnel
View Looking South in Gallery