## Slide 1: MICE Magnet Update Steve Gourlay May 23, 2011
Office of Science

## Slide 2: Overall Strategy
Resolve QP issue ASAP
Aim for process-limited schedule
  Parallel tasks wherever possible
  Saturate Wang resources
  Augment with MICE/LBNL personnel
    Supervision
    Hands-on
Schedule takes priority

## Slide 3: Resources and Responsibilities
Wang – core assembly team, design implementation
  Machnist X 2
  ME, EE, Eng/Phys
  Techs - ?
  Welder – also works at SLAC
LBNL/MICE
  Steve Virostek – Overall coordination, fill in the gaps
  Roy Preece – Onsite supervision/coordination
  Dennis Calais – Onsite tech
  Cryo tech - TBD

## Slide 4: Resources cont’d
LBNL Support team
  Soren Prestemon – QP, assembly
  Tapio Niinikoski – Cryo design/assembly – 50%?
  Heng Pan – QP/Cryo
  Adrian Hodgkinson – Cryo assembly 10%?
  Jon Joseph – Power supplies/interlocks
  Mike Zisman – Project management/technical assistance
  Allan DeMello – Engineering/CAD
  Steve Gourlay – Technical assistance, resources, overall responsibility
Fermilab
  Vladimir Kashikhin + others
  QP
  Sensor calibration
  Short-sample measurements
  Improved vacuum system
  +++?
Others
  MIT (Coupling coils)

## Slide 5
Spectrometer Solenoids

## Slide 6: Spectrometer Solenoid Workshop
May 10 – 11, 2011 at LBNL
Attendees:
Alan Bross, Vladimir Kashikhin, FNAL
Andy Nichols, Mike Courthold, Roy M. Preece, RAL
Alexey Radovinsky, Joe Minervini, Brad Smith, MIT
Pasquale Fabbricatore, INFN, Genova
Wang Li, SINAP
Allan DeMello, Derun Li, Heng Pan, Soren Prestemon, Steve Virostek, Steve Gourlay, Tapio Niinikoski, Michael Zisman, LBNL

## Slide 7: Two primary issues
Quench Protection
  Differences previously seen between LBNL and FNAL analysis are converging. Sources of remaining differences are being systematically evaluated and determined.
  We agreed that we would add external active quench protection to the HTS leads (diodes + resistors + Switch). Also should protect in case of power outage.
  A cooling scheme (addition of heat sink) will be implemented for the by-pass resistors. A bench test will be performed in the next week or so.
  We will consider implementing an active quench protection system IF a subsequent hot-spot analysis with thermal contact between the coils and mandrel removed and quench-back is turned off, results in a temperature higher than 150K. This work should be done in a week or so.
Shipping
  It is a sign of progress that we are now worrying about shipping. We will look at three critical areas: cold mass, shield and HTS leads. Initial focus will be on the shield as they are beginning assembly.

## Slide 8: Other items
Still concern over additional 100W heat leak to 70K. Due to lack of a “smoking gun”, we must emphasize great care in assembling the MLI. We added time to the schedule for this process.
  Many minor mods to reduce heat leak. It should be noted that heat leak appeared with addition of LN2 reservoir which has now been removed
Some discussion on how to attach the stand. Weld or bolt. Stand must meet installation requirements. Need to discuss at collaboration meeting.
A significantly augmented instrumentation plan has gone through initial review and some changes were made. Should be distributed next week for comment.
Power supplies are sufficient but trim supply ground loop problem needs to be fixed.

## Slide 9: Status
A complete set of as-built drawings has been compiled
  200 detail fabrication drawings representing the latest assembly
  Preliminary 3D CAD model developed at LBNL
Heat loads reassessed
  Focus on heat leak into 4.2 K (helium boil-off)
  Shield and vacuum insulation
    Shield might have been an issue with earlier design (not in equilibrium during testing)
EM calculations redone for testing and operation
  Self and mutual inductance
  Hot spot temperature and coil voltage for different scenarios
Mechanical supports of internal components have been reassessed
  Cooldown stresses on components and supports
  Relative motion of components that could cause thermal shorts

## Slide 10: Design Modification Plan
Reduction of heat leaks to cold mass
Addition of more cooling power
Modification of cold leads near the feedthroughs to prevent burn-out
Improved vacuum pumping and instrumentation
Cover, wherever possible, all 4.2K areas with actively cooled shield
Baffles added to vent lines
Possible thermal acoustic oscillations in vent lines will be monitored with fast pressure gauges
Improved application of MLI
  Bore insulation was over compressed
Optimized sensor wires with proper heat sinking
Remake radiation shields using 1100 series aluminum
Improve thermal contact between cooler and shield
Much more instrumentation and monitoring
24/7 supervision by MICE/LBNL personnel

## Slide 11
Coupling Coils

## Slide 12: Status
Cryostat design out for review
  Wang Li from SINAP visited for 1.5 weeks to review with Tapio Niinikoski
  Some changes were made to potentially reduce heat leak and make installation of the MLI simpler.
Derun Li visited QiHuan Company along with Feng Yu and ICST Director
  cold mass welding to be completed at HIT - cover and tubes
  welding to start on 6/1 (complete in 3-4 weeks)
  HIT will test the 1/4 length coil at their facility
  they placed a contract with an outside company
  test to start in ~45 days
Drawing plan at LBNL has been finalized
  model will reflect the QiHuan as-built cold mass
  eventually will have a full set of dwgs w/english translations on LBNL title block

## Slide 13: Near-Term Plan
First coil will be sent to LBNL for impregnation of gap between coil and band
  Tentatively scheduled to arrive in August
Universally agreed that we need to test the first coil before continuing with winding
We have located a dewar large enough for the test at NHMFL
  They can not test before late next summer but are willing to ship the dewar wherever we need it

## Slide 14: Options for next steps
MIT Plasma Science Fusion Center (PSFC)
  They will assess possibility of testing at MIT facility
  Also could provide additional manpower
    Mechanical analysis of coil
    Cryostat design review
    Quench Protection
    Lead design
  SOW and cost estimate in a couple of weeks
Fermilab?
  Logical choice for test and cryostating of at least the first coil since it will stay at FNAL
    Testing
      Setup/install dewar, instumentation/disgnostics
        FNAL - 2.0 FTE over two months
      Test
        LBNL/FNAL – 3.0/2.0 FTE for a month
    Cryostating
      Drawing review
        LBNL/FNAL – 1 p-m/0.5 p-m
      Assembly and parts modifications
        LBNL/FNAL – 0.5/2.0 FTE for 3 months

## Slide 15: Beyond this?
Wait and see how QiHuan does on coldmass welding
  Can they do subsequent cryostating?
¼ coil test at HIT
  Can HIT do the testing
We gain a big advantage by working the bugs out of each procedure in the US
  Hand-off shouldn’t be as risky
  But must have personnel based in China for significant intervals at critical times