## Slide 1: ND LArTPC Preliminary Design Phase
07/31/2020

## Slide 2: Outline
Outlook Ahead
Management Meeting
Preliminary Design Phase – LBNF/DUNE Review Plan
  PDR Deliverables

## Slide 3: Outlook Ahead
After completing the July CDR, the ND LArTPC design effort is entering the preliminary phase
Before getting into details, I think it is useful to first take a look ahead at key dates:
  November 2021: First revisions of all documentation due → not final versions but reasonably complete such that an “interim review” would find them in an acceptable state
  January 2021: US DOE Independent Project Review → primarily affects US partners → International contributions still extremely important at this juncture (i.e. interfaces)
  April 2021: Completion of Preliminary Design Phase
  April 2021 – May 2021: Preliminary Design Review (PDR) of all subsystems
  Summer 2021: CD-2 Review → Gateway to Final Design Phase and CD-3

## Slide 4: Management Meeting
Follows this meeting @ 9AM PCT
Will cover:
  Management Scope
  Consortium Work-Breakdown Management
  Consortium Resource-loaded Schedule Management
  Consortium Risk Management
  Consortium Resource Plan and MOU Development
This meeting to cover
  Consortium Design Change Management
  Consortium Internal/External Interface Management
  PDR Deliverables

## Slide 5: Preliminary Design Phase
Preliminary design phase begins August 2020 with a completion target of April 2021
  Execute preliminary design review (PDR) for all sub-systems April 2021 – May 2021
  Ready for CD-2 in Summer 2021 → Final Design Phase
Key Deliverables per LBNF/DUNE Review Plan @ Preliminary Design Conclusion
  Design choice identified
  Design in accordance with detector requirements
  Detailed engineering drawings, schematics, models, interface drawings and preliminary parts list
  Interface documentation
  Engineering safety analysis plan and initial engineering analysis
  Preliminary installation and testing plans
  Incorporation of ProtoDUNE & other prototyping lessons learned
  Manufacturing methods and acquisition strategy
  Plans for production and evaluation of prototypes
  Draft manufacturing, quality assurance, testing and procurement plans
  Preliminary installation plans including special tools and fixtures
  Preliminary cost and schedule estimate
  Results of value engineering exercise
  Resolution of previous review recommendations

## Slide 6: Design Choice Identified
All open design questions settled with clear design that is ready to final design phase
Any significant design changes require review by the Consortium partners and approval by the Consortium Lead (CL) and Technical Lead (TL)
Tracking & closing out all proposed design changes w.r.t the conceptual design is accomplished via the ND LArTPC Preliminary Design Change Spreadsheet
It is critical that we settle open design issues promptly

## Slide 7: Design Choice Identified
ArgonCube Full-Scale Module |  |  |  |  |  |  |  |  | 
Design Change | Short Task Description | Rationale | Requirements Impacted? | Interfaces Impacted? | Resources Impacted? | Entered By? | Date needed | Responsible Institiution | Details
Optical Segmentation -> Modularity | Physics study to determine required optical segmentation such that pile-up concerns are fully mitigated | Currently the active volume of 5m x 7m x 3m is instrumented by a 5 x 7 module array with nominal module size of 1m x 1m x 3m. The overall active volume must be maintained, however the 5 x 7 array size is not fully optimized, i.e. a 4 x 7 or 3 x 7 array may achieve commensurate results with less active components. | Yes | Yes | No | Lambert | 09/04/2020 | LBNL | 
  July 31, 2020: Initiate collection of proposed design changes
  August 7, 2020: Review list of key design change proposals (Next week’s Engineering Meeting)
  September 4, 2020: Status reports on engineering analyses/studies
  October 2, 2020: Complete & present required analyses
  October 9, 2020: Complete design change proposals & send to Management team
  October 20, 2020: Final evaluations and approvals by Leadership team

## Slide 8: Design in accordance with detector requirements
Requirements Document: Maturity ≥ 90%
  Subsystem L3 Managers: Requirements on your subsystem as they flow down from the overall physics requirements
Specification Document: Maturity ≥ 90%
  Subsystem Lead Engineers: Technical specifications that your design must deliver to meet the requirements set forth in the Requirements Document
Templates at: https://drive.google.com/drive/folders/1-lmBSjRDpnzZ0gtHTAFEspFZpMyo_4Z0?usp=sharing

## Slide 9: Detailed engineering drawings, schematics, models, interface drawings and preliminary parts list
CAD model: Maturity ≥ 90%
Engineering Drawings: Maturity ≥ 60%
  Component fabrication drawings
  Schematics (P&IDs, Grounding Diagrams, etc.)
  Interface Drawings
  Bill of Materials
Engineering Analyses: Maturity ≥ 90%
  Each subsystem will need to perform relevant engineering analyses & document the results
    Finite Element, Computational Fluid Dynamic, Classical Analyses, Experimental Results
      Formally documented in Engineering Technical Notes
    Lead engineer to help define required analyses in conjunction with subsystem lead engineers
    Subsystem lead engineers responsible for delivering analyses to lead engineer for review
Lead Engineer with work with L3’s and subsystem engineering leads to develop schedule for engineering analyses & preliminary design drawing package development between now and April 2021

## Slide 10: Interface documentation
Engineering team is responsible for designing and documenting (via interface drawings) both internal and external interfaces: Maturity ≥ 90%
  Subsystem lead engineers are responsible for the design of their interface to other subsystems (internal)
  Lead engineer is generally responsible for external interfaces (with input from subsystem engineers where required/applicable)
L3 managers are responsible for maintaining Interface Control Documents (ICDs) : Maturity ≥ 90%
  These document templates have been distributed, interfaces are tracked in a table format
  Interfaces can be defined by an interface drawing → this drawing must be referenced in the interface document → if interface document is released, interface drawing should be released as well to ensure interface is preserved
Near term schedule
  August 20th 2020: Collect initial drafts of interface documents from subsystem leads
  August 27th 2020: Lead engineer completes review, revises, and forwards to TL
  September 1st 2020: CL & TL review and approve initial revision
For the initial release of these documents it is unlikely that interface drawings exist → identify all interfaces and locations, use “TBC” in lieu of interface drawings → incorporate interface drawings into 2nd revision
Templates at: https://drive.google.com/drive/folders/1-lmBSjRDpnzZ0gtHTAFEspFZpMyo_4Z0?usp=sharing

## Slide 11: Engineering safety analysis plan and initial engineering analysis
Lead engineer is coordinating with LBNF/DUNE EH&S lead to develop ND LArTPC safety documentation: Maturity ≥
  Distribute EH&S documentation templates to L3s (August 7th)

## Slide 12: Preliminary installation and testing plans
Subsystem lead engineers responsible for developing assembly/installation plans for their system: Maturity ≥ 50%
  Acceptance Criteria List: Maturity ≥ 65%
    What are the key parameters that must be satisfied to show your system meets spec?
  Test and Inspection Plan: Maturity ≥ 45%
    What testing/inspection is required to show acceptance criteria is met?
  Work Instructions: Maturity ≥ 45%
    How should your system be handled/assembled during both testing and eventual assembly?
    What are
Lead engineer to supply subsystem leads with templates for above documents

## Slide 13: Incorporation of ProtoDUNE & other prototyping lessons learned
Prototyping is an integral part of the preliminary design development
At a minimum, we are targeting to have two prototyping efforts wrapped up by the conclusion of preliminary design with a third in underway/imminent
  SingleCubeTPC: all field structure kits are distributed → charge readout (7-8 weeks)
  Module 0: targeting November 2020 for initial operations
    Module 0 Master Parts List → main page is updated, please go into your subsystem and update your BOM or use as opportunity to see where you are at in your deliverables
  2x2: targeting spring 2021 for initial operations, which may coincide with the PDRs
It is critical that prototype results are clearly communicated and available for next years PDR → additionally January 2021 IPR

## Slide 14: Manufacturing methods and acquisition strategy
Subsystem lead engineers determine how their system are fabricated with L3s supporting procurement efforts
At PDR level this is most likely referring to high-cost, high-risk, long-lead items
Lead Engineer to provide better definition on this in the future

## Slide 15: Plans for production and evaluation of prototypes
Full-Scale Demonstrator (FSD)
  Single full scale ND module that incorporates all design features and subsystems
  Final prototype before 1st article production of the ND LArTPC
  Preliminary design feeds into development of the FSD (2021-2023)

## Slide 16: Draft manufacturing, quality assurance, testing and procurement plans
Lead engineer is coordinating with LBNF/DUNE QA/QC lead to develop ND LArTPC safety documentation
  Distribute QA/QC documentation templates to L3s (August 7th)

## Slide 17: Preliminary installation plans including special tools and fixtures
Referring to official TPC Integration Planning
  TPC Integration will need to receive installation & handling information from other subsystems in order to plan out the larger module assembly process at the Module Integration Facility
  Additionally this probably overlaps with NSI&I → Need to provide installation plans for how ArgonCube modules are handled and installed to rows
    Technically we are handing off the modules to NSI&I once they are completed at the MIF, but NSI&I will most likely still need guidance from the consortia on how to handle the modules safely and install them to the cryostat

## Slide 18: Preliminary cost and schedule estimate
L3s responsible for maintaining cost/schedule estimates for their subsystems and communicating this to Leadership Team
Further details in Management Meeting @ 9 AM PCT

## Slide 19: Results of value engineering exercise
Lead engineer to provide further definition of this exercise in the future

## Slide 20: Resolution of previous review recommendations
At January 2021 we must show resolution of both July CDR and July IPR recommendations, or very credible progress towards their resolution
At Spring 2021 PDR we must show resolution of CDR recommendations, and relevant January 2021 IPR recommendations (if any)
Management team is responsible for tracking resolution of review recommendations, further details on Management Team responsibilities @ following 9 AM PCT meeting

## Slide 21: Summary
Entering preliminary design phase → moving to much more detailed design both in terms of technical advancement and cost estimates
Begin creation of documentation in earnest → templates provided for some documents, others to soon follow:
Preliminary design engineering efforts to be discussed and tracked in this meeting on a weekly basis
  Would like to continue a format of rotating presentations, contributions from all subsystems
    First half-hour: Presentation from 1-2 subsystems on engineering design/analysis/interfaces/specs/etc.
    Last half-hour: Round table updates from all subsystems
Management discussed at following 9AM PCT meeting
Key engineering near term deliverables:
  August 7th → Review list of key design change proposals & initiate relevant engineering studies, distribution of QA/QC and EH&S templates to L3s
  August 20th → Interface Control Document drafts due (see Slide