## Slide 1: Cryostat Assembly Status Update
R. Rabehl
August 3, 2020

## Slide 2: Tooling
Validation tests 7/16-7/17
  Received draft report from CERN (docdb 3653):
    A full de-cryostating of a cold mass dummy from a pre-assembled Q1 vessel was performed with the Fermilab tooling.
    Only minor issues to be resolved.
    Tooling is packed, will ship in September
      We have requested shipment ASAP.

## Slide 3: Shipping post
Drawings
  Final details of drawings for shipping post and associated post are nearing completion, after which they will be formally reviewed and approved.

## Slide 4: Tooling Installation at Fermilab
Installation requirements:
  We have a draft tooling installation procedure (aka, Integration Plan).
  Will follow requirements (e.g., subcontractor training) of 013100 ES&H Requirements for Subcontractors.
  Installation activities will adhere to FESHM 2060 “Work Planning and Hazard Analysis,” which was rewritten in the last few months and is defined by SHAPE.
    Scope – define the scope of the work
    Hazard – identify hazards and controls
    Authorize – authorize the work to begin
    Perform – perform the work
    Evaluate – post-work evaluation