## Slide 1: Cryo Assembly, Cold Mass
A. Vouris
Cryo Assy Meeting
August 03, 2020

## Slide 2: Cold Mass Tooling & Design Status
Work Station Equipment
  Order status
    Clock position clamps – Req#306584 PO #666757 (2/25/2020) – Waiting on inspection for clamps – Ted Beale marked as HOT but has 3 mo. Back log from COVID-19 lock down
    Metrology In-House to finish verifying indexing bracket locations on inspection table (Next week).
    Press test fixtures - PRN #242664 extruded shapes rec’d in IB2
    LBNL Survey Ball – @ Village Machine Shop for fab
    Weld Station - Up-grdades being made this week
  ICB-A: High Pressure Air system: Now in Operation mode
  Cold Mass Model – drawings (instrumentation/align, pre-weld / post weld) –
      Cold Mass drawing and model work- CM Alignment (Model: 100%, Dwgs:100%), CM shell fit up (Model: 100%, Dwgs: 100%), CM End Cover fit up (Model: 100%, Dwgs: 100%) and Final assembly/Interface: (Model: 99% drawings 98% ) welding and end cover

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Cold Mass Practice parts
    MQXFA03 – metrology in house and on list to verify fiducial measurement with LBNL ball Fixture
    Lower plates (saddle supports) – SOW in progress
    Shell – strain gauge installation:
      Addition of short magnet gauges complete on one shell. Staged 2nd shell for last 2 internal gauges. Shell to be rolled and external gauge placement is next
      pre-series shells in procurement (forming & machining) sending HT/PLT # today
      Fasteners PO: EBN placed 7/31 - PRN#244165
      Next: backing strips, fasteners
    Cold Mass Practice Unit parts – 1st shipment rec’d and being checked
    Tack Blocks – Fit up to magnet complete….Ordering for 1st pre-series to be released this week
    HA’s – Pressure Washing, Alignment Station, Welding Station completed. Tack Block testing HA and Inspection station HA draft complete
    Repair traveler
  Engr Analysis & Note:
    Pressure Vessel Note – latest rev. uploaded to docdb and submitted to reviewer (24-April)- Response from Reviewer confirmed Note is now in good shape and approved up until weld sample testing is completed.
    Tack Block testing – report 1st draft complete.

## Slide 4: Cold Mass Tooling & Design Status
Cold Mass Tooling ORC
  Initial ORC walk through completed on Tuesday, 6/30 …
    ORC-1752, Cold Mass Tooling: All components with exception of Weld Roller was sufficient. Searching requested documents for roller to upload this week
      Outline for Practice unit sent to ORC panel for tagging tasks to be witnessed by reviewers
      Alignment Table docs: FDR Presentation, FRS, design & Analysis Note, Assembly Drawing, HA link, Cold Mass Assy & Inspection Traveler
      Welding Table Docs: FDR Presentation, FRS, design & Analysis Note, Assembly Drawing, HA link, Cold Mass Assy & Inspection Traveler
      Inspection Table Docs: Assy drawings and all above
    ORC-1754, Bus Soldering and Wrapping: submitted (Rob Bushek Review in process)
      Reviewer walk through set for Thursday 8/06.
      Bus Soldering Docs: Solder Fixture and Bus Assy drawings, MSDS for solder and Flux, Soldering Note HiLumi Docdb #3256
      Wrapping Station Docs: Drawings for wrapping assemblies and word document with Mu2e ORC link
    Lifting Devices: Orozco to send maintenance records.