## Slide 1: Bus Work Status
R. Bossert 8/10/2020

## Slide 2
Bus and Expansion Loop Status
Assembly and detail drawings for the bus and expansion loops complete at the 95% level. A few minor details are still to be completed by revisions. They are:
  Addition of coil voltage tap and Quench heater wire routing to the assembly.
  Addition of temperature sensors for MTF to the assembly.
  Addition of sub-assemblies for individual hold-down fixtures
  Cable exit bumpers.
  Addition of IFS and Kmod/CLIQ exit spiders to the assembly and details.
  Coil voltage taps and addition of sub-assemblies are completed and the spiders are in process.
All parts for the first two Q2 bus assemblies have been ordered. A minor revision to the Q2 bus assembly drawing to show the twist more clearly and to add the screw lock-down system is being completed this week.
Parts for the Q1/Q3 lead exit supports for the first cold mass have been received, inspected and accepted. 4 more Q1/Q3 bus housings are ordered, due on August 20th. Hardware order for all bus housings and end hold down parts has been sent to procurement.
The first bus to be sent to CERN for the Q2 prototype is wrapped and hipotted. Remaining parts arrived on August 6th. The bus will be assembled into the housing this week and shipped to CERN in the same box as was used for the beam tube to be shipped to FNAL.
Bus insertion into the Q1/Q3 practice cold mass took place this week and was successful. The parts needed from the Q1/Q3 bus to use n the Q2 bus have been removed and are ready for Q2 bus assembly.

## Slide 3
Bus and Expansion Loop Status
Magnetic analysis of the expansion loops is in process by Vadim Kashikhin. He has been provided magnetic field information as well as the model of the loop and bus configurations. Some rework of the solid model is necessary and is complete. Vadim is finishing the analysis now.
Talks are ongoing to plan the special wiring for the first pre-series cold mass (MQXFA03). Some discussions took place last week. A plan for removal of strain gauges is expected to be completed this week.
The bus soldering fixture was completed. Some minor rework of the fixture will take place before soldering of the production busses begins. Bullet #1, addition of thermocouples, has been done. Temperature tests have been done with a new 11 meter element. Strand sample testing been completed, at a range of temperatures between 220C and 320C. Bullet #2, cold block design, is in process. Bullet #3 has not been started.
  More thermocouples will be added to allow more detailed monitoring of the temperature.
  “Cold Blocks” will be implemented to better prevent solder from wicking into the non-soldered area. Parts for the cold block and soldering cart have been procured and design on this part is underway.
  A second temperature will be added to the program to allow the bus to be heated to an intermediate level after soldering to facilitate removal from the fixture.
New design for the Qa splice fixture has been completed, and quotes for elements have been received. The Qa end fixture fabrication will take place this week. The Qb fixture design will be completed this week.