## Slide 1: Cryo Assembly, Cold Mass
A. Vouris
Cryo Assy Meeting
August 10, 2020

## Slide 2: Cold Mass Tooling & Design Status
Work Station Equipment
  Order status
    Clock position clamps – Req#306584 PO #666757 (2/25/2020) – inspection for clamps completed and reviewed. One Clamp usable, second to far out to fit indexing brackets. Procurement informed.
    Indexing brackets preliminary located & mounted to table. Waiting for Metrology to return & final verification.
    Press test fixtures - PRN #242664 extruded shapes rec’d in IB2
    LBNL Survey Ball – @ Village Machine Shop
    Weld Station - received remaining material - Up-grdades in process
  Cold Mass Model – drawings (instrumentation/align, pre-weld / post weld) –
      Cold Mass drawing and model work- Final assembly/Interface
      Component drawings updated with additional notes for PED material certs required. tack block drawings in process.

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Cold Mass Practice
    Bus Assembly installed and expansion loops in process – see Rodger Bossert slides
    Shell – strain gauge installation:
      external gauge placement is in process
      pre-series shells in procurement (forming & machining) Waiting for plate shipment orders
      Weld supplies ordered and at local pick up location
  CM-01
    Fasteners PO: EBN received 7/31 - PRN#244165
    backing strips, drawings updated and in workflow process
    MQXFA03 – metrology on list to verify fiducial measurement with LBNL ball Fixture
  Repair traveler
  Engr Analysis & Note:
    Pressure Vessel Note – latest rev. uploaded to docdb and submitted to reviewer (24-April)- Response from Reviewer confirmed Note is now in good shape and approved up until weld sample testing is completed.
    Tack Block testing – report

## Slide 4: Cold Mass Tooling & Design Status
Cold Mass Tooling ORC
  Initial ORC walk through completed on Tuesday, 6/30 …
    ORC-1752, Cold Mass Tooling: All components with exception of Weld Roller was sufficient. Searching requested documents for roller to upload this week
      Outline for Practice unit highlighted by ORC panel for witness points
      Alignment Table docs: FDR Presentation, FRS, design & Analysis Note, Assembly Drawing, HA link, Cold Mass Assy & Inspection Traveler
      Welding Table Docs: FDR Presentation, FRS, design & Analysis Note, Assembly Drawing, HA link, Cold Mass Assy & Inspection Traveler
      Inspection Table Docs: Assy drawings and all above
    ORC-1754, Bus Soldering and Wrapping: submitted (Rob Bushek Review in process)
      Reviewer walk through completed Thursday 8/06. Comments received 8/10/20
      Bus Soldering Docs: Solder Fixture and Bus Assy drawings, MSDS for solder and Flux, Soldering Note HiLumi Docdb #3256
      Wrapping Station Docs: Drawings for wrapping assemblies and word document with Mu2e ORC link
    Lifting Devices: Orozco to send maintenance records.