## Slide 1: 302.4.04 – Cryo-assemblies Horizontal Test Weekly status report
Guram Chlachidze
Aug. 10, 2020

## Slide 2: Test Stand 4 Upgrades
TS4 External piping installations close to completion
  Remaining installations at the Stand 4 platform are on hold, waiting for pressure tests completed
Stand 4 Pressure tests in progress
  Relief valve spool test in MW9 - Done
  CA relief vent line – Done
  LN2 bath vent line – Done
  FB/AB thermal shield piping – Done
  Return end thermal shield piping – Done
  Pumping lines portion from the test stand to the Midway roof - Done
  Feed Box rupture disk vent line – Done
  High pressure Helium lines – 4 min only at the target pressure last week, need to repeat the test
  Low pressure Helium lines – replacing the top plate bolts
Complete FB-AB interconnects after all the helium lines are tested

## Slide 3: More Upgrades
WACHS cutter demonstration revealed some space issues
  CA piping design will be changed to accommodate extra space for the cutter
Quench Protection and Monitoring system moved to the Test Stand 4 area
  Connecting all QPM components together, commissioning will start this week
CERN HFU upgrade for ZMT
  4 HFUs are ready, we will start inserting in the crate this week
Req in preparation for outsourcing upgrade of the remaining 12 HFUs
  Received preliminary quotes from Surya Electronics Inc. - Electronics manufacturer in Glendale Heights, Illinois

## Slide 4: Test Stand 4 PLC progress
Analog Inputs
  40/40 cables pulled
  40/40 terminated, cabinet end
  3 to be terminated on instr. end
  24/40 tested
Digital Inputs
  11/11 cables pulled
  11/11 terminated, cabinet end
  3 to be terminated on instr. end
Analog Outputs
  14/14 cables pulled
  14/14 terminated, cabinet end
  6 pending piping installation
Digital Outputs
  18/18 cables pulled
  18/18 terminated, cabinet end
  12 pending piping installation
Lakeshore modules
  31/31 cables pulled
  31/31 all terminated
  4 pending sensor instrumentation

## Slide 5: Test Stand 4 ORC
ORC for Zero-magnet test only
ORC 1731 created
Electrical ORC documents updated according to the review suggestions and comments
Document with our answers to the review findings and recommendations has been uploaded
Now waiting for the safety walkthrough

## Slide 6: Test Stand 4 ORC (2)
Cryogenic ORC status
 | Engineering Notes | TC number | Review Status
1 | P&ID | F10121488 | Complete
2 | Valve, Instrument, and Equipment (VIE) list | ED0009958 | Complete
3 | Failure Mode Effects Analysis (FMEA) | ED0010083 | Complete
4 | Process controls description | ED0011588 | Complete
5 | System description | ED0010620 | Complete
6 | What If Analysis | ED0011786 | Complete
7 | Operating procedures/checklists |  | 
 | Leak check procedure |  | In progress
 | Cryogenic operating procedure |  | In progress
 | Pre-cooldown checklist |  | Complete
 | Overnight shutdown checklist |  | Complete
 | Pre-warmup checklist |  | Complete
 | Warm & secure checklist |  | Complete
8 | LOTO/configuration control description | ED0012043 | Complete
9 | LN2 supply to thermal shield | EN03232 | Pressure test completed. Awaiting final review/approval of note.
10 | LN2 supply to baffle shield | EN03216 | Pressure test completed. Awaiting final review/approval of note.
11 | LHe supply | EN03233 | Pressure test completed. Awaiting final review/approval of note.
12 | Feed Box/Interconnect/Adapter Box thermal shields | EN03449 | Pressure test completed. Awaiting final review/approval of note.
13 | TeV subcooler pressure vessel | EN01498 | Complete
14 | Feed Box LHe vessel | EN02043 | Complete
15 | LN2 jumper | EN03323 | Pressure test completed. Awaiting final review/approval of note.
16 | LN2 supply to bath | EN03324 | Preliminary review completed, walkthrough completd. Ready for pressure test permit submittal for signature.
17 | Cold GHe jumper | EN03323 | Pressure test completed. Awaiting final review/approval of note.
18 | Cold GHe to Feed Box | EN03391 | Preliminary review completed, walkthrough completd. Ready for pressure test permit submittal for signature.
19 | Feed Box relief piping | EN03531 | Pressure test completed. Awaiting final review/approval of note.
20 | LN2 bath vent | EN03530 | Pressure test completed. Awaiting final review/approval of note.
21 | Vacuum vessel | EN02044 | Note review/approval complete.
22 | Zero magnet turnaround piping | EN03897 | Preliminary review completed, walkthrough completd. Ready for pressure test permit submittal for signature.
23 | Adapter Box and Feed Box-Adapter Box interconnect He piping | EN03454 | Preliminary review completed. Ready for pressure test permit submittal for signature.
24 | Pumping line | EN03851 | (1/2) Pressure test completed. Awaiting final review/approval of note.
 |  |  | (2/2) Preliminary review completed, walkthrough completd. Ready for pressure test permit submittal for signature.
25 | Cryo-Assembly relief spool | EN03755 | Complete
26 | Cryo-Assembly relief vent line | EN03757 | Pressure test completed. Awaiting final review/approval of note.
27 | High-pressure GHe supply | EN03800 | Pressure test permit approved
28 | Return end thermal shield piping | EN03801 | Pressure test completed. Awaiting final review/approval of note.
29 | Cool-down return | EN03838 | Pressure test permit approved
30 | Leads bypass/suction return | EN03835 | Pressure test permit approved
31 | Quench line | EN03898 | Pressure test permit approved