## Slide 1: Cryo Assembly, Cold Mass Status
A. Vouris
Cryo Assy L2 Meeting
August 17, 2020

## Slide 2: Cold Mass Tooling & Design Status
Work Station Equipment
  Order status
    Clock position clamps – Req#306584 PO #666757 (2/25/2020) – Fit up of clamps to station tooling completed. Confirmed - One Clamp usable, second to be returned…Procurement & vendor notified of return and awaiting pick up.
    Indexing brackets mounted to table. Waiting for Metrology to return & final verification.
    Press test fixtures - PRN #242664 extruded shapes rec’d in IB2
    LBNL Survey Ball – @ Village Machine Shop
    Weld Station - received remaining material - Up-grades in process
  Cold Mass Model – drawings (instrumentation/align, pre-weld / post weld) –
      Cold Mass drawing and model work- Final assembly/Interface
      Component drawings for lower plates and tack blocks reviewed and start procurement work flow process today. After drawings are released by D/D

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Cold Mass Practice
    Bus Assembly installed and expansion loops in process – see Rodger Bossert slides
    Shell – strain gauge installation:
      external gauge placement continues today. One internal gauge needs repair
      pre-series shell plates loaded on truck trailer and en-route to vendor for forming/machining.
      Welding supplies received – documents reviewed and forwarded for CERN approvals
      Dummy 316L Beam tube/HT-X tubes ordered #PRN244254
  CM-01
    Fasteners PO: EBN received 7/31 - PRN#244165
    backing strips, drawings released for procurement
    MQXFA03 – metrology inspection complete…rec’d inspection reports today and started reviewing
  Repair traveler
  Engr Analysis & Note:
    Pressure Vessel Note – latest rev. uploaded to docdb and submitted to reviewer (24-April)- Response from Reviewer confirmed Note is now in good shape and approved up until weld sample testing is completed.
    Tack Block testing – report

## Slide 4: Cold Mass Tooling & Design Status
Cold Mass Tooling ORC
  Initial ORC walk through completed on Tuesday, 6/30 …
    ORC-1752, Cold Mass Tooling: All components with exception of Weld Roller was sufficient. Searching requested documents for roller to upload this week
      Outline for Practice unit highlighted by ORC panel for witness points
      Alignment Table docs: FDR Presentation, FRS, design & Analysis Note, Assembly Drawing, HA link, Cold Mass Assy & Inspection Traveler
      Welding Table Docs: FDR Presentation, FRS, design & Analysis Note, Assembly Drawing, HA link, Cold Mass Assy & Inspection Traveler
      Inspection Table Docs: Assy drawings and all above
    ORC-1754, Bus Soldering and Wrapping: submitted
      Reviewer walk through completed Thursday 8/06. Comments received 8/10/20
        HA updated per recommendations and forwarded to DSO for review
        Wrapping station safety cover – procedure analyzed. Cover to be reinstalled
        Soldering station control panel modifications by L Elementi in process
      Bus Soldering Docs: Solder Fixture and Bus Assy drawings, MSDS for solder and Flux, Soldering Note HiLumi Docdb #3256
      Wrapping Station Docs: Drawings for wrapping assemblies and word document with Mu2e ORC link
    Lifting Devices: Orozco to send maintenance records.