## Slide 1: MuCool Resource Needs Mechanical

## Slide 2: MuCool Test Area Overview
MuCool Test Area
  RF Power
    201 MHz (5MW)
    805 MHz (12 MW)
  Class 100 clean room
  Instrumentation
    Ion counters, scintillation counters, optical signal, spectrophotometer
  4T SC Solenoid
    250W LHe cryo-plant
  400 MeV p beam line

## Slide 3: Resource Needs Programmatic
Programmatic/on-going needs
  Pillbox cavity inspection and window change Repetitive
    3-4 times in 2 months
  HPRF cavity installation in magnet in hall July 5
  Installation/removal of cavities under test at
  2nd RF station and/or inside magnet
  (rectangular box(es), ALD-pillbox,
  4-season, Be-wall Repetitive
  201-MHz cavity coupler replacement and
  pump down August 11

## Slide 4: Upcoming Activities
HPRF with beam
Continued testing of existing cavities
  “All-seasons” (vacuum & HP)
  Pillbox
    Button tests
Test of an E parallel to B box cavity
Test of 201 MHz cavity in realistic B
Resource Intensive

## Slide 5: Resource Needs Requested
Design support system for installation of 805 MHz re-circulator and switch (linac gallery and MTA hall) and install. System delivery is scheduled for June 2011.
  Our MP estimate:
    1 man-month engineering
    2 man-week designer
    6 man-week technician for installation
No work started yet

## Slide 6: Resource Needs Requested
Design/Fabrication/assembly of new "parallel" box cavity
  1 man-month engineer
  1 man-month designer/draftsman
  2 man-week fabrication support
Develop plan and tooling and support design for installation of 2.5m bore solenoid in the MTA hall.
  1 man-month engineering
  2 man-week designer
Support for assembly of single-cell 201 MHz MICE cavity vacuum vessel
  1 man-month Tech
Installation of the 2.5m bore superconducting solenoid in the MTA hall
  1 man-week engineering
  10 man-week technician
No work started yet

## Slide 7: Coupling Coil & SCVV

## Slide 9: Conclusions
Programmatic/on-going needs are in good shape w/r to engineering & technical support
  Supplemented to a great deal by experimenters
Resources for upcoming requirements have not been found
  First step is to get engineering support to make detailed estimated of required resources
    Our estimates are likely to be “lite”
    Some things are just slipping day-for-day
      New box cavity
    Work to prepare for installation of coupling coil and SCVV becoming time critical due to complexity & schedule
      SCVV out for bids
      Expect Coupling Coil in 2012