## Slide 1: RunCo Report for IOTA/FAST Meeting 09/11
FAST Startup has started. (will run off-hours)
  Tasks before beam: Laser on / HLRF / Cooldown / System check-outs / SRF conditioning
Cryo: Delays due to insulating vacuum issues
  Cool-down started / CM @60K, moving to 5K
  CC1 & CC2 cooldown to start after CM is at 5K
IOTA: B-R spool / E-Straight disintegration
FESS: gas leak work outside NML delayed 2 wks / ESB A/C waiting for parts / 25t portable on its way
ACNET computer room outages 9/19-20 & 9/23
NML General Network and WiFi fiber was cut on 9/9
Reminders:
  Cave will remain Controlled Access (unless cleared with RunCo)
  Document everything in the eLog!!!
Notes: Why are you looking down here? Look back at the slide.