## CM Prod
CRYOMODULE PRODUCTION Lessons Learnt / Learning from Experience Log
Tuesday 01/12/20
Topics in yellow, Lessons identified can be added below each topic
Sealing surfaces and bellows protection (over all the life cycle of the part)
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
is closed cell foam a problem to get back into CR ? | FNAL | CEA;STFC;RRCAT | major problem on cavity dstring which go back to CR | Yes | carefull blowing and cleaning but it's not a problem | Grimm
Protect seal surfaces and bellows all the time | CEA | all | leak tightness | Yes | put appropriate protection in place | Berry
RGA - Vacuum requirements - Permitted materials
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Cleanliness is and essentiel step |  | all
project RGA specifications are needed |  |  | hydrocarbon contamination | yes | send a project specifications | A Rowe
common specifications for leak tighness and maximum leak rate for retightning |  |  | cold leaks and field emission | yes | send a project specifications | A Rowe
Magnetic Hygiene - Permitted materials
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
316L versus 316LN : "L" flavour can remagnetize | CEA | RRCAT | RF performances | No - info only | recommendation to use 316LN for solenoids
incoherent documents : Handbook µr=1.02 and ED0011955 : µr=1.1 | CEA | all | procurement | Yes | clarified th µr (add also the distance to cavity) | Yi Xie
weldings can remagnetize parts | FNAL | all | assembly/ RF performances | yes | demagnetize after welding if required by the distance to the cavity | Yi Xie
Weld certification
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Are the documents delivered with cryomodule for PED (Europ code) enough for installation in US (ASME code and FESHM requirement) | STFC and CEA | FNAL | cryomodule test/installation in tunnel | yes | check with US certifying body if PED docs are sufficient | A. Klebaner
Shall we involve third party inspector in the certification from the beginning? |  | cavity and cryomodule providers | certification
Geodesic strategy - fiducials, alignment - Alignment Process
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
current leads modified (softer current leads-> easier assembly) for SSR2 modules, | FNAL | RRCAT | SSR2 module assembly | Yes |  | D.Passarelli
better configuration with interfaces (change the supports of the cold mass) for all module types | FNAL | FNAL, STFC, CEA | cryomodules assembly | No - info only |  | V. Roger
factory quality controls (CMM) for many components | CEA/INFN | all | assembly in general | No - info only |  | R. Paparella
Instrumentation interfaces, interfacing of sub-systems to accelerator
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Full calibrated or partial calibrated cernox sensors | FNAL | FNAL, other? | instrumentation procurement | Yes | decission
Welding can be dangerous for sensors | FNAL | STCF,CEA,RRCAT | intrumentation | No - info only | put shorting caps during welding steps
LN thermal shock and TDR for incoming inspection of RF cables | FNAL | - ? - | RF intrumentation | No - info only |  | F. Lewis
Wednesday 02/12/20
The care, maintenance (issue of access to the CM for maintenance / repairs) and final preparation of the CM prior to shipping
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Production / industrialization : how to organize the production line? Standardization: Tooling. Moving parts or moving team?
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
High-skill staffing training (cleanroom, assembly, chemical technicians)
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
OPEN ISSUES LOG
Summary of Open Issue | Organisation Identifying The Issue | Partners who may benefit | When does issue need to be resolved? | Action Required? | Forum to resolve issue (technical meeting, DCB, CCB, Tech Coord meeting, Technical Workshop, other) | Originator / Point of Contact
Add extra rows as necessary

## SRF Fac
SRF FACILITIES Lessons Learnt / Learning from Experience Log
Wednesday 02/12/20
Topics in yellow, Lessons identified can be added below each topic
Flythrough of current SuRF Lab Facility 10 mins per speaker [Subject area]
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
EXAMPLE: We found that distortion of bellows on fitting to the HB 650 HB prototype CM could be best controlled using a jig we designed. Drawing reference ABC123 v1.0 | FNAL | CEA; INFN; FNAL; RRCAT | Cavity string assembly | Yes | All partners assembling cavity strings to consult FNAL drawing ref ABC123 v1.0 for information on their stabilising jig and produce similar. | Saravan Chandrasekaran
Add extra rows as necessary
Setting up infrastructure for Assembly of 650MHz Cryomodule (3D models) Workstations configurations/requirements
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Instrumentation and Calibration standards
Thursday 03/12/20
SuRF Cryogenic systems / Cryomodule system performance acceptance planning
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Facility Preparedness
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
HPR current set-up and proposal for 650MHz cavities (20 mins per institution)
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
SuRF Lab SuraBee system overview: Data management systems - what are the requirement for outputs from the system?
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Data transfer mechanisms. Responsibility of designer of record.
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Close Out/Summary Report
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
OPEN ISSUES LOG
Summary of Open Issue | Organisation Identifying The Issue | Partners who may benefit | When does issue need to be resolved? | Action Required? | Forum to resolve issue (technical meeting, DCB, CCB, Tech Coord meeting, Technical Workshop, other) | Originator / Point of Contact
Add extra rows as necessary

## Cav Design
CAVITY DESIGN Lessons Learnt / Learning from Experience Log
Tuesday 01/12/20
Topics in yellow, Lessons identified can be added below each topic
Multiphysics Simulations
Presentation of the different methods used by each partner to perform multiphysics analysis (simulations, code assumptions, ...)
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
EXAMPLE: We found that distortion of bellows on fitting to the HB 650 HB prototype CM could be best controlled using a jig we designed. Drawing reference ABC123 v1.0 | FNAL | CEA; INFN; FNAL; RRCAT | Cavity string assembly | Yes | All partners assembling cavity strings to consult FNAL drawing ref ABC123 v1.0 for information on their stabilising jig and produce similar. | Saravan Chandrasekaran
Add extra rows as necessary
Presentation of some advanced analysis: How to simulate and take into consideration the fabrication constraints (impact of the welds, of the forming process on the thickness)…etc.
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Wednesday 02/12/20
Multipacting Simulations
Presentation of the different methods used by each partner to perform multipacting analysis (simulation codes, assumptions,…)
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Presentation of some advanced analysis : How correlate multipacting simulation outputs (final number of electrons, growth rate) with experimental observations (conditioning time,…) etc.
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
OPEN ISSUES LOG
Summary of Open Issue | Organisation Identifying The Issue | Partners who may benefit | When does issue need to be resolved? | Action Required? | Forum to resolve issue (technical meeting, DCB, CCB, Tech Coord meeting, Technical Workshop, other) | Originator / Point of Contact
Add extra rows as necessary

## Cav Proc+Test
CAVITY PROCESSING & TESTING Lessons Learnt / Learning from Experience Log
Wednesday 02/12/20
Topics in yellow, Lessons identified can be added below each topic
Processing and testing WG: VTS topic introduction
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
EXAMPLE: We found that distortion of bellows on fitting to the HB 650 HB prototype CM could be best controlled using a jig we designed. Drawing reference ABC123 v1.0 | FNAL | CEA; INFN; FNAL; RRCAT | Cavity string assembly | Yes | All partners assembling cavity strings to consult FNAL drawing ref ABC123 v1.0 for information on their stabilising jig and produce similar. | Saravan Chandrasekaran
Add extra rows as necessary
Vertical cavity testing at RRCAT
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Vertical cavity testing at INFN
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Vertical cavity testing at Fermilab
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Vertical cavity testing at Daresbury
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Vertical cavity testing at DESY
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
VTS specifications
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Thursday 03/12/20
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Processing and testing WG: SSR processing introduction
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
SSR cavity processing plans at Fermilab
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
SSR cavity processing plans at IJCLab
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Processing of spoke cavities
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Process Acceptance Criteria
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Processing and testing WG: 650 processing introduction
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
650 MHz cavity processing plans at Fermilab
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
650 MHz cavity processing plans at RRCAT
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Coaching vendors on the cavity processing
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
650 MHz cavity processing plans at INFN
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Process Acceptance Criteria
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
OPEN ISSUES LOG
Summary of Open Issue | Organisation Identifying The Issue | Partners who may benefit | When does issue need to be resolved? | Action Required? | Forum to resolve issue (technical meeting, DCB, CCB, Tech Coord meeting, Technical Workshop, other) | Originator / Point of Contact
Add extra rows as necessary

## Cav Manu
CAVITY MANUFACTURING Lessons Learnt / Learning from Experience Log
Tuesday 01/12/20
Topics in yellow, Lessons identified can be added below each topic
What are the issues in achieving required RRR, mechanical properties and grain size? Updated high RRR and Nb-Ti Technical specification ? Who are the qualified vendors today?
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
EXAMPLE: We found that distortion of bellows on fitting to the HB 650 HB prototype CM could be best controlled using a jig we designed. Drawing reference ABC123 v1.0 | FNAL | CEA; INFN; FNAL; RRCAT | Cavity string assembly | Yes | All partners assembling cavity strings to consult FNAL drawing ref ABC123 v1.0 for information on their stabilising jig and produce similar. | Saravan Chandrasekaran
Add extra rows as necessary
Vertical vs. horizonthal EBW: pro vs. cons? High Voltage vs Low Voltage EBW machine ? Where does the inclusions and scratches might come from nowadays? Which are the reference procedure for a clean assembly? Forming: how to control control profile and thinning? Control of component, subassemblies and final cavity length, frequency and Feld Flatness?
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Eddy current scanning: is it still needed? Which diagnostic during manufacturing? Visuals, Replicas, XRF? And when in the cycle: after EBW, after treatments? Which other non-destructive diagnostic? Is grinding harmful to cavity performances?
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Wednesday 02/12/20
How challenging are requirements for vendor? How integration qualification is performed? Cavity inner volume during integration: vacuum or not? How to control of cavity frequency and prevent field-flatness degradation?
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Has been External Quality Control (Additional QA/QC asked by orderers) applied? How to successfully transfer and fulfill required specifications? How to transfer cavity geometry reference frame from manufacturing to string assembly? (impact on production cycle, open vs close cavity, etc.)
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
OPEN ISSUES LOG
Summary of Open Issue | Organisation Identifying The Issue | Partners who may benefit | When does issue need to be resolved? | Action Required? | Forum to resolve issue (technical meeting, DCB, CCB, Tech Coord meeting, Technical Workshop, other) | Originator / Point of Contact
Add extra rows as necessary

## RF Couplers
RF POWER COUPLERS Lessons Learnt / Learning from Experience Log
Tuesday 01/12/20
Topics in yellow, Lessons identified can be added below each topic
Design studies on SSR1_SSR2 power couplers - Simulation challenges and issues
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
EXAMPLE: We found that distortion of bellows on fitting to the HB 650 HB prototype CM could be best controlled using a jig we designed. Drawing reference ABC123 v1.0 | FNAL | CEA; INFN; FNAL; RRCAT | Cavity string assembly | Yes | All partners assembling cavity strings to consult FNAL drawing ref ABC123 v1.0 for information on their stabilising jig and produce similar. | Saravan Chandrasekaran
Add extra rows as necessary
Design studies on LB650 & HB650 power couplers - Simulation challenges and issues
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Comparative analysis of PIP-II to the designs used in different facilities worldwide
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Design considerations for assembly operations and integration needs
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Wednesday 02/12/20
Manufacturing of PIP-II high power couplers - Experience feedback
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
On going manufacturing of PIP-II high power couplers
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
704MHz ESS Power couplers manufacturing experience feedback
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
PIP-II Power couplers qualifications and acceptance tests
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Cleaning and RF power test performances needs for Power couplers
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
PIP-II power couplers cleaning and RT RF power tests
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Thursday 03/12/20
Indian Power couplers activities: Coupler test bench and manufacturing experience
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Development of key technologies for Power Coupler manufacturing - experiences and challenges
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
New ceramic developments…
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
LCLS II power coupler manufacturing feedback
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
XFEL large scale power coupler manufacturing feedback
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Hot topics (open discussion): Fermilab to choose a list of questions or technical aspects that need to be discussed more deeply
Summary of Lesson / Information | Organisation Identifying The Learning Point |  | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
OPEN ISSUES LOG
Summary of Open Issue | Organisation Identifying The Issue | Partners who may benefit | When does issue need to be resolved? | Action Required? | Forum to resolve issue (technical meeting, DCB, CCB, Tech Coord meeting, Technical Workshop, other) | Originator / Point of Contact
Add extra rows as necessary

## Cryo Syst
CRYOGENICS SYSTEMS Lessons Learnt / Learning from Experience Log
Tuesday 01/12/20
Topics in yellow, Lessons identified can be added below each topic
Design status & development of PIP-II Cryogenic Distribution System
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
EXAMPLE: We found that distortion of bellows on fitting to the HB 650 HB prototype CM could be best controlled using a jig we designed. Drawing reference ABC123 v1.0 | FNAL | CEA; INFN; FNAL; RRCAT | Cavity string assembly | Yes | All partners assembling cavity strings to consult FNAL drawing ref ABC123 v1.0 for information on their stabilising jig and produce similar. | Saravan Chandrasekaran
Add extra rows as necessary
Cryoplant integration process design
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Cryoplant integration technical design
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
CDS design capacity and requirements
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Cryogenic Distribution System operating modes
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Wednesday 02/12/20
CDS Pressure safety relief sizing methodology: trapped volumes, operational scenarios, failure scenarios, and vacuum reliefs
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
CDS Pressure safety relief sizing Direct Integration Method; CM 2 K relief sizing methodology
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
ESS design solutions for CDS transfer lines and cryogenic vessel supports
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
LCLS-II design solutions for CDS transfer lines and cryogenic vessel supports
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Thermalization of thermal shields, proposed and proven solutions of thermal connections between steel and aluminium/copper - experiences and best practices
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Thursday 03/12/20
Stress and flexibility of bayonets, control valves, and supports
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Stress and flexibility criteria for bayonets
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Thermo-mechanical FEA models development, specification, and methodology
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
OPEN ISSUES LOG
Summary of Open Issue | Organisation Identifying The Issue | Partners who may benefit | When does issue need to be resolved? | Action Required? | Forum to resolve issue (technical meeting, DCB, CCB, Tech Coord meeting, Technical Workshop, other) | Originator / Point of Contact
Add extra rows as necessary

## Req+Int
REQUIREMENTS AND INTERFACE MANAGEMENT Lessons Learnt / Learning from Experience Log
Wednesday 02/12/20
Topics in yellow, Lessons identified can be added below each topic
Design status & development of PIP-II Cryogenic Distribution System
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
EXAMPLE: We found that distortion of bellows on fitting to the HB 650 HB prototype CM could be best controlled using a jig we designed. Drawing reference ABC123 v1.0 | FNAL | CEA; INFN; FNAL; RRCAT | Cavity string assembly | Yes | All partners assembling cavity strings to consult FNAL drawing ref ABC123 v1.0 for information on their stabilising jig and produce similar. | Saravan Chandrasekaran
Add extra rows as necessary
PIP-II Management Requirements Process
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
PIP-II Interface Management Process
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Structured Discussion of PIP-II Requirements and Interfaces (R&I) Management Process
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Thursday 03/12/20
Experience from ESS
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Experience from XFEL
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Experience from CERN
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
OPEN ISSUES LOG
Summary of Open Issue | Organisation Identifying The Issue | Partners who may benefit | When does issue need to be resolved? | Action Required? | Forum to resolve issue (technical meeting, DCB, CCB, Tech Coord meeting, Technical Workshop, other) | Originator / Point of Contact
Add extra rows as necessary

## Controls
CONTROLS Lessons Learnt / Learning from Experience Log
Tuesday 01/12/20
Topics in yellow, Lessons identified can be added below each topic
Topic 1
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
is closed cell foam a problem to get back into CR ? | FNAL | CEA;STFC;RRCAT | major problem on cavity dstring which go back to CR | Yes | carefull blowing and cleaning but it's not a problem | Grimm
Protect seal surfaces and bellows all the time | CEA | all | leak tightness | Yes | put appropriate protection in place | Berry
Topic 2
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Topic 3
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Wednesday 02/12/20
Topic 4
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Topic 5
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Topic 6
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Thursday 03/12/20
Topic 7
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Topic 8
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
Topic 9
Summary of Lesson / Information | Organisation Identifying The Learning Point | Partners who may benefit | Process Step / Activity Affected | Action Required? | Proposed Action | Originator / Point of Contact
Add extra rows as necessary
OPEN ISSUES LOG
Summary of Open Issue | Organisation Identifying The Issue | Partners who may benefit | When does issue need to be resolved? | Action Required? | Forum to resolve issue (technical meeting, DCB, CCB, Tech Coord meeting, Technical Workshop, other) | Originator / Point of Contact
Add extra rows as necessary

## Data Validation
Yes
No - info only