## Slide 1: Some Comments to the issue of Interface Management
DESY XFEL Point of View / Hans Weise
PIP-II Techn Workshop
Dec. 3, 2020

## Slide 2: Interface between people…
Different in different project areas
  We have worked with
    good friends
    partners
    in an customer/producer situation
In almost all areas we had sufficient expertise on site
We enjoyed project partnership but…
  had to fulfill budget restrictions (share holders)
  had to work on avoiding too many formalities
We were in a learning phase wrt. Project Management
  Invested approx. 3% of the ~500M€ of the hardware cost in PM; outside budget book
  Used a lot of common sense; improvisation, flexibility, personal engagement….

## Slide 3: The Cold Linac Case
Here we worked with good long-time friends
We had a quite distributed common knowledge and expertise
Technical interfaces were defined relatively early; before procurement start
Organization interfaces also early but with some exceptions (PED etc)
Different working habits were taken care by extremely close collaboration; very frequent visits / exchange
Easy escalation, not so easy decisions when money was involved…
QA, NCR played an important role!!!
We relied on quite professional interaction with companies; specs, close supervision etc. strict NCR handling…

## Slide 4: Other areas – some comments
CF was 100% DESY responsibility; room data sheets were extensively used
We concentrated more on a compoent than system view
We had many PRRs for components and IRR for systems; quite informal
CAD integration was essential
DESY was responsible for all on site, integration related QC; important for all safety issues (PED, welding, …)