## Slide 1
Cons Gattuso
9/25/20
09:00 Meeting

## Slide 2: Beam Sign Off Sheets
Beam Sign Off sheets can be found on the clip boards outside my office.
Reminder: Once the top portion is completely signed contact Maddie to setting the signing party… Conducted via Zoom

## Slide 3: Switching From Shutdown Mode
Please Update
  MCR Call-in list
    Support Department
      People retiring
      CoVid
      Ect.
    Updated Machine Coordinators
As we bring up machine system
  Please provide clear instruction for operators to follow
    Please clear this with Todd Sullivan and/or Joe Compton prior to making the request

## Slide 4: Alignment Needs Moving Forward
Muon Campus
  Resonate extraction : 5-6 days
    Beam Pipe late next week or following week
  M4 line mask; 1 day
MI/RR
  201 kicker beam pipe: 1 day
    May need to go back due to stand issues
  MI RF cavities: 2 days
    Slated for next week
  112 Multi wire :1 day
    Slated for TODAY
NuMI
  Target: 1 day
  Horn 1: 2-3 days
  Horn 2: 2-3 days
LBNF
  Berm check: 3 days
  MI Tunnel check: 4 days
  MI Tunnel moves: 3-4 days

## Slide 5: Power Outages LBNF-Site Prep
MI20
  Thursday October 1st (Tentative Date)
  Duration: 4 hours
  Time :TBD
MI10 (TBD)
  4 Consecutive Day Shift Outages
    Powered off during day shift
    Restored for evening and owls
  Impacts
    MI10, MI11, MI12, MI14, SBND
  Piggy backing
    Pulse and House power maintenance
Best solution to balance LBNF Feeder tie in work while maintaining vacuum and sumps

## Slide 6: Linac Startup
Thursday Sept 24th
  Turning on water skid and polishing up water systems
Friday Sept 25th
  Turning on Filaments
  Turn-on power supplies
    Lower energy Linac
    High energy Linac
Saturday and Sunday
  Lower Energy Buncher Conditioning
Monday
  Turn-on RF and start Conditioning
Tuesday-Friday
  Get gradient up to nominal and attempt to get beam (if sign-off, Run Conditions and beam permits are complete)
MTA and Booster
  Critical device testing will occur some during Linac startup period.
Draft

## Slide 7: Booster Startup
Complete injection Foil change out today- Monday September 28th
Tunnel cleaning: Tuesday Sept 29th
Air/Filter changes and Remaining RF tunnel checks/repairs: Thursday Oct 1st
Interlock Testing
  Re-Coring: Friday October 2nd
  Search and secure: Saturday October 3rd-Sunday October 4th
  Interlock testing/Rad monitor TLM: Monday October 5th
    After Test Drop interlocks
RF testing/Phase matching: TBD
Switching over to full LCW pump running TBD
Search and Secure Booter: October 8th (evening or owl shift of the 9th )
Turn on Power Supplies : October 8th (evening or owl shift of the 9th )
Complete CDC testing Friday October 9th
Beam Ready: Friday October 9th
Draft

## Slide 8: Muon Campus
Switching over to full LCW pump running: Week of October 5th
  Deal with any water leaks that may appear
Clean Tunnel: Wednesday October 7 and Thursday October 8th
Latest date to close the hatch: Thursday October 8th
  Driven by delivery of the Spare Delivery Ring magnet
Interlock Testing
  Re-Coring: Friday October 9th
  Search and secure: Saturday October 10th -Sunday October 11th
  Interlock testing/Rad monitor TLM: Monday October 12th – Wednesday October 13th
Assess Pre-Covid Shutdown list for potential jobs to be done
Muon Campus will be kept in controlled access.
Draft

## Slide 9: MI8 Line
Cleaning
  Standard tunnel cleaning will occur this afternoon
    ~810 to 836 Can be cleaned
    836-MI gate is current roped off and will require RCT decon
      Next week
      Issues We have all our major hot jobs occurring so we will need to figure out a time to have this done.
  Re-coring
    Next Monday September 28th at the end of the workday
      Exact time will be noted on Monday at the 09:00 meeting
  Search and Secure
    Will have next week sometime after the above cleaning is done
  Interlock testing
    Will follow Search and secure
We plan on having this ALL done mid week if possible

## Slide 10
Items marked “Behind” are related to the LBNF site prep impacts to Main Injector.
Testing
Today and next week
Scheduled
Oct 5th
Scheduled
Oct 12th 13th

## Slide 11
MI40 Abort Room Water Skid
201 kick install
MI/RR
Muon Campus
NuMI Beam line
8/31
Linac/Booster/MTA
Current Schedule
Week 13
Week 14
Week 15
Week 16
Week 17
Weeek18
Week 19
Week 20
Week21
Week 12
This week
RR sext. install
MI307 Buss repair
201 kick install
MI 30 Motion
Resonant ext system
Open Hatch/ D30 Shielding/closing Hatch
M4 line, Mask, multiwire
V907 window
RFKO
MI 30 insert
Multi wire M112
AP30 electrical work (volt)
Linac
Beam
Driven by LBNF-Construction
Horn 1 and Horn 2 installation
9/7
9/14
9/21
9/28
10/5
10/12
Cable pulls (sext. Loads,ext)
900 line leak check
Absorber Interm. HX addition
HVAC Chase Duct
10/19
10/26
11/2
Booster
Beam
MI30
MI40
MI20
MI60N
MI8
Terminations
Misc main/repairs
Last outage that
impacts Linac
Tuneup/beam to MTA/Beam to Booster
Linac Turn on
Oct 12th End
of shutdown
RF vac recovery
Next week
MI40 Abort Room Water Skid
RF Cavity install
RF Cavity testing
SS testing
today

## Slide 12
Running beam to users
MI/RR
Muon Campus
Week 14
Week 15
Week 16
Week 17
Weeek18
Week 19
Week 20
Week21
Week 23
Week 24
Week 22
NuMI Beam line
Linac
Beam
9/14
9/21
9/28
10/5
10/12
10/19
10/26
11/2
Booster
Beam Dump
Beam Based Alignment Tune up
Linac/Booster/MTA
Misc main/repairs
Last outage that
impacts Linac
Tune up/beam to MTA/Beam to Booster
Linac Turn on
Oct 12th End
of shutdown
Beam Based align
Close up of chase/hall
Beam Based Align
Beam for scans
Beam Commissioning
Projected Schedule
11/9
11/16
11/23
Driven by LBNF-Construction
LBNF Site
Prep Berm
Work done
Turn on
MI10/20 cable term.
Pond/LCW turn on
M10* power outage impacts MI12/14/SBND
HEP
Beam Startup
MI/RR
Startup
BNB
Beam
Our Best Guess At This Time
MI 30 Motion
Resonant ext system
Open Hatch/ D30 Shielding/closing Hatch
M4 line, Mask, multiwire
V907 window
MI 30 insert
Q112 Multi wire
Horn 1 and Horn 2 installation
Cable pulls (sext. Loads ,ext)
900 line leak check
Absorber Interm. HX addition
Cable term:MI20, MI30, MI60N
Cable termination
RF vac recovery
Last MI RF
cavity installed
Tunnel component alignment
Topo Mi10/20 align
MI40 Abort Room Water Skid
Cables 10/20 done
MI safe system testing
MI307 Buss repair
MI10 power outages

## Slide 13
Chart: % Of Work Completed AD Summer Shutdown

## Slide 14: General Power Outage and Maintenance status
Power outages/Feeder and Transformer PM
Outages (count)
  Planned (currently)……………5
  Executed……………………...49
  Still need to be planned……..0
  Deferred………………………..2 (by owner)
Power Supply/Vacuum/ Water Maintenance Work Completed
*% of completed
Chart: 
 | 0.93
 | 0.07
Chart: Maintenace Work Compelete
| Linac | Booster | MI/RR | NuMI | Muon Campus | External beams
 | 0.95 | 0.9 | 0.85 | 0.9 | 0.86 | 0.85
Remaining outage are LBNF site prep driven