## Slide 1: Magnet Fabrication Travelers, Non-Conformities and Resolution
Katherine Ray – LBNL (QA)
Mike Solis – LBNL (Procurement Technical Contact)
October 20, 2020 – MQXFA06 Structure and Loading Review

## Slide 2: Overview
State of the Magnet Fabrication Travelers
Non-Conformances on MQXFA06
Pion Non-Conformance Discussion

## Slide 3: Magnet Fabrication Travelers Overview
# | Title | Revision | ID
1 | Coil Acceptance WI | A | SU-1011-5294
2 | Coil CMM WI (new) | A | SU-1012-3958
3 | Yoke Pre-Stack WI | C | SU-1008-8072
4 | Yoke Half Stack WI | E | SU-1009-7829
5 | Shell Instrumentation WI | E | SU-1009-3745
6 | Shell-Yoke Assy WI | C | SU-1008-2169
7 | Loadpad Pre-Stack WI | B | SU-1008-8075
8 | Dressed Coil WI | G | SU-1008-8073
9 | Pad-Collar Assy WI | B | SU-1010-1610
10 | Coil Pack Subassy WI | C | SU-1008-8074
11 | Magnet Electrical QA at LBNL | D | SU-1010-1903
12 | Magnetic Measurements | A | SU-1010-2018
13 | Integration and Loading WI | C | SU-1011-5637
14 | Axial Rods Instrumented WI | D | SU-1008-8069
15 | Connectors and Finishing WI (new) | A | SU-1012-5517
16 | Splice Box WI | C | SU-1008-8067
17 | Magnet Shipping WI | B | SU-1011-3284

## Slide 4: Magnet Fabrication Travelers Overview
# | Title | Revision | ID
1 | Coil Acceptance WI | A | SU-1011-5294
2 | Coil CMM WI (new) | A | SU-1012-3958
3 | Yoke Pre-Stack WI | C | SU-1008-8072
4 | Yoke Half Stack WI | E | SU-1009-7829
5 | Shell Instrumentation WI | E | SU-1009-3745
6 | Shell-Yoke Assy WI | C | SU-1008-2169
7 | Loadpad Pre-Stack WI | B | SU-1008-8075
8 | Dressed Coil WI | G | SU-1008-8073
9 | Pad-Collar Assy WI | B | SU-1010-1610
10 | Coil Pack Subassy WI | C | SU-1008-8074
11 | Magnet Electrical QA at LBNL | D | SU-1010-1903
12 | Magnetic Measurements | A | SU-1010-2018
13 | Integration and Loading WI | C | SU-1011-5637
14 | Axial Rods Instrumented WI | D | SU-1008-8069
15 | Connectors and Finishing WI (new) | A | SU-1012-5517
16 | Splice Box WI | C | SU-1008-8067
17 | Magnet Shipping WI | B | SU-1011-3284
We continue to update the travelers based on lessons learned. We have 2 new travelers since last time, one for using the Leica, one for describing the wiring
All travelers were used and signed off for MQXFA05

## Slide 5: Change Records
We are tracking Non-Conformances, Deviations and Engineering Changes in one spreadsheet
These are currently communicated to Fermilab L2 on a monthly basis

## Slide 6: MQXFA06 Change Records
The NCRs on A06 thus far include:
  (#29) wrong s/n on collars (reworked)
  (#80) Dents in master keys (discussed during A05 review) (accept as is)
  (#99) Loadpad minor non-conformances (accept as is)
  (#129) Overtorqued yoke half stacks, wrong bushing ordering (reworked)
  (#138) Scratched yokes (reworked – stoned/polished)
  (#140) rust on loadpads (reworked – cleaned)
  (#142) Coil 122 sequential R (CRITICAL) (accept as is, create as-built schematic)
  (#145) Coil 122 hole in GPI (reworked)
  (#147) Coil 122 flashing not filed down, damaged GPI on coil 117 (CRITICAL) (reworking/reworked)
  (#148) Coil 119 PHB03a and PHB02a wires protruding (CRITICAL) (reworked)
  (#149) All 4 coils have pion location out of spec (CRITICAL) (to be discussed)

## Slide 7: Pion Location Data for MQXFA06

## Slide 8: Investigation
Question: Is the pion location out of spec due to delamination?
Question: If we clamp down on delaminated areas, will it come in spec?
Question: Should we clear the fiberglass and glue pion directly to the titanium pole?
FNAL sent us a section of coil 108 that had 6 pin holes, 3 looked delaminated, 2 looked still laminated, one uncertain
Measured all 6 locations
Clamped one to see if we could press the area down
Cleared fiberglass in two locations
Installed pions in 4 locations (two with fiberglass, two cleared)

## Slide 9: Some examples of out of spec pion locations

## Slide 10: Pion locations on Coil 117
In Spec
In Spec
Out of Spec

## Slide 11: Clamping
Chart: Difference between clamped and not
| Min | Avg | Max
delam-xsec2 | -0.167 | -0.14 | -0.116
clamp-xsec2 | -0.156 | -0.132 | -0.104
Difference between clamped and not is 8-12 microns

## Slide 12: Pions vs. Delamination on small section of 108
Chart: Pion Location Difference from Nominal
| delam-xsec1 | delam-xsec6 | delam-xsec2 | iffy-xsec3 | lam-xsec4 | lam-xsec5
Min | -0.181 | -0.189 | -0.167 | -0.228 | -0.227 | -0.182
Avg | -0.142 | -0.142 | -0.14 | -0.209 | -0.212 | -0.163
Max | -0.103 | -0.065 | -0.116 | -0.178 | -0.196 | -0.14

## Slide 13: Further Steps
We took measurements with the pions installed on 10/19/20, but the data is not processed yet
Two possible approaches:
  File the pions
  Clear the fiberglass