## Slide 1: 200 kT Water Cherenkov Detector Excavation
50% Conceptual Design Review

## Slide 2: Outline
Overview of 200 kT WCD Layout
Generalized Development Sequence
200 kT WCD Excavation Sequence
Ground Support & Stability Modeling
Ventilation
Preliminary Conceptual Cost Estimate
Updates Going Forward
  Utility Drift Size
  AoRs
  Other Excavations

## Slide 3: 200 kT WCD Layout

## Slide 4: 200 kT WCD Excavation Sequence
Ramp to dome (exploratory drift)
5117 Ramp & drift to center of WCD
Top level dome excavate/support
Raise bore
Continue down dome
Excavate tank
  5 meter benches
  Work in sections

## Slide 5: 200 kT WCD Excavation Sequence

## Slide 6: WCD Excavation Cycle
Mucking
Wall Scaling & Cleanup
Cable & Rock Bolting
Explosive Loading
(Foot Traffic)
Blasthole Drilling
No-go Zone for Excavator Backup

## Slide 7: Ground Support
WCD Excavation
  15m, 50T cable bolts, 2.5m centers
  5m, 20T resin bolts, 1.25m centers
  100mm mesh
  100mm shotcrete
Utility Drift
  3m resin bolts, 1.5m centers
  75mm shotcrete
Others
  1.2m resin bolts, 1.5m centers

## Slide 8: Ventilation & Hoisting
Driven by diesel requirements
~125,000 cfm in 5117 Ramp
Volume and velocity in WCD excavation?
~100,000+ cfm at working level in WCD
Crane/Hoist in utility drift, 4T – 8T capacity

## Slide 9: Alternative Utility Drift
270 m2
950 m2