## Slide 1: 302.4.01 Magnets Vertical Test at BNL Weekly Report
Joseph F Muratore – BNL
07-Dec-2020

## Slide 2: Return to Work Planning– Building 902 High Bay
Magnet Division Electrical Group |  |  |  |  | 
Date | Days | Probable Staff | Job | # of SMD staff | Staff %
Ph 1 | D+0 | William McKeon,Frank Teich, John Cintorino | Tower water, compressors for pump and purge. | 6 | 15
 |  | Ray Ceruti, Glen Jochen, Toby Levin | Coil fabrication preparation. |  | 
 |  |  | DI water, QA cable, start cryo plant. |  | 
Ph 2 | D+15 | Above+ Piyush Joshi, Honghai Song | Validate and debug field measurement | 21 | 50
 |  | Sebastian Dimaiuta, Daniel Sullivan | LabView program. |  | 
 |  | Joseph Muratore, Patrick Doutney, Richard Felter | AUP magnet preparation. |  | 
 |  | William Themann, Dominick Milidantri | QA cable, start cryo plant, start coil fabrication. |  | 
 |  | Matthew Milidantri,Drew Carleton, Michael Hartsough | Alpha G. |  | 
 |  | Thomas Van Winckel, Jesse Schmalzle, Andy Marone |  |  | 
Ph 3 | D+30 | Above + Peter Galioto, Suresh Deonarine, Jorge Galarraga | Start AUP magnet testing. | 30 | 75
 |  | Shresht Joshi, Anis Ben Yahia, Henry Hocker, Paul Kovach | Prepare 10kA and 8kA PS for |  | 
 |  | Michael Anerella, Chris Runyan | sweet spot magnet testing. |  | 
Ph 4 | D+45 | Above + John Cozzolino, Steve Plate, Ramesh Gupta | Engineering and scientific work. | 40 | 100
 |  | Brett Parker, Kyle Capobianco, Kathleen Amm |  |  | 
 |  | Peter Wanderer, William Sampson, Marteenio Sams, |  |  | 
 |  | New Admin |  |  | 
P. Joshi and K Amm.
Started 1-June
Started 18-June
Started 6-July

## Slide 3: CRYOGENICS UPDATES
  Work on CTI4000 to replace Phase 1 Heat Exchanger (LN2) in progress.
    New heat exchanger is in place. Welding to pipes is underway.
    CTI4000 cooldown most probably after New Year (4-January 2021).
    Aiming to have MQXFA05 in Test Dewar and ready to cooldown before Christmas.
  Linde1610 in operation and making LHe.

## Slide 4: QUENCH ANTENNA UPDATE
  Quench antenna to be shipped to Fermilab for amplifier replacement on noisy channels.
  Packed in warm bore tube crate and ready to ship.
    No need to use coil crate.
    Fits without bending cables on lead end.
  Expecting truck on Wednesday.
    Dedicated, air ride truck, as for coils.
  Cost variance?
  Cooldown of MQXFA05 to start 4-Jan-2021.

## Slide 5: MQXFA05 UPDATE
  Magnet on shipping fixture and installed on horizontal test stand for incoming electrical tests.
  Initial electrical checkout including hipots were finished successfully. Two reversed tap pairs found.
  All hipots successful to 3680V with little or no leakage currents.
  Initial strain gauges are done. All gauges are working.
  Yet to do before up-righting:
    Magnet bore video.
    New centering fixture did not fit due to strain gauge harnesses. Fixture has been modified and is installed.
    Spacers to be added to WBT. Design will be presented at Giorgio’s meeting by Mike.
  Main Test Plan is finished.
  MM Test Plan is finished
  Expect in test Dewar & ready for cooldown before Christmas.
  Cooldown of refrigerator and magnet 300-100K cooldown to start 4-Jan-2021.

## Slide 6: 2nd TEST FIXTURE UPDATE
  Work on second top plate/test fixture in progress.
    Mains and CLIQ leads are installed.
    Lambda plate and hanging hardware are installed.
    Still to be done:
      Connector trees and wiring.
        Wiring for connector trees has been started.
        New electrical and mechanical techs are being hired and will be helping with remaining work.

## Slide 8: MQXFA04 UPDATE
  Final electrical measurements are done – all tests OK. Electrical check sheets (Excel) are finalized.
  Test summary for CERN done.
  Magnet at Fermilab.

## Slide 9: MQXFA03 UPDATE
  Magnet at Fermilab.
  Missing jam nuts from return end found.
  Were removed to install micarta centering fixture for warm bore tube.
  Nuts placed in hardware cabinet and not re-installed before shipping.
  “Rust” on threads probably micarta dust.