## Slide 1: Cryo Assembly, Cold Mass Status
A. Vouris
Cryo Assy L2 Meeting
December 07, 2020

## Slide 2: Cold Mass Tooling & Design Status
Work Station Equipment
  Order status
    Clock position clamps – Req#306584 PO #666757 (2/25/2020) – reworked part is in IB2 awaiting QC
    Indexing brackets mounted to table - Locations adjusted and verified.
    Press test fixtures - PRN #242664 extruded shapes rec’d in IB2 –
      ordering some vacuum components to use with leak test fixtures
      Modifying circ weld fixture for procurement/fabrication
    LBNL Survey Ball – @ QC
    Weld Station - Testing by ESH&Q shows sufficient draw from fume extractor. First 2 Samples taken confirmed within limits. Need additional 4 samples (2 cold masses).
    Circumferential welding procedure confirmed well within limits and no need for additional samples.
    Cold Mass Model – drawings (instrumentation/align, pre-weld / post weld) –
      Cold Mass drawing and model work- Final assembly/Interface – Rev. A released. Need to make additional changes

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Cold Mass Practice
    Bus Assembly and expansion loops – see Rodger Bossert slides
    Shell :
      Utilized indexing clamps for transporting CM practice unit from alignment table to inspection table
      Lower plates (saddles) presently being welded to cold mass – Today, 7-Dec.-2020
      NDE HA and other forms complete. in Procurement. NDE vendor available in 2-3 days after PO
  CM-01
    All pre-series components with procurement
      Tack block expecting initial shipment for 1st pre-series prior to Holidays (Dec. 24th)
      Lower plate order complete
      Shell machine complete and received at Fermi – Pressure washing complete
        Re-inspecting Machining today
        Thickness scan at 6 locations – marking specific locations for QC to scan (UT)
        Strain gauge mounting – mounting after inspection
      Cold Mass Assy traveler – revisions complete
      MQXFA04 – metrology inspection complete
      Repair traveler
  Engr Analysis & Note:
    Pressure Vessel Note – latest rev. uploaded to docdb and submitted to reviewer (24-April)- Response from Reviewer confirmed Note is now in good shape and approved up until weld sample testing is completed.

## Slide 4: Cold Mass Tooling & Design Status
Cold Mass Tooling ORC
  Initial ORC walk through completed on Tuesday, 6/30 …
    ORC-1752, Cold Mass Tooling:
      Outline for Practice unit highlighted by ORC panel for witness points -
      Prepare for and complete Phased Array UT (NDE) – PO in progress
      Fit and weld lower saddle plates Matt-CR6 sample - NEXT
      Alignment Table docs: FDR Presentation, FRS, design & Analysis Note, Assembly Drawing, HA link, Cold Mass Assy & Inspection Traveler
      Welding Table Docs: FDR Presentation, FRS, design & Analysis Note, Assembly Drawing, HA link, Cold Mass Assy & Inspection Traveler
      Inspection Table Docs: Assy drawings and all above
      Electrical Q/A from OEM Fume extractor/Weld Roller vendors replied…to be uploaded to ORC file
    ORC-1754, Bus Soldering and Wrapping - APPROVED