## Slide 1: Inventory
Cable at FNAL | Qualified
P43OL1136 | QXFA130
P43OL1139 | Q
P43OL1141 | Y
P43OL1146 | 
P43OL1147 | Y
Cable at BNL | Qualified
P43OL1135 | QXFA220
P43OL1143 | Y
P43OL1144 | Y
P43OL1145 | Y
P43OL1148 | 
P43OL1149 | 
P43OL1150 | 
Coil Parts | Qt.
Pole | 9 sets
End Parts | 12 sets
Wedges | 80 sets
QH Trace | 28 sets
NbTi cable | 32 sets

## Slide 2: FY20 Procurement Status
Item | PO | Qt. | Delivery Date | In Process/Received |  |  | 
Pole | ˅ | 28 sets | 02/26/2021 | 18 sets/10 sets |  |  | 
End Parts | ˅ | 28 sets | 12/04/2020 | IC1 | IC2 w slits | IC3 w slits | IC4 w slits
 |  |  |  | IC5 | IR1 w slits | IR2 w slits | IR3 w slits
 |  |  |  | OC1 w slits | OC2 w slits | OC3 w slits | OC4 w slits
 |  |  |  | OC5 | OR1 w slits | OR2 w slits | OR3 w slits
Plasma Coating | ˅ | 28 sets | 02/26/2021 | IC1 | IC2 | IC3 | IC4
 |  |  |  | IC5 | IR1 | IR2 | IR3
 |  |  |  | OC1 | OC2 | OC3 | OC4
 |  |  |  | OC5 | OR1 | OR2 | OR3
Wedges | ˅ | 78 sets | 07/17/2020 | L1 Long | L1 Short | L2 Long | L2 Short
R&I Liners | ˅ | 10 | 10/28/2020 | Waiting for welding and final machining |  |  | 
NbTi | CERN | 2200 m | 2/30/2020 |  |  |  | 
Modified IC3 |  | 2+26 | 12/23/2020 | Delayed, to be updated by the end of 1/4 |  |  | 

## Slide 3: QC Priority List
R&I Liners (10 pcs) (25-2033110 Rev A): Reject 1 pc
L2 Pole (40 pcs_keyway repair) :Reject 7 pcs
L2 Splice block (28 pcs) : Pass QC
L1 LE pole and L2 LE pole (10 sets)
L1 RE pole (10 pcs)
L2 RE pole (10 pcs)
L1 pole (90 pcs)
L2 pole (90 pcs)

## Slide 4: FY21 Procurement
End parts 12 sets (in option) + 2 additional sets
  Waiting for the vendor to deliver the two pieces of modified IC3.
  Installation during coil fabrication at both labs and verify the design modification.
  Submit the request to exercise the procurement option in January/February.
Plasma coating on End parts in May, 2021
Pole parts 12 sets (in option) + 2 additional sets in May, 2021
Coil Parts and Materials Status on Jan. 4, 2021