## Slide 1: 302.4.04 – Cryo-assemblies Horizontal Test Weekly status report
Guram Chlachidze
Jan. 4th, 2021

## Slide 2: Stand 4 upgrade
Remaining Zero-magnet Tests
Hi-potting test at 100 K is complete
  Shorted bus was at 118 K
  Coil-to-ground hi-potted at 500 V, leak current was 0.1 uA
Automated warmup and cooldown to be verified
  Sullair compressors tripped on Dec.25 due to failure of the 2nd stage contact, may need 2-3 days to be ready for cooldown
Preparation for Production Tests
Quench Recovery Line (Off-project)
  New Req initiated for the pipefitting T&M
  Old Req. # 314576 (Fixed price contract) will be canceled
Cryo-assembly vacuum sleeve
  PO # 673914 went to Ability Engineering
  Due date shown in the PO is Jan. 29
ek

## Slide 3: Preparation for Production Tests
Cryo-assembly 80 K thermal shields arrived
Req #315263 for the Return End thermal shield was initiated last
  Delivery date March 15
Warm finger assembly
  Small WF assembly is complete
  All tubes and parts for the large warm finger have been delivered
PO #672003 (Req. #311345) for the CERN HFU upgrade is approved
  CERN HFU parts delivered to the vendor
E.H. WACHS cutters
  PO 672401 approved
  Delivery date is 01/22
No updates on procurement of the trailer