## Slide 1: Cryo Assembly, Cold Mass Status
A. Vouris
Cryo Assy L2 Meeting
January 01, 2021

## Slide 2: Cold Mass Tooling & Design Status
Work Station Equipment
  Status
    Clock position clamps – Req#306584 PO #666757 (2/25/2020) – reworked part is in IB2 awaiting QC
    Press test fixtures - PRN #242664 extruded shapes rec’d in IB2 –
      Trial run on leak test fixture completed and tweaked for final combination Leak Check/Pressure Test after NDE (UT)
      Circ weld fixture drawings revised and in approval process To be forwarded for procurement/fabrication shortly
    LBNL Survey Ball – @ QC – requested and forwarded drawings for inspection last week Friday.
    Weld Station - Testing by ESH&Q shows sufficient draw from fume extractor. First 2 Samples taken confirmed within limits. Need additional 4 samples (2 cold masses).
    Circumferential welding procedure confirmed well within limits and no need for additional samples.
    Lead Can – design complete and procurement specification drafted – revision updated
    Cold Mass Model – drawings (instrumentation/align, pre-weld / post weld) –
      Rev. A released. Need to make additional changes
      Writing Design/Draft Work request for Cold Mass drawing updates on assemblies.

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Cold Mass Practice
    Bus Assembly and expansion loops – see Rodger Bossert slides
    Shell :
      Lower plates (saddles): inspection after welding in process today
      Checking on NDE vendor (available in 2-3 days after PO). Vendor registration needed.
  CM-01
    All pre-series components with procurement
      Tack block shipment for 1st pre-series around Holidays…. At plater, Now due by end of week, Jan 4th. Remaining pcs will go to plater this week.
      Lower plate : PO 671905, Moritz – delayed again, first article on site this week for FNAL approval. Remaining order rough machined, awaiting release to stress relief & final machining.
      Shell:
        Internal Strain gauge mounting on shell complete except for 1 gauge failure. This gauge repaired and attached today. Will test and setup for external gauges by end of this week/beginning next week.
      Cold Mass Assy traveler – revisions in process
      MQXFA04 – metrology inspection report received – will review with metrology and forward final results to Sandor/Giorgio Ambrosio
      elect. Check out see R. Bossert report
      Repair traveler
  Engr Analysis & Note:
    Pressure Vessel Note – uploaded to docdb - Note approved up until weld sample testing.

## Slide 4: Cold Mass Tooling & Design Status
Cold Mass Tooling ORC
  Initial ORC walk through completed on Tuesday, 6/30 …
    ORC-1752, Cold Mass Tooling:
      Outline for Practice unit highlighted by ORC panel for witness points -
      Prepare for and complete Phased Array UT (NDE) – PO in progress (R. Bushek/A Panvica to be notified for work Witness)
      Alignment Table docs: FDR Presentation, FRS, design & Analysis Note, Assembly Drawing, HA link, Cold Mass Assy & Inspection Traveler
      Welding Table Docs: FDR Presentation, FRS, design & Analysis Note, Assembly Drawing, HA link, Cold Mass Assy & Inspection Traveler
      Inspection Table Docs: Assy drawings and all above
      Electrical Q/A from OEM Fume extractor/Weld Roller vendors replied…to be uploaded to ORC file
    ORC-1754, Bus Soldering and Wrapping - APPROVED