## Slide 1: Bus and Instrumentation Work Status
R. Bossert 1/11/2021

## Slide 2
Bus, Expansion Loop and Instrumentation Status
Assembly and detail drawings for the bus and expansion loops are 100% complete. New revisions of the major assemblies were released last week. Another set of revisions, with a few minor updates, will be completed and released in the near future.
A final version of the Q2 bus insertion procedure, including expansion loop forming, has been completed. Minor modifications are in process based on the first CERN insertion of a bus into a Q2. A demonstration for CERN personnel of the expansion loop forming on our mockup will also be done if desired by CERN.
Implementation of the special wiring for the first pre-series cold mass (MQXFA03 and MQXFA04) is taking place. Strain gauges and green putty have been removed. Quench protection heater wiring system is scheduled to be done this week. Housings for termination of voltage taps were received last week, so termination of unneeded voltage taps can proceed. Redesign of splice housing on the Qb end has been completed and parts are in process. A plan for attachment of the splice housing on Qb end is in place. Label design and plan for routing of voltage taps that are not to be terminated will be completed this week.
New design for the Qa and Qb splice fixtures has been completed and parts have been ordered. Fermilab stock heating elements will be used.
A modified version of the bus housing lock, to be used for the preseries and production magnets, has been designed and is being completed by design/drafting.
All parts for Q2 expansion loop forming and support have been received. They are included in a kit for this process. The last of the parts needed was received on Jan 8. The kit will be sent to CERN this week.

## Slide 3
An order for bus housing parts for two more Q1/Q3 and two more Q2 busses has been received. The clips were rejected and have been replaced. The new clips have arrived and have passed inspection. Hardware order for all bus housings and end hold down parts is being done by procurement.
Another update to the cold mass assembly traveler has been created based on experience to date. The update is expected to be available Jan 11th and will be used on the first preseries. A companion procedure for Q1/Q3 bus and expansion loop is in process.
All busses for Q2 prototypes and Q1/Q3 preseries magnets are soldered. Some minor rework of the bus soldering fixture will take place before soldering of the production busses begins. Bullet #1, addition of thermocouples, has been done. Temperature tests have been done with a new 11 meter element. Strand sample testing been completed, at a range of temperatures between 220C and 320C. Bullet #2, cold block design, is taking place this week. Bullet #3 has not been started.
  More thermocouples will be added to allow more detailed monitoring of the temperature.
  “Cold Blocks” will be implemented to better prevent solder from wicking into the non-soldered area. Parts for the cold block and soldering cart have been procured and design on this part is underway.
  A second temperature will be added to the program to allow the bus to be heated to an intermediate level after soldering to facilitate removal from the fixture.
Discussions for the completion of the IFS and CLIQ/Kmod capillaries are taking place with CERN.
Bus, Expansion Loop and Instrumentation Status