## Slide 1: ArgonCube Engineering Meeting
January 22nd, 2021

## Slide 2: Agenda
Light Readout – Sasha Selyunin
Charge Readout – Brooke Morrison
Module 0 Schedule – Andrew Lambert
Round Table - All

## Slide 3: Module 0 Recent Progress
Functional testing enclosure for pixel boards: production at LBNL shops completed
  Enclosure assembly being assembled today & testing beings
Functional testing enclosure for light tiles: production complete, assembly complete, in testing now
Top flange LAr inlet modification – welding complete?
James and I combed through Module 0 schedule this week & updated (see next slide)
Continuing tasks:
  PLC
  Charge tile shipment to Bern & test
  Complete light readout testing
  Cryogenics system regeneration
  Procedure development

## Slide 4: Module 0 Assembly & Test Schedule
Test begins March 10th
Critical path currently flows through charge + light tile warm testing prior to TPC assembly
Cryogenic PLC development competing with this based on recent updates from Bern
  Igor Kreslo (Bern) working closely with FNAL colleagues on this

## Slide 5: Module 0 Procedure Development
No. | Document Description | Status | Who? | Notes
1 | Field Cage Assembly Procedure | Complete | Francois/SLAC | Completed, used in Module 0 HV
2 | TPC Integration Procedure | Near Complete | JJ/CSU | Incorporate lessons learned from Module 0 HV assembly, pixel mapping & light mapping
3 | Pixel Board Warm Enclosure Acceptance Test (Post Shipment) | Testing | Brooke/LBNL | Dan & Armin reviewing
4 | Pixel Anode Bring-Up (Post TPC Installation to Cryostat, warm) | Testing | Brooke/LBNL | Dan & Armin reviewing
5 | Light Readout Acceptance Test (Post Construction, pre-installation) | Testing | Igor/BERN; Nikolay/JINR | 
6 | Light Readout Bring-Up (Post TPC Installation to Cryostat, warm) | Testing | Igor/BERN; Nikolay/JINR | 
7 | Integrated TPC Grounding & Noise Testing Procedure (warm) | Started | Armin/LBNL;Igor/BERN Review: Linda | Charge + Light Teams
8 | High Voltage Cable Insertion Procedure (warm) | Started | Knut/SLAC | Incorporate lessons learned from Module 0 HV assembly
9 | TPC Lifting & Installation Procedure | Started | James/FNAL;AL/LBNL | Covers TPC removal from support frame through cryostat installation