## Slide 1: Cryo Assembly, Cold Mass Status
A. Vouris
Cryo Assy L2 Meeting
January 19, 2021

## Slide 2: Cold Mass Tooling & Design Status
WorkStation Equipment
  Status
    Clock position clamps – reworked part QC inspection complete and notified of inspection report availability.
    Press test fixtures – Radial Test fixtures fabrication by VMS
    Lead Can – design complete and procurement specification drafted – revision updated. Reviewed final drawings last week. Finalizing approvals and procurement process this week.
    Beam insert fixture drawing complete, material due to arrive in 1-2 days – work by VMS (complete end of this week/early next week
    Re-setting Alignment Table through PPD Metrology inspection. Minor adjustments/cleaning needed and will remeasure next week
    Cold Mass Model – drawings (instrumentation/align, pre-weld / post weld) –
      Rev. A released. Need to make additional changes
      Writing Design/Draft Work request for Cold Mass drawing updates on assemblies.
    Additional tooling:
      Shell profile and machining gauges
      SSW supports for Inspection table

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Cold Mass Practice
    Bus Assembly and expansion loops – see Rodger Bossert slides
    Shell :
      Lower plates (saddles): inspection complete - report reviewed
      NDE vendor Registered (2-3 days after PO). PO today then scheduling of work
  CM-01
    Pre-series components
      Tack block shipment for 1st pre-series expected end of last week…. Not received (follow up today).
      Lower plate : PO 671905, Moritz – first article received in QC.
      Shell:
        Internal Strain w/ internal gauges wired & External gauge mounting complete and tested.
      Cold Mass Assy traveler – revisions in review
      MQXFA04/03 – metrology inspection report received – calibrating tooling needed.
      Heat –X set up and leak tested. End plugs to be cut off and final cleaning to be done
      elect. Check out see R. Bossert report
      Repair traveler
  Engr Analysis & Note:
    Pressure Vessel Note – uploaded to docdb - Note approved up until weld sample testing.

## Slide 4: Cold Mass Tooling & Design Status
Cold Mass Tooling ORC
  Initial ORC walk through completed on Tuesday, 6/30 …
    ORC-1752, Cold Mass Tooling:
      Outline for Practice unit highlighted by ORC panel for witness points -
      Prepare for and complete Phased Array UT (NDE) – PO in progress (R. Bushek/A Panvica to be notified for work Witness)
      Alignment Table docs: FDR Presentation, FRS, design & Analysis Note, Assembly Drawing, HA link, Cold Mass Assy & Inspection Traveler
      Welding Table Docs: FDR Presentation, FRS, design & Analysis Note, Assembly Drawing, HA link, Cold Mass Assy & Inspection Traveler
      Inspection Table Docs: Assy drawings and all above
      Electrical Q/A from OEM Fume extractor/Weld Roller vendors replied…to be uploaded to ORC file
    ORC-1754, Bus Soldering and Wrapping - APPROVED