## Slide 1
PIP-II Booster Charge Zero (CHG0) Detector Internal Review
David Johnson PIP-II L3 Manager for Booster Upgrades
Proton Source Department
25 - January - 2021

## Slide 2: Welcome and Schedule
I would like to Welcome everyone to the Internal Review for the new Booster CHG0 Detector
A special thanks to the Review committee
  Paul Derwent
  David Capista
  Brian Fellenz
Schedule
  Welcome: David Johnson (10 min)
  Present CHG0 and Requirements: C. Y. Tan (10 in)
  TBD – Aisha Ibrahim (30 min)
  Questions (20 min)
  Committee Deliberation (35 min)
  Closeout (15 min)

## Slide 3: Background
The Proton Source through PIP-II Accelerator Upgrade task is replacing the current CHG0 detector and electronics with a high resolution, large dynamic range, good linearity, and low distortion commercial unit.
The main purpose of this replacement is to provide a detector with a higher charge range to accommodate the continued increase in cycle intensity and to provide for a finer resolution and linearity due to the strict requirement for increased acceleration efficiency to the 98% range for PIP-II.
The complete CHG0 system will consist of
  a commercial Unser-style Current Transformer with control, processing, amplification electronics,
  a front-end for interfacing to the control system and distribution electronics.
The current commercial unit under selection id the Bergoz NPCT-CF6”-96.0-120 UHV with the very high resolution and radiation-resistant with matched interface cable.

## Slide 4: Background
It is desired to install the detector in the tunnel and cables to the gallery during the 2021 Summer shutdown.
The front-end electronics, distribution electronics, and ACNET interface will be assembled and commissioned post shutdown during FY22.
The 14-week lead time for the detector means the detector needs to be ordered as soon ad the PIP-II project obtains CD-3A.
Timeline
  The PIP-II CD-3A review is scheduled for Feb 17th
  The DOE CD-3A approval is estimated by March 15th  needed to (commit to) spend money
  The RQN process starts Jan 26th with approval Feb 15th
  PO Awarded to Bergoz April 29th
  Delivery of Detector Aug 9th with QC inspection between Aug 9th and Aug 16th
  Installation takes place After QC inspection and electronics check out complete

## Slide 5: Charge
The goal for the current internal review is to focus on the detector and tunnel installation, so that the project can move forward on the purchase of the detector and installation stands. We would like the committee to comment and provide any recommendations concerning the suitability of the selected detector for the Booster beam current monitor. Additionally, we would like the committee to consider the following three charge questions
We would like the committee to consider the following two Charge questions
  Have the requirements for the replacement detector been sufficiently spelled out?
  Does the selected unit meet the specifications?
  Does the installation hardwire look appropriate?