## Slide 1
PDR Expectations
Eric James
NS Integration Workshop
March 16, 2021

## Slide 2: DUNE Design Reviews
We attempt to incorporate a series of three reviews into the design process for each DUNE detector element
Conceptual Design Review (CDR)
Preliminary Design Review (PDR)
Final Design Review (FDR)
ND CDR was held July 7-9, 2020

## Slide 3: Connection to Design Reports
For each detector, DUNE produces Conceptual Design Reports and Technical Design Reports that are reviewed by the LBNC
Conceptual Design Reviews have been typically carried out in conjunction with production of the Conceptual Design Report
Would nominally expect to have completed at least Preliminary Design Reviews in advance of releasing Technical Design Report (process was a bit more convoluted for Far Detector Module 1)

## Slide 4: Connection to DOE Project Reviews
DOE Critical Milestone Reviews require technical reviews to have been completed for all project elements
CD-1 : Conceptual Design Reviews
CD-2 : Preliminary Design Reviews
  Project baselining
CD-3 : Final Design Reviews
  Construction approval

## Slide 5: Connection to Component Production
Various stages of component production should ideally be proceeded by a successful review
Preliminary Design Review – Initiates production of components for large-scale prototypes
Final Design Review – Initiates production of module zero components
Production Readiness Review (PRR) – Initiates production of final detector components

## Slide 6: ND Status
Conceptual design review completed last summer
Moving towards holding Preliminary Design Reviews
  Required for DOE CD-2 review and release of Technical Design Report (2022?)
  Beneficial to hold as soon as possible (for example, will provide additional credibility for DOE CD-1RR review in October)

## Slide 7: ND Preliminary Design Reviews
Targeting time window between Summer 2020 and Summer 2021
Major goal of reviews starting with the PDRs is to ensure that all necessary documentation is in place
  Documentation requirements for each review stage have been (will be) specified
  PDR documentation requirements for consortia PDRs are summarized in attached document

## Slide 8: ND Installation Design Reviews
Installation reviews will be held in conjunction with the reviews of the detector elements
Need to ensure
  Global installation plan incorporating all elements
  Design of common installation infrastructure (for example, cranes and cleanrooms)
  Resource plan for installation infrastructure and coordination team
Consortia documentation requirements for installation reviews outlined in separate, attached document