## Slide 1
Dean (Chip) Edstrom
03/26/2021
IOTA Proton Injector Activities

## Slide 2: Summary of Activities
HLRF Build-out
  Placement of HLRF Components (DONE!)
    325 MHz Klystron / Modulator / Charging Supply / Transformer
  Meeting with Fluids / RF / Drafting
    Electrical Fixed-Price-Contract
    Water Fixed-Price-Contract
    HLRF Distribution
  Low-Energy Beam Transport
    Looking for the stub… Leak check before assembly.
    EID design progress
  Medium Energy Beam Transport
    Updated Wiki
    Beamsheet Complete
  Cable List Updated

## Slide 3: HLRF Build-out
Placement of HLRF Components (DONE!)
  325 MHz Klystron / Modulator / Charging Supply / Transformer
Meeting with Fluids / RF / Drafting
  Electrical Fixed-Price-Contract
    Kermit & Dave Featherston
    Contract in purchasing.
  Water Fixed-Price-Contract
    Yurick Czajkowski
    Price estimate from last year’s budget exercise… No FPC yet.
  HLRF Distribution
    Ding Sun & John Reid
    Off-the-shelf parts

## Slide 4: The 325 MHz HLRF Area Now

## Slide 5: HLRF Distribution (Courtesy: Ding Sun)

## Slide 6: Electrical / Water FPC (Courtesy Steve Wesseln)

## Slide 7: LEBT
LEBT Upstream Stub at NWA
  Odd ‘split-flange’ design
  Needs a leak check
  Adapter to be fabricated
Electrically Isolated Diapragm
  Based on PIP-II design
  13 mm initial aperture

## Slide 8: MEBT
Updated Wiki
  https://cdcvs.fnal.gov/redmine/projects/iota-proton-injector/wiki/MEBT
  Includes updated beamsheet from Sasha R.
Priority #3 after HLRF area & LEBT
  HLRF Area needed for FPCs
  LEBT needed for Test Cage & Source Commissioning

## Slide 9: Cable List
Intended to include all beamline elements & timing
  Broken into 5 primary areas:
    Source (HV Enclosure / Ground Racks)
    Low-Energy Beam Transport
    RFQ
    Medium-Energy Beam Transport
    Timing (ESB to NML)
  Also updated on the Wiki
  Need to update est. lengths