## Slide 1: RunCo Report for IOTA/FAST Meeting 03/26
Linac:
  The LCW PLC CPU was DOA (Tom Z). Finally fixed Monday
  Access (SA) today till Wednesday PM (cable-pull, OSC)
  Try to stay out of tunnel Tuesday –Heavy Work Zone
IOTA: Working on lifetime & aperture & lattice
  Lifetime now ~23 minutes
  150 MeV studies started
  Some aperture issues found: (Sasha A., Jarvis, Brandon)
    Corrected some elements wrt Beam-Based alignment
    D-Right has some aperture issues
  OSC diagnostics installation continues (J. Jarvis)
    (dark boxes, optics, cameras, lasers)
  Kicker timing needs attention (Arden???)
Misc:
  Main Complex Summer Shutdown = June 28 – Sept 12
  FAST Shutdown: ?
  FESS: NML 13.8 kV switch/transformer HV-PM August 3
  FESS: Lab B HV-PM: June?... July?... August?
Notes: Why are you looking down here? Look back at the slide.

## Slide 2: Run Plan for Next Week (March 29)
Today – Wednesday
  Supervised Access till 3/31 evening
    OSC diagnostics installation
    IOTA Cable-pull
  Run beam in IOTA 3/31 evening for:
    lattice tunning
    aperture studies
Shutdown for IOTA cable-pull TBA
  ~Monday, 3/29 to Wednesday 3/31
    Need 600 section beamline protected
      8020 & plywood: Today & Monday
      Water Group Q601-2-3: Monday AM & Wednesday PM