## RPS
Assessment Topic | Reason / Justification for Assessment | Requirements (i.e. EPA Regulation, 10CFR835 Requirement, Internal etc.) | Assessment Scope / Criteria | Assessor(s) | Frequency | Fiscal Year | Scheduled Completion Date | Actual Completion Date | Status | Link to Report | iTrack Review ID & Link
Permanent Shielding | visual verification of permanent shielding in the field; compare against as-built civil drawings and/or approved assessments | FRCM | create procedure | RPS, as assigned | annual | 2020 | 2020-10-01 |  | ongoing
Moveable Shielding | visual verification of moveable shielding in the field; compare against Moveable Shielding Inventory list and/or approved assessments | FRCM | create procedure | RPS, as assigned | annual | 2020 | 2020-10-01 |  | ongoing
Incremental Shielding Assessment Methodology | update to reflect current practice | Internal | re-write | RPS, as assigned | once | 2020 | 2020-10-01 |  | open
Radionuclide Analysis Facility QA/QC spike preparation | verify uniform process for QA/QC performance indicator | Internal | RAF SOP #75 | RSP, as assigned | once | 2020 | 2020-10-01 |  | open
Dosimetry Program | RPP element | 10CFR835 | specified in Dosimetry Program Requirements | RPS, as assigned | triennial | 2021 | 2021-10-01 |  | ongoing
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If one-time assessment list "once"

## RPE
Assessment Topic | Reason / Justification for Assessment | Requirements (i.e. EPA Regulation, 10CFR835 Requirement, Internal etc.) | Assessment Scope / Criteria | Assessor(s) | Frequency | Fiscal Year | Scheduled Completion Date | Actual Completion Date | Status | Link to Report | iTrack Review ID & Link | Priorities
Dept. Procedures Assessment | Organize and justify the use of AD and ESH department procedures after merging Interlocks from AD. See what procedures Instrumentation uses. |  | AD ESH Procedures (ADDP) | Adam Olson, Randy Zifko, Mark Zientarski | 1 year | FY2020 | 2020-08-31 |  | PLANNED |  | 53109 |  | who can I delegate this with?
MUX Program Assessment | Identify MUX driving requirements and stakeholders. | 10 CFR 851, 420.1C, FRCM, Fermilab Engineering Manual, Worksmart Set | Regulatory/Laboratory requirements, organizational requirements, technical constraining requirements | Adam Olson, Mark Zientarski, Jonathan Gecht | ad-hoc | FY2020 | 2020-08-31 |  | PLANNED |  | 53107
Scanning Station Locations | Review of the current scanning station locations to assess a)objectively the average location's spatial dimensions and how much they deviate between locations and b) subjectively the accessibility and ergonomics of the area for the scanning station functions. | Internal, project. | Survey a sample of locations and record their spatial dimensions and accessibility/ergonamics. Report findings. | Jamie Clayton, Dan Watson | ad-hoc | FY2020 | 2020-08-07 |  | PLANNED |  | 53106
Instrumentation Team Calibration Procedures | Ensure best practices are used for calibrations and documentation. Identify areas for opportunities. | Worksmart Set |  | Adam Olson, Mark Zientarski | 1 year | FY2020 | 2020-08-31 |  | PLANNED |  | 53108
Check Source Internal Inventory | Ensure all check sources for which the team is responsible are accounted for. | internal organization | Create a list that is available on sharepoint or docDB that documents the inventory of sources at RPCF | Adam Olson,Mark Zientarski | 1 year | FY2020 | 2020-09-30 |  | PLANNED
Engineering Project Tools Assessment | Develop design pipeline and project standards, etc. | Engineering Manual, Quality Assurance | Assess engineering tools (software, equipment, hardware, services) and processes used in engineering projects within the department. | Adam Olson | ad-hoc | FY2020 | 2020-08-31 |  | PLANNED |  | 53111
Instrumentation Program Assessment | Organize, categorize, document the business requirements, activities, and functions of the Instrumentation Program | 10 CFR 851, 420.1C, FRCM, Fermilab Engineering Manual, Worksmart Set | Overall Instrumentation Team Program Assessment | Adam Olson, Mark Zientarski, Jamie Clayton, Jonathan Gecht | 3 years | FY2021 | 2021-09-30 |  | PLANNED
Interlocks Program Assessment | Organize, categorize, document the business requirements, activities, and functions of the Interlocks Program | 10 CFR 851, 420.1C (ASE), FRCM, Fermilab Engineering Manual, Worksmart Set | Overall Interlocks Group Program | Adam Olson, Randy Zifko, Jon Holmes, John Angelus | 3 years | FY2021 | 2021-09-30 |  | PLANNED
Interlocks Test Procedures | Ensure procedures are up-to-date and satsify DOE and lab requirements | FRMC Chapter 10 | FRCM Chapter 10, identify other requirements | Adam Olson, Randy Zifko | 1 year | FY2021 | 2021-09-30
Documentation Map Assessment | Identify all official documentation in the teams |  |  | Adam Olson | 1 years | FY2021 | 2021-09-30
Equipment Inventory Assessment | Document all major equipment |  |  | Adam Olson | 1 year | FY2021 | 2021-09-30
Dept. Spares Inventory | Ensure adequate spares planning is in place for teams. |  |  | Adam Olson | 2 years | FY2021 | 2021-09-30
Software Inventory Assessment | Account for all software used in teams |  |  | Adam Olson | 1 year | FY2021 | 2021-09-30
Software System Assessment | Identify systems like 4D database for status, issues, opportunities, budget etc. |  |  | Adam Olson | ad-hoc | FY2021 | 2021-09-30
Budget and Economics Assessment | Maintain a budget plan and provide budget analysis for decisions |  |  | Adam Olson |  | Y2023 | 2023-09-30
DOE standard on accredidation programs | DOE-STD-1111-2018
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If one-time assessment list "once"

## RPO
Assessment Topic | Reason / Justification for Assessment | Requirements (i.e. EPA Regulation, 10CFR835 Requirement, Internal etc.) | Assessment Scope / Criteria | Assessor(s) | Frequency | Fiscal Year | Scheduled Completion Date | Actual Completion Date | Status | Link to Report | iTrack Review ID & Link
Control of Contamination Areas | Recent concern about how actual and possible contamination areas within the beamline enclosures are posted and controlled to ensure compliance and worker safety | 10 CFR 835 | Review areas with Contamination Area postings or potential contamination areas, to determine how they're posted, controlled & monitored | Maddie Schoell | one time | 2020 | 2020-07-01 | 2020-05-31 | COMPLETE | ESH DocDB 5995 | 53226
10 CFR 835 Triennial | Compliance with 835 requirement. Reviews all aspects of the Radiological Protection Program every 3 years. | 10 CFR 835 | Perform a review against 4 subparts of 10 CFR 835 every year, covering all 12 subparts (with requiremnts) over 3 year cycle. | TBD - from RSSC | every year | 2020 | 2020-05-01 | 2020-05-15 | COMPLETE | ESH DocDB 1557 | 52826
Review of Use and Storage of Radioactive Sources | To evaluate the use and storage of radioactive soruces that are loaned to soruce users and to evaluate how the Soruce Access Log is being used. | No regulatory requirement | Perform and internal review of use and storage of radiaoctive sources that are loaned and stored in source boxes. Perform internal review of completion of Source Access Logs. | Graden, Kathy | every 3 years | 2020 | 2020-09-08 | 2020-10-30 | COMPLETE |  | Review #53586 and Documented on R.P. Form # 106
Nuclear Materials MC&A - Access Controls for Other Accountable Nuclear Materials (OANM) and Protection of the Public | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | one time | 2020 | 2020-08-03 | 2020-09-30 | COMPLETE |  | Review #53587
DOE O 420.2C Triennial | Recommendation from Mu2e Diagnostic Absorber to have a 420 trienneal similar to the 835 trienneal to ensure ASO compliance | DOE O 420.2C | Perform a review against DOE O 420.2c, including other D/S as appropriate. | TBD | every 3 years | 2021 | TBD |  | PLANNED
Configuration Control Log | In addition to recommended DOE O 420.2c trienneal recommendation, the ARR review team also recommended having dedicated review of config. control as part of the trienneal | DOE O 420.2C | Perform a review of the configuration control requirements within DOE O 420.2c | TBD | one time | 2021 | TBD |  | PLANNED
Eating and Drinking in Radioactive Material Areas | Determine where lunch areas are located within RMAs and determine risk assoicated with this areas | No regulatory requirement | Identify eating/drinking areas within RMAs, designate these areas on maps, and determine risks | RPO | one time | 2021 | TBD |  | STARTED
Nuclear Materials MC&A - MC&A plans and procedures | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2021-07-01 | 2021 | 2021-07-01 | - | PLANNED
Nuclear Materials MC&A - Performance tests | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2021-07-01 | 2021 | 2021-07-01 | - | PLANNED
Nuclear Materials MC&A Assessment of Training records, reports, and lesson plans | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2021-07-01 | 2021 | 2021-07-01 | - | PLANNED
Radiological Work Permit | RWP process is in need of revisions to simplify the process and to better meet requirements, and to eliminate inefficiency. | 10 CFR 835 | TBD - would like to tie in review with improvements/inclusion in IMPACT tool. | RPO | ad-hoc | 2022 | TBD |  | PLANNED
Nuclear Materials MC&A Database descriptions | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2021-10-01 | 2022 | 2021-10-01 | - | PLANNED
Nuclear Materials MC&A Categorization process documentation | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2021-10-01 | 2022 | 2021-10-01 | - | PLANNED
Nuclear Materials MC&A - Incident reporting process and procedures | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2021-10-01 | 2022 | 2021-10-01 | - | PLANNED
Nuclear Materials MC&A - Emergency response plans and facility procedures | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2021-10-01 | 2022 | 2021-10-01 | - | PLANNED
Nuclear Materials MC&A - Material transfer records | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2022-01-01 | 2022 | 2022-01-01 | - | PLANNED
Nuclear Materials MC&A - Nuclear Material Management and Safeguards System (NMMSS) reports | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2022-01-01 | 2022 | 2022-01-01 | - | PLANNED
Nuclear Materials MC&A - Material Balance Area (MBA) account structure | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2022-01-01 | 2022 | 2022-01-01 | - | PLANNED
Nuclear Materials MC&A - Internal control procedures | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2022-01-01 | 2022 | 2022-01-01 | - | PLANNED
Nuclear Materials MC&A - Material access program | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2022-04-01 | 2022 | 2022-04-01 | - | PLANNED
Nuclear Materials MC&A - Facility procedures | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2022-04-01 | 2022 | 2022-04-01 | - | PLANNED
Nuclear Materials MC&A - Inventory difference program | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2022-04-01 | 2022 | 2022-04-01 | - | PLANNED
Nuclear Materials MC&A - Material control indicator program | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2022-04-01 | 2022 | 2022-04-01 | - | PLANNED
Nuclear Materials MC&A - Materials containment documentation | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2022-04-01 | 2022 | 2022-04-01 | - | PLANNED
Nuclear Materials MC&A - Material surveillance procedures | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2022-07-01 | 2022 | 2022-07-01 | - | PLANNED
Nuclear Materials MC&A - Search procedures | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2022-07-01 | 2022 | 2022-07-01 | - | PLANNED
Nuclear Materials MC&A - Authorization access lists | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2022-07-01 | 2022 | 2022-07-01 | - | PLANNED
Nuclear Materials MC&A - Shipper/receiver difference procedures and records | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2022-07-01 | 2022 | 2022-07-01 | - | PLANNED
Nuclear Materials MC&A - Portal monitor records and procedures | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2022-10-01 | 2023 | 2022-10-01 | - | PLANNED
Nuclear Materials MC&A - Tamper-indicating device program | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2022-10-01 | 2023 | 2022-10-01 | - | PLANNED
Nuclear Materials MC&A - Daily administrative check program and procedures | Required by DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) | DOE O 474.2, Nuclear Materials Control & Accountability (MC&A) DOE S&S Review Lines of Inquiry | Graden, Kathy | 2022-10-01 | 2023 | 2022-10-01 | - | PLANNED
Access and Exposure Prevention of Radiological Hazards to Unqualified Workers or Members of the Public | This review will cover programs, processes & documentation used to implement the requirements of DOE O 420.2c Safety of Accelerator Facilities and the associated Contractor Requirements Document (CRD). | 10 CFR 835 | This review will cover programs, processes & documentation used to implement the requirements of DOE O 420.2c Safety of Accelerator Facilities and the associated Contractor Requirements Document (CRD). | RPO | one time | 2020, 2021 |  |  | PLANNED
Area Monitoring in Response to FSO Dose to Public Concerns | DOE FSO dose to public concerns | 10 CFR 835 | In order to address this, and identify any areas of potential concern, Fermilab will perform cursory beam-on surveys as the accelerator beamlines resume operation following the 2020 shutdown | RPO |  | 2020, 2021 |  |  | STARTED
Beam-On Surveys in Response to FSO Dose to Public Concerns | DOE FSO dose to public concerns | 10 CFR 835 | In order to address this, and identify any areas of potential concern, Fermilab will increase site-wide area radiation monitoring on a routine, quarterly basis. | RPO | one time | 2020, 2021 | TBD |  | STARTED
RPO Procedure Review - Initial | Review current procedures related to radiological protection (lab-wide and division specific) to determine where division procedures should be lab-wide and update content as needed. | All DOE Orders & Notices included in FNAL contract Appendix I: | All current ESHQ, ADSP, ADAP, ADDP, etc. related to the radiological protection program. Develop procedure layout for merging procedures. Determine what needs to be lab-wide for rad. workers, and where these procedures should "live". Determine what needs to be lab-wide for RCTs. Include SOP signature page for RCT procedures. Establish frequency for review of all procedures (suggest 5 years) (stagger review by dates to ensure not all of the now updated procedures are due at the same time). | Maddie Schoell, Matt Quinn | once | 2021 On-going |  |  | STARTED
Radiological Postings |  | 10 CFR 835 Fermilab Accelerator Safety Envelope | Review radiological postings to ensure consistency in how areas are posted and wording of postings (not the semi-annual posting/fence audit, which is intended to replace missing/faded signs) to ensure areas posted as required (835, ASE, etc.). |  | every 3 years | every year |  |  | PLANNED
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If one-time assessment list "once"