## Slide 1: RunCo Report for IOTA/FAST Meeting 04/09
Linac:
  Cable-pull stuff removal needs to be scheduled
IOTA: Working on lifetime & aperture & lattice
  Some aperture issues found, some corrected
    (Sasha A., Jarvis, Brandon)
  150 MeV studies started
    IBEND PS is being re-tapped to 460 A (+5%)
  OSC commissioning continues (see J. Jarvis)
    (lattice, e-/PU/KU alignments, tuning, LOCO)
  Cables pulled for OSC & IOTA being terminated
    Work to occur during morning CAs
  MPS timing work started (see Chip)
  Need ACNET alarms making noise in the FCR
Dates:
  Main Complex Summer Shutdown = June 28 – Sept ~12 (HEP 10/04)
  FAST Shutdown: end of June???
  FESS:
    FESS is in the process of switching the site from Heating to Cooling in April
    NML 13.8 kV switch/transformer HV-PM August 3
    Lab B HV-PM (Cryo): July23 or July 30 or August 3?
    Master Sub Outages: August 30 & September 07 & September 13
  BEAMSSRV1\groups\nmlscrf.bd has exceeded 95% of its quota (72 GB)
Notes: Why are you looking down here? Look back at the slide.

## Slide 2: Run Plan for Next Week (April 12)
Monday – Friday
  Monday Morning CA (till 14:00)
    Cryo at 5K for morning Kinney work, 2K by 2PM
  CA in the mornings (w/ RunCo approval)
    OSC diagnostics installation
    IOTA Cable termination and clean-up
  Run beam in IOTA after noon for:
    lattice tunning
    aperture studies
    150 Commissioning