## Slide 1: Lessons Learned
Jefferson Lab Scheduled Maintenance Down and Restart During COVID
Harry Fanning
Thomas Jefferson National Accelerator Facility

## Slide 2: Lessons Learned - Overview
Terminology
End of Physics Run / SAD 2020–2021
Complications, Challenges and Opportunities
Restoration of CEBAF Accelerator
Parting Thoughts/Questions

## Slide 3: Lessons Learned - Terminology
CHL – Central Helium Liquefier
I.G. – Inspector General
IGBT – Insulated Gate Bi-polar Transistor
PM – Preventative Maintenance
PPE – Personnel Protective Equipment
PSS – Personnel Safety System
  PPS – Personnel Protection System
QEW – Qualified Electrical Worker
R&D – Research and Development
SAD – Scheduled Accelerator Down
  A scheduled maintenance period for prolonged projects, multiple tasks or preventative maintenance activities
SAD – Safety Assessment Document
  JLab uses Final Safety Assessment Document - FSAD, but doesn’t stop confusion when we use SAD interchangeably

## Slide 4: Lessons Learned – End of Physics Run / SAD 2020–2021
Planned Physics Run end was extended to allow Physics to obtain the last bits of data for FY20 Physics Run to compensate for COVID related issues/delays in program
Physics was halted on September 21st, 2020
  2020-21 Scheduled Accelerator Down commenced

## Slide 5: Complications, Challenges and Opportunities
Unexpected Outages
  Power
    Weather Related (on and off-site)
    Automobiles vs. Transformer Poles (offsite)
    Line Feed Issues from aging hardware (onsite and offsite)
  HVAC for Accelerator Service Buildings
    Chilled water loop system developed a leak at propylene glycol valve
      Outage started in December 2020
      Repairs completed April 2021 (mainly parts availability)
Box Power Supply PMs found Unexpected Issues
  IGBTs on some box supplies were leaking liquid onto electronics
    Thermal Gel breakdown inside IGBT – (age, heat, original formula?)
    Failed IGBTs were replaced with ready spares
  While testing Box Power Supplies with replacement IGBTs, some failed rather dramatically
    Failed replacement parts had multipoint failures
      Some arced while some just shorted out
      “Bad Batch” were all obtained between 2015-2019 from same vendor
    Closer inspection showed manufacturing issues
    Manufacturer contacted – discrepancies found in samples evaluated by manufacturer
    I.G. is investigating possible 3rd party vendor issues – Report Pending
“Acts of God”

## Slide 6: Complications, Challenges and Opportunities
Isotope R&D Run
  The experiment setup process was well planned and followed
    Successfully tested/verified many features with beam before the isotope was added to the target crucible
  During final beam setup, a downstream magnet mismatched
    Control System did not alert crew of the mismatch
    Diagnostics could have been enhanced to detect issue
  The mismatch caused a vacuum leak at the exit window just before the target
    The exit window was initially suspected as the origin of leak, but later determined to be a vacuum flange warmed by the missteered beam
  Due to the vacuum failure the R&D experiment was ended before appreciable results could be obtained
  Future plans for isotope R&D are on hold
Hall A HVAC
  Equipment aging - planned outage/replacement scheduled early on
  Project delayed by COVID related delays w/ subcontractor and suppliers
    Delays prompted a shorted install period
    Demo of old unit postponed to a later date
    Installation was modified to “temporarily” install on old detector structure (not in use)

## Slide 7: Complications, Challenges and Opportunities
Hall A Overhead Crane
  Crane mounts were found to have structural issues during routine inspection
    Mounting points were weakened over 30 years of use
    Spare parts and subcontractor limited by COVID and schedules
    Inability to use overhead crane delayed planned projects / experiment change out
      Contracted mobile cranes
Hall A Beam Dump Inspection
  Corrosion found on outer protective shell (11th hour before Physics start)
    Repairs required welding patches to seal leaks and weak points
    Earlier periodic inspections had not detected corrosion
      Inspection periodicity modified
COVID Protocols
  Reduced on-site personnel during most of SAD
    Resources limited for planned projects – extended original SAD estimates
  Vaccination of Staff
    Not available in area until January – February 2021
    Initial age restrictions put in place by state and local regions
    Not all employees eligible to get vaccinations until April +
    Some staff were reluctant to obtain an “unapproved” vaccination even after they became eligible
      As of late Sept – 78.2% of JLab staff declared vaccinated

## Slide 8: Complications, Challenges and Opportunities
COVID Protocols MedCon 5
  PPE & Expectations
    PPE
      Work >6ft apart – Approved face coverings
      Work <6ft apart – N95 mask w/ training, nitrile gloves, Tyvek®/coveralls with hood and face shield/goggles
    Social distancing
      Daily Health Check List and Pre-Job Briefings
      Work >6ft apart
      No in-person meetings/Outdoor >6ft – Telework maximized
      Person Loading limits (170ft2 minimum/person)
      Cubical Areas limited to every other cubical – no adjoining cubical & Plastic shields
COVID Protocols MedCon 4
  PPE & Expectations
    PPE
      Work >6ft apart – Approved face coverings
      Work <6ft apart – N95 mask w/ training, nitrile gloves, cloth coveralls and safety glasses or goggles (Unvaccinated workers only)
    Social distancing
      Daily Health Check List and Pre-Job Briefings
      Work >6ft apart (Unvaccinated workers only)
      Limit In-person meetings – Outdoor/Large Area recommended – Telework preferred
      Office space with closed doors – no restrictions
      Cubical areas – Vaccinated no restrictions

## Slide 9: Complications, Challenges and Opportunities
COVID MedCon 5 & 4 – Complications
  Initial PPE requirements had to be evaluated by the Jlab Doctor due to work tasks not matching COVID PPE
    U-Tube operations (<6 ft)
      Long duration in Tyvek® suits caused overheating in workers
      Suits would not last long during heavy work activities (tears, splits, etc.)
        Cloth coveralls were evaluated and approved for use
      Nitrile gloves would not last longer than one activity of a task
      Work gloves added over nitrile sometimes made tasks more difficult
        Work gloves alone were evaluated and approved for use – no communal sharing!
    Welding activities (<6ft)
      Normal Tyvek® suits not recommended during hot work activities
      Hot work Tyvek® suits caused overheating and were expensive
        Fire retardant coveralls were evaluated and approved for use
      Masks worn underneath the weld masks caused inability to see work during welding
        Anti-fog wipes not effective
      Keep-out zones established around weld areas
        Helpers needed full PPE
    Electrical Workers (>6ft or <6ft)
      QEW PPE is normally communally stored in designated areas
        COVID protocols make this difficult to continue
        Shared PPE would need decontamination = time out of service before next use
        Additional PPE protocols may not be fire retardant

## Slide 10: Complications, Challenges and Opportunities
COVID MedCon 5 & 4 – Complications
  Personal PPE was mandated for all tasks
    PPE cannot be shared among crews
      This included QEW and other specialized PPE
  Lead times elongated for COVID PPE and specialized PPE due to manufacturer shortages
    Postponed tasks requiring PPE
    Staff needed training on certain PPE use once arrived
  Personnel loading of buildings complicated matters
    Practical training centers could not operate in pre-COVID fashion
      Dress-out procedures in training had to be modified
        Bring your own personal PPE – no shared PPE
        Personnel loading and social distancing during training limited class size
      Testing scheduled with cleaning intervals between tests/practical
    Obtaining radiation badges
      Due to personnel loading constraints, the location was moved to a larger building
      Testing scheduled on days when instructors available on-site
      New scheduling tool used to coordinate testing/practical dates
    Placing on-site workers
      Office worker’s spaces (working from home) converted for on-site workers
      Cubical spaces cut in half (or more) to comply with loading limits

## Slide 11: Restoration of the Accelerator
Due to the work ongoing in the CEBAF machine, a phased restoration schedule was planned
  Normally maintenance activities would be completed before machine restoration activities started
  To give more time for commissioning, a coordinated plan was followed
March 2021
  Started Injector commissioning after extensive equipment replacement
  Warm Startup of CHL1 commenced around the same time
May-June 2021
  PSS Certifications
    Bi-Annual checks
    Check of new Hardware
    Verification of New/Old logic
  Tunnel Clean-up
    Personnel Loading restrictions limit personnel participation
    Available ON-SITE personnel only (can’t do it virtually!!!)
    No refreshment incentives (COVID restrictions on Pizza parties) 
    Reduced scale of clean-up due to limited resources

## Slide 12: Restoration of the Accelerator
June 2021
  NL05 commissioning starts
  Beam to 500keV region of Injector
  North LINAC RF ON – Low Gradient
  IGBT swaps in affected Box Supplies
July 2021
  Tornado Warning
    CEBAF secured immediately
      Not all systems recover easily after forced shutdown
  Injector Commissioning continues
  North LINAC RF commissioning
  NL07 (P1-R) commissioning
  Box Power Supplies testing
  Cold Startup of CHL1
  Beam to Arc 1 Recombiner (1R)

## Slide 13: Restoration of the Accelerator
August 2021
  Beam to Arc 2 Recombiner (2R) (1st Pass)
  Further IGBT checks after replacement
  980MeV/LINAC to 910MeV/LINAC
  5 Pass setup starts
September 2021
  Beam to Hall B
    Physics starts Sept 1st
  5 Pass Setup Complete
  Beam to Hall C
    Physics starts Sept 8th
  Beam to Hall D
    Physics starts Sept 16th
Expecting Beam to Hall A ~ October 4
  All 4 endstations will be receiving physics simultaneously

## Slide 14: Lessons Learned – Questions?
Harry Fanning
fanning@jlab.org

## Slide 15
Additional Slides

## Slide 16: Lessons Learned –SAD 2020–2021
Major SAD activities shown here, (far more not listed)
CHL1 was taken down as soon as LINAC was warmed up
  CHL1 was scheduled for a complete overhaul
    Old compressors and turbines removed/replaced
    Electrical systems were gutted and replaced
    Controller hardware was replaced and software updated
    Cryo-connections (U-Tubes) were refitted for new Compressor
    Lots more work to list here…
Injector Front End Upgrade
  Outdated gun and optics hardware replaced or removed completely
  Software for Injector hardware updated
  Diagnostics updated or enhanced

## Slide 17: Lessons Learned – SAD 2020–2021 (cont.)
Accelerator Planned PMs
  Most major systems
    Site Power Substation PMs
    Emergency Power Generator PMs
    Magnet systems PMs
  Even minor systems were included
    Annual Breaker Panel Exercise and PMs
Fire Pipe Replacement in Tunnel
  Older fire pipe had leaks and showing age
  Almost a mile of piping needed to be replaced
  Nitrogen backfill system added to reduce future corrosion
Experimental Hall Equipment Change Out (normal)
PSS Upgrade
  Hardware and Software
  Very little Logic changes

## Slide 18: Lessons Learned – SAD 2020–2021 (cont.)
Survey and Alignment check of all magnet stands
  Recent Surveys showed shifting of equipment
    Earthquake related?
    Constant extreme temperature changes between SAD/Run related?
    Normal and expected small shifts, etc.
North LINAC Cryomodule Upgrades
  NL05 – C30 to C-75
  NL07 – C50 to C-75 (P1-R)
Service Building Chilled Water Pipe Repair
Copper 67 Isotope R&D Run (January 2021)
Tunnel Water Leak Remediation
  Various historic ground water leaks were remediated with a new product
    results pending…