## Slide 1
Dean (Chip) Edstrom
04/16/2021
IOTA Proton Injector Update

## Slide 2: Safety
Documentation
  SAD amendment, including a USID (which was not enforced previously)
    Enclosure model needed – Steve Wesseln will work on this next week
  CDC justification form
    Likely GV301 & Ion Source high voltage (N:PS)
Additional radiation monitors for the RSS likely unnecessary
  based on the energy of the proton beam (max = 2.5MeV)
  To be verified with SAD addendum
The ESS will provide a closed contact for the 325 MHz LLRF
  Necessary for the RFQ
  LLRF expects a TTL signal to be sourced from the 325 MHz RF area (e.g. RF PLC)
RF Switch Mode Controller
  Dummy Load / RFQ
  Will likely live in the 325 MHz RF area
Beam Switch
  Universal beamswitch for FAST?

## Slide 3: 325 MHz RF
Build-out
  Design approved by all major parties
    RF (John & Ding) / LCW (Yurick) / Electrical (Kermit)
    Steve Wesseln will provide top-down drawing and a few 3D views of the full layout early next week
    As of 4/15 Steve still needed the RF Switch dimensions
  Fast Interlocks in progress
    Details on the next slide
  Slow Interlocks PLC components in hand
  LLRF
    Being built by Euclid Techlabs
    EPICS 7 interface – No real forward progress yet
  Mode controller
    À la Electron Gun & CM

## Slide 4: 325 MHz RF Fast Interlocks – Peter / Ding / John
RFQ/Klystron (waveforms):
  PMT#1 -> Klystron window
  PMT#2 -> Transmission line (Kermit wanted)
  RF #1 from Klysrton's reflected port
  RF #2 Forward signal from Klystron forward port or from directional coupler #1 (before circulator) forward port or both.
  RF #3 Reflected signal from directional coupler #1. (before circulator)
  RF #4 Reflected signal from directional coupler #2 (after circulator)
  RF #5 Reflected signal from directional coupler #3. (after adjustable coupler)
  RF #6 Reflected signal from 3 1/8" directional coupler #4 before RFQ
  RF #7 Reflected signal from 3 1/8" directional coupler #5 before RFQ
Buncher (waveforms):
  RF #8 forward signal
  RF #9 reflected signal
RF Cavity Probes (waveforms):
  A selection of RFQ/Buncher cavity probes
    There are 24 total for the RFQ alone, but we probably want/need to monitor waveforms for a few of these
Levels:
  Klystron Solenoid
  Pressure (I think we are planning on pressurizing at least part of the 6" line... how many channels?)
  RF leak detection
  Cavity vacuum
  Modulator status
  An auxiliary sum (klystron vacuum, LCW, etc)

## Slide 5: The 325 MHz HLRF Buildout
  Location of Klystron, Circulator, Variable Tap, RF Switch.
  Final alignment of WR Klystron output.
  Install the Pb shield on the Klystron.
  Electrical fixed-price contract.
  80-20 stands for the circulator and variable tap.
  Alignment of the circulator and variable tap.
  Anchor the circulator and variable tap stands.
  Water fixed-price contract.

## Slide 6: IOTA Proton Injector Beamline - Fabrication
IS LEBT RFQ MEBT D604
Split flange to scraper adapter
  In progress
Electrically Isolated Diaphragm (EID)
  Initial 10 mm aperture
  In progress
RFQ upstream flange rework
Diamond long. profile detector (X332)
RFQ/T310 ceramic rework
  KF to Conflat
Dogleg bend chambers (D330 / D340)
T301 ceramic spool
T344 ceramic spool
1
2/3
4
4
5
6
7
7
8
9

## Slide 7: Engineering & Instrumentation
Vacuum analysis underway
  Will inform us of need for additional pumpout ports / gauging
  RGA? – Just proposed.
-150V 4-Channel LEBT Bias Current monitor
  Final Source Electrode
  LEBT Scraper (2 Channels)
  EID
Toroids (3x) & Wall Current Monitor
  In hand
Scanning Wires
  Borrow / Adopt from PIP-II IT
  Vacuum chambers will be our own
LEBT Allison Scanner
  Borrow from PIP-II IT (NML Gallery Commissioning Only)
MEBT Allison Scanner
  Borrow from PIP-II IT (Electronics in ESB)
Diamond longitudinal profile detector
  Borrow / Adopt from PIP-II IT
  Vacuum chamber will be our own

## Slide 8: Source Assembly
Hydrogen Distribution is coming together
  Need to start working on the interlocks box…

## Slide 9: Source / LEBT
The Source Stand (red) may be removed from the cave
  Stand-alone 50 keV studies
  Includes Upstream LEBT Solenoid
The LEBT includes the following components:
      Solenoids
        Scraper Assembly
          Toroid
            Gate Valve
              Electrically Isolated Dipragm (EID)

## Slide 10: Timeline
Electrical Fixed Price Contract
  Late-April to Mid-May: Begin everything that can be done before power outage
  Late June: IOTA Shutdown
    Power outage for RF Gallery Tie-in
    Begin assembly of Beamline
    Assemble and recommission the 50 keV source / LEBT in NML Gallery
    Cable Pulls